## Summary
Project Name | Highway Construction Project
Project Code | HC-2024-001
Reporting Period | December 2024
Total Budget | 50000000
Actual Expenditure | 35000000
Physical Progress | 65
Financial Progress | 70

## Annexure-A
PROJECT OVERVIEW
Project Name | Highway Construction Project
Location | State Highway 45
Client | State PWD
Contract Value | 50000000
Start Date | 2024-01-01
End Date | 2025-12-31
MILESTONES
Description | Planned Date | Actual Date | Status
Site Mobilization | 2024-01-15 | 2024-01-20 | Completed

## Annexure-B
PHYSICAL PROGRESS
Activity Description | Unit | Planned Qty | Actual Qty | Progress %
Earthwork | CUM | 100000 | 65000 | 65