## Sheet1
P&Loss Working
S.No | Description | MMR
a | WD | 3288.8523
b | Escl etc | 212.4709
| addl claim | 0
| other income | 44.8253
a+b | Total Revenue | 3546.1484
Less Exp
c | Paid to project | 1604.975
d | Cen payments | 670.1291
d | tax | 56.39
e | pol | 170.54
| pay& Allces | 147.588
f | payable ( Add ) | 92.3585
g | Total Expenes | 2741.9806
h | Less Invetory of proj | 23.2323
j | Total Expenes | 2718.7483

## Summary
SUMMARY OF MONTHLY MONITORING REPORT
Rs in Million
,.
1 | Proj Con |  |  | PMU NLC Chahar Bagh LHR
2 | Name of Proj |  |  | PMU NLC INFRA DEV WORKS at Chahar Bagh (RUDA )
3 | Month |  |  |  | July 2025
4 | Progress
| a. | Physical |  |  | As per Contract Cost
|  | (1) Planned Targets |  |  | 3307.223
|  | (2) Achieved |  |  | 2987.5098
5 | Schedule of Proj
| a. | Start Date of Project |  |  | 2022-11-02
| b. | CA Date of Completion |  |  | 2024-11-02
| c. | Date of Completion as per actual site. |  |  | 2025-07-15
6 | Financial State
| a. | Original Cost of Proj |  |  | 3034.216
| b. | Revised Cost (approx) Addl Work |  |  | 528.982
| c. | Funds Received from Client |  |  | 2532.2316 | 3034
| d. | Cost of Work upto Previous Month Incl Escl |  |  | 3454.5319 | -529.198
| e. | Cost of Work Done during the month by Proj Con / Own WD |  |  | 21.4588
| f. | Cost of Work Done during the month by Petty Contrs |  |  | 2.3323
| g. | Total Cost of Work Done during the month by Proj Con / Hired Lab & Petty Contrs (e+f) incl ESCL |  |  | 46.7912
| h. | Total Cost of Work Done till to date (d+e) |  |  | 3478.3231
| j. | Other Income against (MT, Lab & Handling Charges) |  |  | 44.8253
| k. | Total Revenue (j+h) |  |  | 3523.1484 |  | 15.3435 |  | 2.872 | Previous
| l. | Assets |  |  | 30.5086 |  | 3207.4136 |  | 92.3585 | current
| m. | Exp upto last month |  |  | 3207.4136 |  | -3192.0701 |  | -89.4865 | Difference (Prev Liab - Current Liab
| n. | Exp during the month |  |  | 48.2963 |  |  |  | -3102.5836 | Current - Difference
| o. | Total Exp till to date (m+n) |  |  | 3255.7099 |  |  | Liability reduced - Anx-M | -89486506.4055
| p. | Liabilities till to date as per Anx 'M' |  |  | 92.3571 |  |  | I. Tax @ 7% | 106400
| q. | Total Cost of work done excl Escl |  |  | 3501.3231 |  |  | RM | 4398
| r. | Total Cost of vetted work |  |  | 2972.3981 |  |  | Less Payment | 23000
| s. | Slippage (q-r) |  |  | 457.1058 |  |  | Workdone NLC - Anx B | 583320
| t. | Escalation clamied / Other Claims |  |  | 212.4709 |  |  | Provision @ 1% | 35683 | -3192070062.6299
| u. | Any Other Claims |  |  | 0 |  |  |  | -88733705.4055 | -3103336357.2244
| v. | Financial Health
|  | (1) | Based on vetted work done |  | -238.4976
|  | (2) | Based on Work Done |  | 290.4274
7 | Reasons for Delay in Progress
8 | Any Special Activity Carried out
9 | Remarks:
i) Payment of Vetted IPC # 18 of Amounting to Rs.267.775 Mn. yet not Released.

## Anx A
Anx 'A'
PROJ HIGHLIGHTS AS ON July 2025
PMU NLC INFRA DEV WORKS at Chahar Bagh (RUDA )
1 | Schedule of Project | [8 empty] | 9164300 | office estb exp
| a. Date of Commencement | [5 empty] | 2022-11-02 |  |  | 381845.8333
| b. Date of Completion | [5 empty] | 2024-11-02
| c. Date of Completion as per acutal site | [5 empty] | 2025-07-15
2 | Client / Consultant | [5 empty] | RUDA /NESPAK
3 | Progress |  |  |  |  | UPTO DATE WORK
| Work Done |  |  |  |  | Rs (Million) | %age |  |  | -0.003 |  | 2.0803
|  | (1) Planned Targets |  |  |  | 3463.223 | 97.19%
|  | (2) Achieved |  |  |  | 3288.8523 | 92.3% | 0 |  |  |  | 0.068
4 | Financial State | [5 empty] | Rs (Million)
| a. Original Cost of Project as per Contract Agreement | [5 empty] | 2889.7297
| b. Revised Cost Est Cost ( Incl PSt 5% ) | [5 empty] | 144.486
|  |  | Total Cost incl Pst 5% |  |  |  | 3034.216
| b. Revised Cost of Project as VO | [5 empty] | 3393.522 |  | 1.1329
| d. Revised Cost Est Cost ( Incl PSt 5% ) | [5 empty] | 169.676 | 2497.204
|  |  | Revised Cost incl Pst 5% |  |  |  | 3563.198 |  |  | 2409.4633 | 2453.15 | -43.6867
| c. Total Funds Received from Client incl mob adv | [5 empty] | 2532.2316 |  |  | 635.948 | 679.634 | -43.686
| d. Total Funds Released to Project | [5 empty] | 1604.975
5 | Income State (Based on Actual Profit Achieved)
|  |  | Work Done |  |  | Vetted Work
|  |  | During The Month | Upto Date | Year to Date | Upto Date | Year to Date | [5 empty] | -3288.8523
Revenue of Proj
|  | Workdone | 23.7912 | 3288.8523 | 23.7912 | 2831.7464 | 0 | 3265.0611 | 0 | 971.982 | 971.982 | 457.1058
|  | EPC's | 23 | 212.4709 | 23 | 140.6517 | 0 | 189.4709 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Work Done | 46.7912 | 3501.3231 | 46.7912 | 2972.3981 | 0 | 3454.5319 | 0 |  | 0 | 528.925
|  | Direct Cost | 43.912 | 3070.7434 | 43.912 | 3070.7434 | 43.912 | 3026.8314 | 0 | -600.6114 | 0
|  | Gross Profit | 2.8792 | 430.5797 | 2.8792 | -98.3453 | -43.912 | 427.7005 | 0 |  | 0
|  | Gen & Adm Exp | 4.3843 | 184.9664 | 4.3843 | 184.9664 | 4.3843 | 180.5821 | 0 |  | 0
|  | Operating Profit | -1.5051 | 245.6132 | -1.5051 | -283.3117 | -48.2963 | 247.1184 | 0 |  | 0 | 0
|  | Financial Charges | 0 | 0.0111 | 0 | 0.0111 | 0.0105 | 0.0111 | 0 |  | 0
|  | Other Income | 4.469 | 44.8253 | 4.469 | 44.8253 | 4.469 | 40.3563 | 0 |  | 0
|  | Net Profit (Million) before tax | 2.9639 | 290.4274 | 2.9639 | -238.4976 | -43.8378 | 287.4636 | 0 | 250.866 | 0
|  | Net Profit %age | 6.334% | 8.295% | 6.334% | -8.024% | #DIV/0! | 0.019606 | 0 | 40.369
36.5976
|  |  | Work Done |  |  | Vetted Work
|  |  | During The Month | Year to Date | Uptodate | Upto Date | Year to Date
Revenue of Proj
|  | Workdone | 23.7912 | 3288.8523 | 23.7912 | 2831.7464 | 0
|  | EPC's / Other Claims | 23 | 212.4709 | 23 | 140.6517 | 0
|  | Total Work Done | 46.7912 | 3501.3231 | 46.7912 | 2972.3981 | 0
|  | Direct Cost | 41.6441 | 3116.1776 | 41.6441 | 2645.4343 | 0
|  | Gross Profit | 5.147 | 385.1455 | 5.147 | 326.9638 | 0 | 88.45
|  | Gross Profit % | 11% | 11% | 11% | 11% | #DIV/0!
Financial Charges
Other Income
|  | Net Profit (Million) | 5.147 | 385.1455 | 5.147 | 326.9638 | 0
|  |  | 11% | 11% | 11% | 11% | #DIV/0!
6 | Remarks of PM/PD :_
Other Income incl sale of concrete to private contr for Rs 2.346 Million

## Anx B
Anx "B"
MONTH - July 2025
DETAIL OF WORK DONE BY NLC / HIRED LABOUR | [22 empty] | 2147.9767 | 599.6853 | 2003.2429 | 674.1199
PMU NLC INFRA DEV WORKS at Chahar Bagh (RUDA )
[19 empty] | 14.8 |  | 453.469
Bill | Activity | Amount Rs in Million | [5 empty] | Previous |  |  |  |  | Running Uptodate |  | Vetted |  |  |  | 233.612 |  | 100.739
|  | Approx cost of own works | Work Done During the Month | Running Total up to Date | Running Total YTD | Vetted Workdone up to Date | Vetted Workdone Year to Date | Work Done During the Month | Running Total up to Date | Running Total YTD | Vetted Workdone up to Date | Vetted Workdone Year to Date | Work Doneuptodate Anx-C | Anx-B+C | C | B+C |  |  |  |  | 554.208 | 558.408 | 4.2
1 | Earth Work & Allied Activities | 282.989 | -3.726 | 501.0628 | -3.726 | 477.163 | 0 | 4.268 | 504.7888 | 54.2008 | 477.163 | 34.7379 | 91.845 | 592.9078 | 108.115 | 585.278 | 56.467 | 367.037 |  | 500.5208 | 49.9328 | 474.129 | 31.704 | 0.542 | -53.6588 | 3.034 | -31.704
2 | Sub base Course | 341.571 | -7.955 | 278.6808 | -7.955 | 271.1103 | 0 | 14.736 | 286.6358 | 144.4525 | 271.1103 | 188.8237 | 24.8149 | 303.4958 | 24.8149 | 295.9252 |  |  |  | 260.3998 | 118.2165 | 237.4113 | 155.1247 | 18.281 | -126.1715 | 33.699 | -155.1247
3 | Surface Course and pavement | 596.161 | -69.597 | 475.0078 | -69.597 | 311.305 | 0 | 204.135 | 544.6048 | 515.0513 | 311.305 | 286.03 | 56.467 | 531.4748 | 56.078 | 367.383 | -107.6248 |  |  | 259.4698 | 229.9163 | 238.4696 | 213.1946 | 215.538 | -299.5133 | 72.8354 | -213.1946
4 | Drainage & Erosion Work | 462.183 | 0.883 | 357.405 | 0.883 | 354.037 | 0 |  | 356.522 | 8.736 | 354.037 | 6.251 |  | 357.405 | 0 | 354.037 |  |  |  | 356.522 | 8.736 | 347.786 | 0 | 0.883 | -7.853 | 6.251 | 0
5 | Ancillary Work | 134.757 | -1.803 | 24.4097 | -1.803 | 2.4442 | 0 | -17.287 | 26.2127 | 19.7981 | 2.4442 | 2.4442 | 20.451 | 44.8607 | 20.451 | 22.8952 |  |  |  | 21.6257 | 15.2111 | 8.207 | 8.207 | 2.784 | -17.0141 | -5.7628 | -8.207
6 | Sewerage Work | 176.207 | -1.273 | 40.9975 | -1.273 | 28.9894 | 0 | -12.543 | 42.2705 | -15.3365 | 28.9894 | -6.4026 | 66.63 | 107.6275 | 69.536 | 98.5254 | 51 |  |  | 70.9915 | 13.3845 | 46.937 | 11.545 | -29.994 | -14.6575 | -17.9476 | -11.545
7 | O/H Water Tank | 216.382 | -2.258 | 462.9279 | -2.258 | 441.461 | 0 | 19.541 | 465.1859 | 196.7994 | 441.461 | 252.3909 | 81.2323 | 544.1602 | 61.213 | 502.674 |  |  |  | 446.7459 | 178.3594 | 418.5319 | 229.4618 | 16.182 | -180.6174 | 22.9291 | -229.4618
8 | Water Supply | 110.538 | 0.039 | 49.1045 | 0.039 | 23.415 | 0 | 0 | 49.0655 | 31.9987 | 23.415 | 11.4327 |  | 49.1045 | 0 | 23.415 |  |  |  | 46.8345 | 29.7677 | 22.4707 | 10.4884 | 2.27 | -29.7287 | 0.9443 | -10.4884
9 | Tube well | 113.278 | 0.001 | 53.9696 | 0.001 | 29.4874 | 0 | 20 | 53.9686 | 46.7656 | 29.4874 | 29.4874 | 7.449 | 61.4186 | 7.449 | 36.9364 |  |  |  | 36.8556 | 29.6526 | 29.487 | 29.487 | 17.114 | -29.6516 | 0.000358 | -29.487
10 | Bdry Wall | 16.437 | -29.93 | 34.6005 | -29.93 | 64.53 | 0 |  | 64.5305 | 0.198 | 64.53 | -0.467 | 21.46 | 56.0605 | 21.4601 | 85.9901 |  |  |  | 73.5705 | 9.238 | 64.332 | -0.665 | -38.97 | -39.168 | 0.198 | 0.665
11 | Entry Gate | 60.337 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0
| BOQ Items |  | 86.645 | 128.946 | 86.645 | 35.684 | 0 | -27.625 | 42.301 | 42.301 | 35.684 | 30.7277 | 94.892 | 223.838 | 74.609 | 110.293 |  |  |  | 33.252 | 33.252 | 33.2548 | 28.2985 | 95.694 | 53.393 | 2.4292 | -28.2985
| Non BOQ items | -5.9258e-05 | 49.411 | 211.5175 | 49.411 | 172.9245 | 0 | 0 | 162.1065 | 78.6645 | 172.9245 | 111.2634 | 0 | 211.5175 | 40.6245 | 213.549 |  |  |  | 137.601 | 54.159 | 120.9191 | 59.258 | 73.9165 | -4.748 | 52.0054 | -59.258
Total (Rs inMillion) |  | 2510.8399 | 20.437 | 2618.6295 | 20.437 | 2212.5508 | 0 | 205.225 | 2598.1925 | 1123.6293 | 2212.5508 | 946.7193 |  |  | 484.3506 | 2696.9014
Add 5% PST |  | 125.542 | 1.0218 | 130.9315 | 1.0218 | 110.6275 | 0 | 10.2613 | 129.9096 | 56.1815 | 110.6275 | 47.336 |  |  | 24.2175 | 134.8451
G Total (Rs inMillion) |  | 2636.3819 | 21.4588 | 2749.561 | 21.4588 | 2323.1783 | 0 | 215.4863 | 2728.1022 | 1179.8108 | 2323.1783 | 994.0553 |  |  | 508.5681 | 2831.7464
0
|  | 3555.024 | -25.6198 | 3077.3348 |  | 156.612 | [14 empty] | 17.9476
| 12+2+7 |  |  |  |  | 134.8451 | [14 empty] | -121.1513
| 9.386 |  | 22.6583 | 3132.2403 | TOTAL Without PST | 2696.9014 |  | 22565 | 13935 | [13 empty] | -147.34
|  |  | 23.7912 | 3288.8523 | TOTAL with PST | 2831.7464 |  | 14118 | 11582 | [11 empty] | -240.518
Note: | Work done reverse due to distribution of NON BOQ and BOQ items.
|  |  | 0.093 | 0.093
|  |  | 0.017 | 0.017
|  |  | 0.014 | 0.014

## Anx C
Anx "C"
MONTH - July 2025
DETAIL OF WORK DONE BY SUB CONTRACTORS
PMU NLC INFRA DEV WORKS at Chahar Bagh (RUDA )
Rupees in Million
Ser | CA No. | Contractor | Activity | Amount Rs in Million | [6 empty] | Previous
|  |  |  | NLC Cost | Sub Contr Cost | Work Done During the Month | Running Total Upto Date | Running Total YTD | Vetted Work Done up to Date | Vetted Work Done YTD | Work Done During the Month | Running Total Upto Date | Running Total YTD | Vetted Work Done up to Date | Vetted Work Done YTD |  | Profit | profit % | cost % | Contr Cost
1 | C/2022/P0460/Chaharbagh Sch Lhr-Petty-4 (Const of Rd Pkg -1 St No. 11,12,13,14,15,16) | M/s Muhammad Rafique Contractor (MRC) | Earth Work | 20.753 | 14.686 |  | 11.548 | 0 | 11.548 | 0 |  | 11.548 | 0 | 11.548 | 0 |  | 6.067 | 29.2343 | 70.7657 | 8.172 | 0 | 14945188 | #DIV/0! | 6.067 | 0.29234
2 | C/2022/P0460/Chaharbagh Sch Lhr-Petty-17 (Const of Rd Pkg-2 St No. 11,12,13,14,15,16) | M/s Muhammad Rafique Contractor (MRC) | Earth Work | 20.753 | 14.686 |  | 16.509 | 0 | 18.067 | 0 |  | 16.509 | 0 | 18.067 | 0 |  | 6.067 | 29.2343 | 70.7657 | 11.6827 | 1.558
3 | C/2022/P0460/Chaharbagh Sch Lhr-Petty-14 (Const of Rd St No. 4,5,6) | M/s Muhammad Rafique Contractor (MRC) | Earth Work | 17.98 | 12.973 |  | 4.228 | 0 | 4.228 | 0 |  | 4.228 | 0 | 4.228 | 0 |  | 5.007 | 27.8476 | 72.1524 | 3.0506 | 0
4 | C/2022/P0460/Chaharbagh Sch Lhr-Petty-15 (Const of Rd St No. 7,8,9) | M/s Muhammad Rafique Contractor (MRC) | Earth Work | 20.262 | 14.612 |  | 4.453 | 0 | 4.574 | 0 |  | 4.453 | 0 | 4.574 | 0 |  | 5.65 | 27.8847 | 72.1153 | 3.2113 | 0.121
5 | C/2022/P0460/Chaharbagh Sch Lhr-Petty-16 (Const of Rd Pkg-1 St No. B-3) | M/s Muhammad Rafique Contractor (MRC) | Earth Work | 17.015 | 12.363 |  | 16.848 | 0 | -1.112 | 0 |  | 16.848 | 0 | -1.112 | -19.072 |  | 4.652 | 27.3406 | 72.6594 | 12.2417 | -17.96
6 | C/2022/P0460/Chaharbagh Sch Lhr-Petty-19 (Const of Rd Pkg-2 St No. 11,12,13,14,15,16) | M/s Muhammad Rafique Contractor (MRC) | Earth Work | 17.689 | 13.698 |  | 11.093 | 0 | 11.093 | 0 |  | 11.093 | 0 | 11.093 | 0 |  | 3.991 | 22.562 | 77.438 | 8.5902 | 0
7 | C/2022/P0460/Chaharbagh Sch Lhr-Petty-21 | M/s Muhammad Rafique Contractor (MRC) | Earth Work | 19.283 | 14.935 |  | 8.894 | 0 | 8.894 | 0 |  | 8.894 | 0 | 8.894 | 0 |  | 4.348 | 22.5484 | 77.4516 | 6.8885 | 0
8 | C/2022/P0460/Chaharbagh Sch Lhr-Petty-27 | M/s Muhammad Rafique Contractor (MRC) | Earth Work | 11.803 | 9.141 |  | 11.797 | 0 | 11.797 | 0 |  | 11.797 | 0 | 11.797 | 0 |  | 2.662 | 22.5536 | 77.4464 | 9.1364 | 0
9 | C/2022/P0460/Chahar Bagh/Lhr/Petty-13 | M/s Focus Engg | Earth Work | 18.392 | 14.23 |  | 15.369 | 0 | 15.369 | 0 |  | 15.369 | 0 | 15.369 | -0.243 |  | 4.162 | 22.6294 | 77.3706 | 11.8911 | 0 | 2445678 | #DIV/0!
10 | C/2022/P0460/Chahar Bagh/Lhr/Petty-6 | M/s Bhatti Associates | Bndry Wall | 7.698 | 6.719 |  | 4.06 | 0 | 4.06 | 0 |  | 4.06 | 0 | 4.06 | 0 |  | 0.979 | 12.7176 | 87.2824 | 3.5437 | 0 | 2445678 | #DIV/0!
11 | C/2022/P0460/Chahar Bagh/Lhr/Petty-5 (Const of Bdry / Wall Pkg-1 L=5267 Ft | M/s Zaid Waqas Engg & Trading | Bndry Wall | 17.199 | 14.967 |  | 0.304 | 0 | 0.30412 | 0 |  | 0.304 | 0 | 0.30412 | 0 |  | 2.232 | 12.9775 | 87.0225 | 0.26455 | 0.000121 | 2996342 | 24763157023.7629
12 | C/2022/P0460/Chahar Bagh/Lhr/Petty-24 (Const of Sewerage | M/s Al-Hafiz Management Works | Sewerage | 16.312 | 14.623 |  | 14.897 | 0 | 14.897 | 0 | 2.112 | 14.897 | 5.071 | 14.897 | 5.071 |  | 1.689 | 10.3543 | 89.6457 | 13.3545 | 0
13 | C/2022/P0460/Chahar Bagh/Lhr/Petty-25 (Const of Bdry / Wall | M/s Zaid Waqas Engg & Trading | Bndry Wall | 14.892 | 13.574 |  | 12.788 | 0 | 12.788 | 0 |  | 12.788 | 1.416 | 12.788 | 1.416 |  | 1.318 | 8.8504 | 91.1496 | 11.6562 | 0
14 | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-26 | M/s The Muhandis | Sewerage | 16.98 | 14.375 |  | 15.297 | 0 | 15.297 | 0 | 1.678 | 15.297 | 6.955 | 15.297 | 6.955 |  | 2.605 | 15.3416 | 84.6584 | 12.9502 | 0
15 | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-28 | M/s Integration Builders and Enterprises | Sewerage | 11.282 | 10.772 |  | 6.098 | 0 | 9.004 | 0 |  | 6.098 | 2.15 | 9.004 | 5.056 |  | 0.51 | 4.5205 | 95.4795 | 5.8223 | 2.906
16 | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-29 | M/s Ejaz & Co | Sewerage | 10.232 | 9.912 |  | 1.44 | 0 | 1.44 | 0 |  | 1.44 | 0.419 | 1.44 | 0.419 |  | 0.32 | 3.1274 | 96.8726 | 1.395 | 0 |  |  | 2.112
17 | C/2022/P0460/Chaharbagh Sch-Lhr-01 | M/s Z.K Builders | OWHT 1,2 & 4 | 121.116 | 112.878 |  | 33.407 | 0 | 33.407 | 0 |  | 33.407 | 0 | 33.407 | 0 |  | 8.238 | 6.8017 | 93.1983 | 31.1347 | 0 |  | #DIV/0!
18 | C/2022/P0460/Chaharbagh Sch-Lhr-02 | M/s Bhatti Associates | OWHT 3 | 39.694 | 37.626 |  | 14.335 | 0 | 14.335 | 0 |  | 14.335 | 0 | 14.335 | 0 |  | 2.068 | 5.2099 | 94.7901 | 13.5882 | 0 |  | #DIV/0! | 0
19 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-23 | M/s Bhatti Associates | OWHT 5 | 14.976 | 13.685 |  | 13.471 | 0 | 13.471 | 0 |  | 13.471 | 0 | 13.471 | 0 |  | 1.291 | 8.6205 | 91.3795 | 12.3097 | 0
20 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-32 | RBS | Asphalt | 13.674 | 12.238 |  | 13.674 | 0 | 13.285 | 0 |  | 13.674 | 0 | 13.285 | 13.285 |  | 1.436 | 10.5017 | 89.4983 | 12.238 | -0.389
21 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-33 | M/s Junaid Sindhu | Sub Base & base Course | 16.776 | 14.342 |  | 7.241 | 0 | 7.241 | 0 |  | 7.241 | 7.241 | 7.241 | 7.241 |  | 2.434 | 14.5088 | 85.4912 | 6.1904 | 0 | 2.906
22 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-35 | M/s Junaid Sindhu | Sub Base & base Course | 17.399 | 14.875 |  | 5.871 | 0 | 5.871 | 0 |  | 5.871 | 5.871 | 5.871 | 5.871 |  | 2.524 | 14.5066 | 85.4934 | 5.0193 | 0
23 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-36 | M/s Junaid Sindhu | Sub Base & base Course | 16.595 | 14.188 |  | 9.203 | 0 | 9.203 | 0 |  | 9.203 | 9.203 | 9.203 | 9.203 |  | 2.407 | 14.5044 | 85.4956 | 7.8681 | 0
24 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-44 | RBS | Asphalt | 15.8528 | 14.2854 |  | 15.842 | 0 | 15.842 | 0 |  | 15.842 | 15.842 | 15.842 | 15.842 |  | 1.5673 | 9.8868 | 90.1132 | 14.2757 | 0
25 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-45 | RBS | Asphalt | 16.6751 | 14.9359 |  | 12.336 | 0 | 12.336 | 0 |  | 12.336 | 12.336 | 12.336 | 12.336 |  | 1.7392 | 10.4299 | 89.5701 | 11.0494 | 0
26 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-43 | Ms Ali Engineering | Brick Work | 15.1098 | 14.9849 | 0.20126 | 9.4663 | 0.20126 | 9.265 | 0 | 0 | 9.265 | 9.265 | 9.265 | 9.265 |  | 0.12487 | 0.82639 | 99.1736 | 9.388 | -0.20126
27 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-42 | Ms Adan Construction | Brick Work | 15.1098 | 14.9849 | 0.39 | 10.553 | 0.39 | 10.163 | 0 | 0 | 10.163 | 10.163 | 10.163 | 10.163 |  | 0.12487 | 0.82639 | 99.1736 | 10.4658 | -0.39
28 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-46 | Ms Ali Engineering | Sand Filling | 19.152 | 14.938 |  | 13.583 | 0 | 13.583 | 0 | 7.083 | 13.583 | 13.583 | 13.583 | 13.583 |  | 4.214 | 22.0029 | 77.9971 | 10.5943 | 0
29 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-48 | Ms Ali Engineering | Man Hole Covers | 11.536 | 14.978 |  | 12.542 | 0 | 12.542 | 0 | 0 | 12.542 | 12.542 | 12.542 | 12.542 |  | -3.442 | -29.837 | 129.837 | 16.2842 | 0
30 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-47 | Ms Ali Engineering | Hand Holes | 12.682 | 9.2736 |  | 6.7 | 0 | 6.7 | 0 | 3.005 | 6.7 | 6.7 | 6.7 | 6.7 |  | 3.4084 | 26.8759 | 73.1241 | 4.8993 | 0
31 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-49 | MRC | Earth Work | 19.899 | 14.924 |  | 19.406 | 0 | 19.406 | 0 | 2 | 19.406 | 19.406 | 19.406 | 19.406 |  | 4.975 | 25.0013 | 74.9987 | 14.5543 | 0
32 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-66 | MRC | Earth Work | 0 | 0 |  | 4.251 | 0 | 4.251 | 0 | 4.251 | 4.251 | 4.251 | 4.251 | 4.251 |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 0
33 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-38 | SS Enterprises | Ancilary | 15.828 | 13.862 |  | 12.473 | 0 | 12.473 | 0 |  | 12.473 | 12.473 | 12.473 | 12.473 |  | 1.966 | 12.421 | 87.579 | 10.9237 | 0
34 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-41 | AL Nasir Eng Services | Tube Well Chamber | 14.731 | 14.489 |  | 7.449 | 0 | 7.449 | 0 | 6.013 | 7.449 | 7.449 | 7.449 | 7.449 |  | 0.242 | 1.6428 | 98.3572 | 7.3266 | 0
35 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-50 | Farco Builders | Asphalt | 16.431 | 14.85 |  | 8.41 | 0 | 8.41 | 0 | -0.896 | 8.41 | 8.41 | 8.41 | 8.41 |  | 1.581 | 9.6221 | 90.3779 | 7.6008 | 0
36 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-53 | Ms GR Engineer | Boundry Wall | 14.005 | 11.505 |  | 4.308 | 0 | 4.308 | 0 | 0 | 4.308 | 4.308 | 4.308 | 4.308 |  | 2.5 | 17.8508 | 82.1492 | 3.539 | 0
37 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-54 | Ms Ali Engineering | Sewer House Con | 6.658 | 7.5 |  | 3.8 | 0 | 3.8 | 0 | 0 | 3.8 | 3.8 | 3.8 | 3.8 |  | -0.842 | -12.6464 | 112.6464 | 4.2806 | 0
38 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-39 | SS Enterprises | Ancilary | 11.049 | 10.068 |  | 7.978 | 0 | 7.978 | 0 |  | 7.978 | 7.978 | 7.978 | 7.978 |  | 0.981 | 8.8786 | 91.1214 | 7.2697 | 0
39 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-61 | MS Rashid Minhas | Civil Work | 15 | 13.125 |  | 13.5 | 0 | 13.5 | 0 | 0 | 13.5 | 13.5 | 13.5 | 13.5 |  | 1.875 | 12.5 | 87.5 | 11.8125 | 0
40 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-62 | MS Rashid Minhas | Civil Work | 16.97 | 14.993 |  | 15.17 | 0 | 15.17 | 0 | 1.67 | 15.17 | 15.17 | 15.17 | 15.17 |  | 1.977 | 11.65 | 88.35 | 13.4027 | 0
41 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-63 | MS Rashid Minhas | Civil Work | 16.593 | 14.27 |  | 16.7 | 0 | 16.7 | 0 | 6.107 | 16.7 | 16.7 | 16.7 | 16.7 |  | 2.323 | 13.9999 | 86.0001 | 14.362 | 0
42 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-34 | Integration | Sewerage | 4.9104 | 4.104 |  | 3.652 | 0 | 3.652 | 0 |  | 3.652 | 3.652 | 3.652 | 3.652 |  | 0.80638 | 16.4219 | 83.5781 | 3.0523 | 0
43 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-51 | M/S FARCO | Asphalt | 16.0847 | 14.2505 |  | 0 | 0 | 0 | 0 | -7 | 0 | 0 | 0 | 0 |  | 1.8342 | 11.4031 | 88.5969 | 0 | 0
44 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-52 | M/S FARCO | Asphalt | 16.82 | 14.902 |  | 6.205 | 0 | 6.205 | 0 | -0.795 | 6.205 | 6.205 | 6.205 | 6.205 |  | 1.918 | 11.4031 | 88.5969 | 5.4974 | 0
45 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-60 | M/S Nasir | C&G | 18.0684 | 14.9688 |  | 16.709 | 0 | 16.709 | 0 | 5.369 | 16.709 | 16.709 | 16.709 | 16.709 |  | 3.0996 | 17.1548 | 82.8452 | 13.8426 | 0
46 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-59 | Integration | Sewerage | 6.6518 | 6.3396 |  | 6.104 | 0 | 6.104 | 0 | 3.104 | 6.104 | 6.104 | 6.104 | 6.104 |  | 0.3122 | 4.6934 | 95.3066 | 5.8175 | 0
47 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-58 | M/S ACC Associates | Sewerage | 4.4998 | 4.4769 |  | 2.8 | 0 | 2.8 | 0 |  | 2.8 | 2.8 | 2.8 | 2.8 |  | 0.022945 | 0.50991 | 99.4901 | 2.7857 | 0
48 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-40 | M/S Sindhu | Sub Base & base Course | 17.1652 | 14.9768 |  | 2.5 | 0 | 2.5 | 0 |  | 2.5 | 2.5 | 2.5 | 2.5 |  | 2.1885 | 12.7494 | 87.2506 | 2.1813 | 0
49 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-64 | MS Rashid Minhas |  | 12.3615 | 11.306 |  | 12.53 | 0 | 12.53 | 0 | 4.169 | 12.53 | 12.53 | 12.53 | 12.53 |  | 1.0555 | 8.5387 | 91.4613 | 11.4601 | 0
50 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-65 | Ms Ali Engineering | Electrical Works | 8.67 | 1.8182 |  | 0.91351 | 0 | 0.91351 | 0 | 0.91351 | 0.91351 | 0.91351 | 0.91351 | 0.91351 |  | 6.8518 | 79.0286 | 20.9714 | 0.19158 | 0
51 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-56 | M/s Horti Group | Plantation Works Non BOQ | 15.999 | 12.799 |  | 13.275 | 0 | 0 | 0 |  | 13.275 | 13.275 | 0 | 0 |  | 3.2 | 20.0013 | 79.9987 | 10.6198
52 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-30 | M/s Malik Faisal | Boundary | 1.63 | 1.482 | 1.63 | 1.63 | 1.63 | 0 | 0 | [6 empty] | 0.148 | 9.0798 | 90.9202 | 1.482
Total (Rs in Million) |  |  |  | 874.8972 | 755.4885 | 2.2213 | 513.6107 | 2.2213 | 484.3506 | 0 | 38.7835 | 511.3895 | 296.8905 | 484.3506 | 280.4915 | 0 | 119.4087 | #DIV/0! | #DIV/0! | #DIV/0!
Add PST 5% |  |  |  | 43.7449 | 37.7744 | 0.11106 | 25.6805 | 0.11106 | 24.2175 | 0 | 1.9392 | 25.5695 | 14.8445 | 24.2175 | 14.0246 |  | 3.6415 | 0
Total Work Done |  |  |  | 918.6421 | 793.2629 | 2.3323 | 539.2912 | 2.3323 | 508.5681 | 0 | 40.7227 | 536.9589 | 311.735 | 508.5681 | 294.516 |  | 76.4715 | 0
Note: CA are underprocess, nlc & Sub Contractor Cost Might be change in future | [5 empty] | 119.4087 |  |  | 2696.9014
|  | Petty contract with out material |  |  |  | 13.6483 |  | 0.0101
[6 empty] | 85.293 |  | 0.1919 | 2831.7464 |  | 0
438.074
PST
12.45
|  |  | 101.935 |  |  | 0.66425 |  | -0.002
|  |  | 7.094 |  | 14.358 | 14.3382
|  |  | 121.479 |  | 0.7179
13.6401
[7 empty] | 4644978 | 4.645
[7 empty] | 9010928 | 9.0109
[7 empty] | 12718312 | 12.7183
[7 empty] | 15219018 | 15.219
[7 empty] | 17737407 | 17.7374
[7 empty] | 18505079 | 18.5051
[7 empty] | 1253026 | 1.253
[7 empty] | 79088748 | 79.0887 | 57.6527
-434.522
540.6429
27.0321

## Consumtion State
DETAIL OF STORE CUNSUMED AS PER DPR
PMU NLC CHAHAR BAGH RUDA
Ser No. | DESCRIPTION | Unit | Consumption actual | Purchases as Per Store Record | Diff | Comp. Factor | Bal. in Store
a | b | c | d | e | f=e-d | g=e/d | h
1 | Embankment | Cft | 14090861.575 | 13249644.25 | -841217.325 | 94.03%
2 | Sub Base | Cft | 704392.99 | 954961 | 250568.01 | 35.57% | 0
3 | WBM | Cft | 837318.65 | 1276827 | 439508.35 | 52.49% | 2205
4 | Cement | Ton | 5437.9931 | 6932.285 | 1494.2919 |  | 13.35
5 | Sand | Cft | 248170.5009 | 355267 | 107096.4991 |  | 0
6 | Crush/Aggregate | Cft | 376616.7756 | 480278 | 103661.2244 |  | 301
7 | Bricks | Nos | 613533.7132 | 359735 | -253798.7132 |  | 0
8 | Steel | Ton | 1783.6972 | 1942.238 | 158.5408 |  | 52.398
9 | RCC Pipes
10 | iii) 225 mm (9:) i/d | Nos | 149.25 | 156 | 6.75 |  | 0
11 | 310 mm (12") i/d. | Nos | 261.4 | 273 | 11.6 |  | 0
12 | 380 mm (15") i/d | Nos | 160 | 165 | 5 |  | 0
13 | 460 mm (18") i/d | Nos | 15.5417 | 60 | 44.4583 |  | 0
14 | 530 mm (21":) i/d | Nos | 127.1457 | 152 | 24.8543 |  | 0
15 | 610 mm (24") i/d | Nos | 161.3038 | 261 | 99.6962 |  | 0
16 | 760 mm (30")i/d | Nos | 108 | 116 | 8 |  | 0
17 | 910 mm (36")i/d | Nos | 39.3749 | 42 | 2.6251 |  | 0
18 | HDPE Pipe PN-10/SDR-17
19 | 50 mm | Mtr. | 31420.0549 | 17896.0683 | -13523.9866
20 | 90 (3'') | Mtr. | 9041.05 | 7182 | -1859.05 |  | 0
21 | Pipe Dia 5" 125mm | Mtr. | 3662.92 | 5453.49 | 1790.57 |  | 0
22 | Pipe Dia 7" 180mm | Mtr. | 28253.5288 | 2340 | -25913.5288 |  | 0
23 | Pipe Dia 8" 200mm | Mtr. | 189.58 |  | -189.58 |  | 0
24 | Pipe Dia 10" 250mm | Mtr. | 276.14 | 1184 | 907.86 |  | 0
25 | Pipe Dia 12" 315mm | Mtr. | 133.92 | 668.8 | 534.88
26 | Pipe Dia 14" 355mm | Mtr. | 0 | 62.9 | 62.9 |  | 0
27 | MS Pipes | Rft
28 | 12" | Rft | 670 | 1300 | 630 |  | 452
29 | 10" | Rft | 1050 | 1150 | 100 |  | 0
30 | 8" | Rft | 850 | 850 | 0 |  | 0
31 | UPVC Pipe |  |  |  | 0
32 | 8"/200 mm | Rft | 4884.482 | 20540 | 15655.518
33 | 4" /110mm | Rft | 1233.827 | 5368 | 4134.173
34 |  |  |  |  | 0
35 |  |  |  |  | 0
36 |  |  |  |  | 0
37 |  |  |  |  | 0
38 |  |  |  |  | 0
39 |  |  |  |  | 0
40 |  |  |  |  | 0
41

## Anx D
Anx "D"
DETAIL OF EXPENDITURES | [12 empty] | 2362.4501 | 610.1667
PMU NLC INFRA DEV WORKS at Chahar Bagh (RUDA ) | [12 empty] | 3255.7099 | 48.2963
Ser | Head of A/c | Expenditures (Rs in Million) |  |  | Previous | [7 empty] | 893.2598 | -561.8704
|  | During the Month | Upto Date | Year to Date | During the Month | Upto Date | Year to Date |  | 19.5926 |  |  |  |  | -561.2494
Work Expenditures | [11 empty] | 194.4736
1 | Stores Consumed (Material+Diesel) | [15 empty] | 0 | 0
| Misc Site Expense | 0 | 17.8802 | 0 |  | 17.8802 | 4.3342 |  |  | 17.6652 | 17.8802 | 17.6652 | 4.1192 | 0.215 | -4.1192 |  | 204.224
| Store Consume | 1.1866 | 1722.6836 | 1.1866 | 26.9706 | 1721.497 | 676.7201 |  |  | 1527.0234 | 1721.497 | 1521.8584 | 477.0815 | 200.8252 | -475.8949 |  | -204.224
| Plantation Horti Group/Kobble Stone | 0 | 12.872 | 0 |  | 12.872 | 12.872 |  |  | 11.46 | 12.872 | 11.46 | 11.46 | 1.412 | -11.46
| Jhalnader / MS Pipe Asseesories | 2.392 | 4.782 | 2.392 |  | 2.39 | 2.39
| B& I Water Pumps | 0 | 25 | 0 |  | 25 | 25
| Muhammadi Engineering | 0 | 0.78975 | 0 |  | 0.78975 | 0.78975
| Provisional Exp ( Asphalt Plant ) | 23 | 140 | 23 |  | 117 | 117
2 | Sub Contr Cost |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | 0
| Net Payments | 1.8133 | 321.5158 | 1.8133 | 29.2291 | 319.708 | 206.2575 |  |  | 242.0744 | 319.7025 | 242.0744 | 125.4271 | 79.4414 | -123.6138 | 203.0551 | 203.0551
| Retention Money | 0.10342 | 22.3548 | 0.10342 | 1.4771 | 22.2513 | 13.2949 |  |  | 16.0452 | 22.2513 | 16.0452 | 7.0983 | 6.3096 | -6.9949 |  | 13.3044
| Income Tax 7% | 0.15163 | 32.1239 | 0.15163 | 2.1692 | 31.9667 | 20.0527 |  |  | 21.3401 | 31.9722 | 21.3401 | 9.4407 | 10.7837 | -9.2891 |  | 20.0729
| Earnest Money |  | 0.753 | 0 |  | 0.753 | 0 |  |  | 0.753 | 0.753 | 0.753 | 0 | 0 | 0
| Recoveries (Sec Adv etc ) | 0 | 70.3477 | 0 | 0 | 70.3477 | 26.2922 |  |  | 41.5824 | 70.3477 | 41.5824 | 0 | 28.7654 | 0 | 28.7654 | Excess Book in prev MMR
3 | Plants and Machinery |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | 0 |  |  |  | 227 | 13073 | 2967571
| Hiring Charges | 0.638 | 91.2532 | 0.638 | 1.183 | 90.6152 | 23.4339 |  |  | 87.3162 | 90.6152 | 87.3162 | 20.1349 | 3.937 | -19.4969 |  |  |  | 247 | 4869 | 1202643
| Repair/ Maint (Machinery-Grader etc) | 0.08 | 10.6372 | 0.08 | 0.775 | 10.5572 | 5.4612 |  |  | 8.1289 | 10.5572 | 8.1289 | 3.0329 | 2.5083 | -2.9529 |  |  |  | 227 | 16000 | 3632000
| Repair/ Maint (Batching Plant) |  | 1.5623 | 0 |  | 1.5623 | 0.36926 |  |  | 1.5623 | 1.5623 | 1.5623 | 0.36926 | 0 | -0.36926 | [5 empty] | 7802214
| Repair / Maint site |  | 0.382 | 0 |  | 0.382 | 0 |  |  | 0.382 | 0.382 | 0.382 | 0 | 0 | 0
| POL | 2.26 | 170.54 | 2.26 | 4.789 | 168.28 | 67.642 |  |  | 155.304 | 168.28 | 155.304 | 54.666 | 15.236 | -52.406
4 | Direct Labour |  | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  |  | 0 | 0
| Wages/ Muster Roll / Labour Muster Roll/Asphalt | 0.38 | 23.9851 | 0.38 | 0.826 | 23.6051 | 13.7995 |  |  |  | 23.6051 | 164.3331 | 91.7871 | -140.3479 | -91.4071
1 | E & W Building Contractor |  | 0.1512 | 0 |  | 0.1512 | 0.1512 |  |  |  | 92.53
2 | Muhammad Tufail |  | 1.321 | 0 |  | 1.321 | 1.321
3 | Mohsin Ali |  | 2.5099 | 0 |  | 2.5099 | 2.5099
4 | United Devepers & Suppliers |  | 6.1186 | 0 |  | 6.1186 | 6.1186
5 | Al-Nasir Engineering Srvs |  | 0.48847 | 0 |  | 0.48847 | 0.48847 |  | 226.463
6 | Muhammad Rafique Contractors |  | 6.5 | 0 |  | 6.5 | 6.5 |  | 306.463
7 | Bhatti Associates |  | 0.9524 | 0 |  | 0.9524 | 0.9524
8 | Kaleem Ullah |  | 12.5025 | 0 |  | 12.5025 | 1.02
9 | Kamran Nazir |  | 0.22039 | 0 |  | 0.22039 | 0.22039
10 | Naeem Hussain |  | 4.5574 | 0 |  | 4.5574 | 4.5574
11 | Imran Farrukh |  | 0.097295 | 0 |  | 0.097295 | 0.097295
12 | Adan Construction Services | 1.05 | 30.9809 | 1.05 |  | 29.9309 | 7.821 |  | 1.05
13 | ZK Builders Pvt Limited |  | 1.6271 | 0 |  | 1.6271 | 1.6271
14 | Muhammad Ali | 1.1 | 28.8169 | 1.1 |  | 27.7169 | 7.68
15 | M/S Zaid Waqas Engineering Trading |  | 0.26786 | 0 |  | 0.26786 | 0.26786
16 | Khalid Javed Chaudhry |  | 19.9093 | 0 |  | 19.9093 | 19.9093
17 | Sikandar Muaz |  | 0.18429 | 0 |  | 0.18429 | 0.18429
18 | The Muhandis | 0 | 3.3594 | 0 |  | 3.3594 | 3.3594
19 | Fawad Construction |  | 1.9496 | 0 |  | 1.9496 | 1.9496
20 | Punjab Drilling Corporation |  | 2.8992 | 0 |  | 2.8992 | 2.8992
21 | Shah Nawaz |  | 0.78974 | 0 |  | 0.78974 | 0.78974
22 | RBS Constructions Asphalt work |  | 24.3547 | 0 |  | 24.3547 | 15.1257
23 | Mian Associates | 0 | 1.14 | 0 |  | 1.14 | 1.14
24 | Al-Hafiz Management Works |  | 0.0628 | 0 |  | 0.0628 | 0.0628
25 | Muhammad Haris Ilyas |  | 0.36893 | 0 |  | 0.36893 | 0.36893
26 | Muzafar Hussain (Cleaning ) | 0.219 | 3.319 | 0.219 |  | 3.1 | 3.1
| Muster Roll ( Non BOQ items ) |  | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
| Petty contractor ( batching plant ) |  | 1.857 | 0 |  | 1.857 | 0 |  |  | 0 | 1.857 | 1.857 | 0 | 0 | 0
5 | Any Other |  | 0 | 0 |  | 0 | 0 |  |  |  | 0 |  |  | 0 | 0
| Depreciation of Operating Assets | 0.253 | 7.534 | 0.253 | 0.254 | 7.281 | 2.7864 |  |  | 6.521 | 7.281 | 6.521 | 2.0264 | 1.013 | -1.7734
| Office Establishment Exp ( Deffered Cost ) |  | 12.103 | 0 |  | 12.103 | 0 |  |  | 12.103 | 12.103 | 12.103 | 0 | 0 | 0
| Proj Maint Cost Fund |  | 31.0495 | 0 |  | 31.0495 | 11.8247 |  |  | 28.9447 | 31.0495 | 28.9447 | 9.7198 | 2.1048 | -9.7198
| House Rent Charges / Lab Test Fee | 0 | 0.97141 | 0 |  | 0.97141 | 0.2145 |  |  | 0.83161 | 0.97141 | 0.83161 | 0.0747 | 0.1398 | -0.0747
| Client / Consultant misc expense |  | 0.64847 | 0 |  | 0.64847 | 0.04547 |  |  | 0.64847 | 0.64847 | 0.64847 | 0.04547 | 0 | -0.04547
| Asphalt Cost ( NLC + RBS ) |  | 22.858 | 0 |  | 22.858 | 0 |  |  | 22.858 | 22.858 | 22.858 | 0 | 0 | 0
| Tn Charges / Loading/ Unloading |  | 1.065 | 0 |  | 1.065 | 0 |  |  | 1.065 | 1.065 | 1.065 | 0 | 0 | 0
| Client / Consultant ( Expense ) (POL Expense ) |  | 2.9758 | 0 |  | 2.9758 | 0.31635 |  |  | 2.9758 | 2.9758 | 2.9758 | 0.31635 | 0 | -0.31635
| Insurance Exp |  | 2.427 | 0 |  | 2.427 | 0 |  |  | 2.427 | 2.427 | 2.427 | 0 | 0 | 0
| Provision for PST | 9.285 | 157.1398 | 9.285 |  | 147.8548 | 56.4099 |  |  | 137.8318 | 147.8548 | 137.8318 | 46.5768 | 19.3081 | -37.2918
| Provision for unseen expenses PST | 0 | 5.203 | 0 |  | 5.203 | -0.498 |  |  | 5.5 | 5.203 | 5.5 | 0.5 | -0.297 | -0.5
|  |  |  | 0 | [5 empty] | 0
| Total Work Expenditure | 43.912 | 3070.7434 | 43.912 | 67.6731 | 3026.8314 | 1377.0299 | 2712.8595 | 1063.2495
[8 empty] | -313.972 | -313.7804
1 | Pay & Allowances
| Monetary Awards |  | 0.273 | 0 |  | 0.273 | 0.054 |  |  | 0.229 |  | 0.01 |  |  | Salaries
| Civ Personals/benefits | 3.176 | 147.588 | 3.176 | 3.353 | 144.412 | 57.941 |  |  | 128.25 |  | 41.779 |  | 0.845 | 3.3671
| NLC Employees Paybill |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0 |  |  | 118.3831
2 | Other Expenditures |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0 |  |  | 4.2121
| POL ( bikes petrol, Vib, ) |  | 1.3651 | 0 |  | 1.3651 | 0.29948 |  |  | 1.3651 |  | 0.29948
| POL ( Diesel Adm Veh ) |  | 1.0134 | 0 |  | 1.0134 | 0.56374 |  |  | 1.0134 |  | 0.56374
| Utilities | 0.701 | 13.3681 | 0.701 | 0.511 | 12.6671 | 10.9651 |  |  | 11.1191 |  | 9.4171 |  |  |  |  | 255
| Repair & Maint ( Building Container ) |  | 1.636 | 0 |  | 1.636 | 0.5 |  |  | 1.636 |  | 0.5 |  |  |  |  | 256.5
| Repair & Maint (Vehicles) |  | 1.8241 | 0 |  | 1.8241 | 0.94035 |  |  | 1.8241 |  | 0.94035 |  |  |  |  | 195840 | 0.19584
| Repair & Maint (Generator) |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0 |  |  |  |  | 5038686 | 5.0387
| Repair & Maint (ICT ) | 0.02 | 0.7865 | 0.02 | 0.097 | 0.7665 | 0.5544 |  |  | 0.5064 |  | 0.2943 |  |  |  |  | 5234526
| Repair & Maint (Furniture ) |  | 0.243 | 0 |  | 0.243 | 0 |  |  | 0.243 |  | 0
| Repair & Maint (Batching Plant ) |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0
| Repair & Maint (Office Equipment ) |  | 0.1927 | 0 |  | 0.1927 | 0.1398 |  |  | 0.1927 |  | 0.1398
| Repair & Maint (Cptr, Electric,Building and Genral) |  | 1.1993 | 0 | 0.301 | 1.1993 | 0.301 |  |  | 0.8983 |  | 0
| Charge Off - Electric Inst |  | 1.633 | 0 |  | 1.633 | 0 |  |  | 1.633 |  | 0
| Charge Off - Office Furniture |  | 0.049 | 0 |  | 0.049 | 0 |  |  | 0.049 |  | 0
| Weigh Bridge Charges |  | 0.0036 | 0 |  | 0.0036 | 0.0018 |  |  | 0.0036 |  | 0.0018
| TA/DA Allowance |  | 0.1064 | 0 |  | 0.1064 | 0.011 |  |  | 0.1064 |  | 0.011
| Medical Charges | 0.03 | 0.1843 | 0.03 |  | 0.1543 | 0.0075 |  |  | 0.1543 |  | 0.0075
| Entertainment Exp | 0.06 | 2.4628 | 0.06 | 0.035 | 2.4028 | 1.3943 |  |  | 2.1861 |  | 1.1775
| Newspaper Exp |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0
| Printing & Stationery/Photocopies | 0.07 | 1.7561 | 0.07 |  | 1.6861 | 0.72012 |  |  | 1.6111 |  | 0.64512
| Computer Stationery |  | 0.27007 | 0 |  | 0.27007 | 0 |  |  | 0.27007 |  | 0
| Courier Charges |  | 0.0004 | 0 |  | 0.0004 | 0.0004 |  |  | 0.0004 |  | 0.0004
| Freight Charges |  | 1.6177 | 0 |  | 1.6177 | 0.62029 |  |  | 1.6177 |  | 0.62029
| Misc Exp |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0
| Security Exp Rahbar Guards/Fauji Guards | 0.1633 | 2.0129 | 0.1633 |  | 1.8496 | 0.447 |  |  | 1.8496 |  | 0.447 |  | 0.01875
| Tel / Mobile Exp/Internet | 0.065 | 0.6842 | 0.065 | 0.019 | 0.6192 | 0.407 |  |  | 0.5422 |  | 0.33
| ICT Eqpts, Tools etc | 0 | 0.143 | 0 | 0.04 | 0.143 | 0.08 |  |  | 0.063 |  | 0
| Hiring Charges |  | 0.75862 | 0 |  | 0.75862 | 0.75862 |  |  | 0.75862 |  | 0.75862
| Other Exp (Const Mat) |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0
| Local Purchase |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0
| Fee & Subscription |  | 0.007 | 0 |  | 0.007 | 0 |  |  | 0.007 |  | 0
| Welfare / Distress Gt NLC Emp |  | 0.499 | 0 |  | 0.499 | 0.141 |  |  | 0.499 |  | 0.141
| Token Tax of Vehicles | 0.029 | 0.05826 | 0.029 |  | 0.02926 | 0.00036 |  |  | 0.02926 |  | 0.00036
| Sports Events |  | 0.008 | 0 |  | 0.008 | 0 |  |  | 0.008 |  | 0
| Office Contigencies (342 Aug) | 0.07 | 3.223 | 0.07 | 0.125 | 3.153 | 1.0604 |  |  | 2.896 |  | 0.80338
3 | HQ Expenditures |  | 0 | 0 |  | 0 | 0 |  |  | 0
| HQ NLC Expenses |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0
| HQ Engrs NLC Expenses |  | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0
| Total Overhead Expenditure | 4.3843 | 184.9664 | 4.3843 | 4.481 | 180.5821 | 77.9086 |  |  | 114.8315 |  | 12.158
| Tax on Revenue 7.5% | 0 | 0 | 0 | 0 | 0 | 0
| Grand Total Expenditure (Work + Overhead) | 48.2963 | 3255.7099 | 48.2963 | 72.1541 | 3207.4136 | 1454.9386
|  | 3207.4136 | 3207.4136
48.2963
0
3207.4136
|  | Prev | 148.8223 | [8 empty] | 5.6813
|  |  | -3058.5913 | [8 empty] | 9.0779
114
396
2745.7099
614886
0.61489
| Soil Reversal | 0.938
| Cement Reversal | 3.433
4.371
7391618.15
|  |  | 533.98 | 55480.75
|  |  | 266.99 | 7447098.9
7.4471
258.05
3.246
3.028
3.028
740.919
115
383
242.919

## Anx E
MONTH - July 2025
DETAIL OF PAYMENTS TO SUB CONTRACTORS
PMU NLC INFRA DEV WORKS at Chahar Bagh (RUDA )
Previous
S.No | CA No | Contractor | Activity | NLC CA Amount | Sub Contr CA Amount |  | Month | [5 empty] | UTD | [6 empty] | YTD | [5 empty] | Month | [5 empty] | UTD | [6 empty] | YTD | [9 empty] | UTD | [5 empty] | YTD
[7 empty] | Sub Contr's Vetted Work Done | Retention Money | I. T@ 7% on WD after ded of POL and Mat Rec | Material Recovery | Earnest Money | Net Payment Due | Sub Contr's Vetted Work Done | Retention Money | Material Recovery | I. T@ 7% on WD after ded of POL and Mat Rec | Earnest Money | Net Payment Due |  | Sub Contr's Vetted Work Done | Retention Money | Material Recovery | I. T@ 7% on WD after ded of POL and Mat Rec | Earnest Money | Net Payment Due | Sub Contr's Vetted Work Done | Retention Money | I. T@ 7% on WD after ded of POL and Mat Rec | Material Recovery | Earnest Money | Net Payment Due | Sub Contr's Vetted Work Done | Retention Money | Material Recovery | I. T@ 7% on WD after ded of POL and Mat Rec | Earnest Money | Net Payment Due |  | Sub Contr's Vetted Work Done | Retention Money | Material Recovery | I. T@ 7% on WD after ded of POL and Mat Rec | Earnest Money | Net Payment Due |  | Profit Margin |  |  | Sub Contr's Vetted Work Done | Retention Money | Material Recovery | I. T@ 7% on WD after ded of POL and Mat Rec | Secured Adv rel | Net Payment Due | Sub Contr's Vetted Work Done | Retention Money | Material Recovery | I. T@ 7% on WD after ded of POL and Mat Rec | Net Payment Due
1 | C/2022/P0460/Chaharbagh Sch Lhr-Petty-4 (Const of Rd Pkg -1 St No. 11,12,13,14,15,16) | M/s Muhammad Rafique Contractor (MRC) | Earth Work | 20.753 | 14.686 | 29.23% | 0 | 0 | 0 | 0 |  | 0 | 8.1725 | 0.40863 | 0 | 0.54347 | 0 | 7.2204 | 7.2204 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 8.1725 | 0.40863 | 0 | 0.54347 | 0 | 7.2204 | 7.2204 | 0 | 0 | 0 | 0 |  | 0 |  | 29.23% | 100% | 70.77% | 15.8255 | 0.79128 | 0 | 1.1078 | 0 | 13.9265 | 1.3246 | 0 | 0 | 0.092722 | 1.2319
2 | C/2022/P0460/Chaharbagh Sch Lhr-Petty-17 (Const of Rd Pkg-2 St No. 11,12,13,14,15,16) | M/s Muhammad Rafique Contractor (MRC) | Earth Work | 20.753 | 14.686 | 29.23% | 0 | 0 | 0 | 0 |  | 0 | 11.6834 | 0.58417 | 0 | 0.77695 | 0 | 10.3223 | 10.3223 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 11.6834 | 0.58417 | 0 | 0.77695 | 0 | 10.3223 | 10.3223 | 0 | 0 | 0 | 0 |  | 0 |  | 29.23% | 100% | 70.77% | 2.446 | 0.1223 | 0 | 0.17122 | 0 | 2.1525 | 0 | 0 | 0 | 0 | 0
3 | C/2022/P0460/Chaharbagh Sch Lhr-Petty-14 (Const of Rd St No. 4,5,6) | M/s Muhammad Rafique Contractor (MRC) | Earth Work | 17.98 | 12.973 |  | 0 | 0 | 0 |  |  | 0 | 3.0505 | 0.15253 | 0 | 0.20286 | 0 | 2.6951 | 2.6951 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 3.0505 | 0.15253 | 0 | 0.20286 | 0 | 2.6951 | 2.6951 | 0 | 0 | 0 | 0 |  | 0 | 4.263 | 21.32% | 4.0499
4 | C/2022/P0460/Chaharbagh Sch Lhr-Petty-15 (Const of Rd St No. 7,8,9) | M/s Muhammad Rafique Contractor (MRC) | Earth Work | 20.262 | 14.612 |  | 0 | 0 | 0 |  |  | 0 | 3.2111 | 0.16055 | 0 | 0.21354 | 0 | 2.837 | 2.837 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 3.2111 | 0.16055 | 0 | 0.21354 | 0 | 2.837 | 2.837 | 0 | 0 | 0 | 0 |  | 0
5 | C/2022/P0460/Chaharbagh Sch Lhr-Petty-16 (Const of Rd Pkg-1 St No. B-3) | M/s Muhammad Rafique Contractor (MRC) | Earth Work | 17.015 | 12.363 |  | 0 | 0 | 0 |  |  | 0 | 12.2401 | 0.612 | 0 | 0.81396 | 0 | 10.8141 | 10.8141 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 12.2401 | 0.612 | 0 | 0.81396 | 0 | 10.8141 | 10.8141 | 0 | 0 | 0 | 0 |  | 0
6 | C/2022/P0460/Chaharbagh Sch Lhr-Petty-19 (Const of Rd Pkg-2 St No. 11,12,13,14,15,16) | M/s Muhammad Rafique Contractor (MRC) | Earth Work | 17.689 | 13.698 |  | 0 | 0 | 0 |  |  | 0 | 8.5904 | 0.42952 | 0 | 0.57126 | 0 | 7.5896 | 7.5896 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 8.5904 | 0.42952 | 0 | 0.57126 | 0 | 7.5896 | 7.5896 | 0 | 0 |  | 0 |  | 0
7 | C/2022/P0460/Chaharbagh Sch Lhr-Petty-21 | M/s Muhammad Rafique Contractor (MRC) | Earth Work | 19.283 | 14.935 |  | 0 | 0 | 0 |  |  | 0 | 6.8884 | 0.34442 | 0 | 0.45808 | 0 | 6.0859 | 6.0859 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 6.8884 | 0.34442 | 0 | 0.45808 | 0 | 6.0859 | 6.0859 | 0 | 0 |  | 0 |  | 0
8 | C/2022/P0460/Chaharbagh Sch Lhr-Petty-27 | M/s Muhammad Rafique Contractor (MRC) | Earth Work | 11.803 | 9.141 |  | 0 | 0 | 0 |  |  | 0 | 9.1368 | 0.45684 | 0 | 0.6076 | 0 | 8.0723 | 8.0723 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 9.1368 | 0.45684 | 0 | 0.6076 | 0 | 8.0723 | 8.0723 | 0 | 0 |  | 0 |  | 0
9 | C/2022/P0460/Chahar Bagh/Lhr/Petty-13 | M/s Focus Engg | Earth Work | 18.392 | 14.23 | 0 | 0 | 0 | 0 | 0 |  | 0 | 11.891 | 0.59455 | 0 | 0.79075 | 0 | 10.5057 | 10.5057 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 11.891 | 0.59455 | 0 | 0.79075 | 0 | 10.5057 | 10.5057 | 0 | 0 | 0 | 0 |  | 0
10 | C/2022/P0460/Chahar Bagh/Lhr/Petty-6 | M/s Bhatti Associates | Bndry Wall | 7.698 | 6.719 | 12.72% | 0 | 0 | 0 | 0 |  | 0 | 3.5436 | 0.17718 | 0 | 0.23565 | 0 | 3.1307 | 3.1307 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 3.5436 | 0.17718 | 0 | 0.23565 | 0 | 3.1307 | 3.1307 | 0 | 0 | 0 | 0 |  | 0 |  | 12.72% | 100% | 87.28% | 4.8472 | 0.24236 | 0 | 0.3393 | 0 | 4.2655 | 4.8472 | 0 | 0 | 0.3393 | 4.5079
11 | C/2022/P0460/Chaharbagh Sch-Lhr-01 | M/s Z.K Builders | OWHT 1,2 & 4 | 121.116 | 112.878 |  | 0 | 0 | 0 | 0 |  | 0 | 31.1347 | 1.5567 | 21.034 | 2.0705 |  | 6.4735 | 6.4735 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 31.1347 | 1.5567 | 21.034 | 2.0705 |  | 6.4735 | 6.4735 | 0 | 0 | 0 | 0 |  | 0
12 | C/2022/P0460/Chaharbagh Sch-Lhr-02 | M/s Bhatti Associates | OWHT 3 | 39.694 | 37.626 |  | 0 | 0 | 0 | 0 |  | 0 | 13.5881 | 0.67941 | 7.742 | 0.90361 | 0.753 | 3.5101 | 3.5101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 13.5881 | 0.67941 | 7.742 | 0.90361 | 0.753 | 3.5101 | 3.5101 | 0 | 0 | 0 | 0 | 0 | 0
13 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-23 | M/s Bhatti Associates | OWHT 5 | 14.976 | 13.685 |  | 0 | 0 | 0 | 0 |  | 0 | 12.3098 | 0.61549 | 8.131 | 0.8186 |  | 2.7447 | 2.7447 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 12.3098 | 0.61549 | 8.131 | 0.8186 |  | 2.7447 | 2.7447 | 0 | 0 | 0 | 0 |  | 0
14 | C/2022/P0460/Chahar Bagh/Lhr/Petty-5 (Const of Bdry / Wall Pkg-1 L=5267 Ft | M/s Zaid Waqas Engg & Trading | Bndry Wall | 17.199 | 14.967 |  | 0 | 0 | 0 |  |  | 0 | 0.26454 | 0.013227 |  | 0.017592 |  | 0.23372 | 0.23372 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0.26454 | 0.013227 |  | 0.017592 |  | 0.23372 | 0.23372 | 0 | 0 | 0 | 0 |  | 0
15 | C/2022/P0460/Chahar Bagh/Lhr/Petty-24 (Const of Sewerage | M/s Al-Hafiz Management Works | Sewerage | 16.312 | 14.623 |  | 0 | 0 | 0 |  |  | 0 | 13.3546 | 0.66773 | 0.94657 | 0.88808 |  | 10.8522 | 6.8358 | 0 | 0 | 0 | 0 |  | 0 | 1.8933 | 0.094666 | 0.12591 |  |  | 1.6728 | 13.3546 | 0.66773 | 0.94657 | 0.88808 |  | 10.8522 | 6.8358 | 4.5459 | 0.2273 |  | 0.30231 |  | 4.0163
16 | C/2022/P0460/Chahar Bagh/Lhr/Petty-25 (Const of Bdry / Wall | M/s Zaid Waqas Engg & Trading | Bndry Wall | 14.892 | 13.574 |  | 0 | 0 | 0 |  |  | 0 | 11.6563 | 0.58281 | 3.3107 | 0.77514 |  | 6.9876 | 6.731 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 11.6563 | 0.58281 | 3.3107 | 0.77514 |  | 6.9876 | 6.731 | 1.2907 | 0.064534 | 0.263 | 0.08583 |  | 0.87732
17 | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-26 | M/s The Muhandis | Sewerage | 16.98 | 14.375 |  | 0 | 0 | 0 | 0 |  | 0 | 12.9504 | 0.64752 | 1.2191 | 0.8612 |  | 10.2226 | 5.4587 | 0 | 0 | 0 | 0 |  | 0 | 1.4206 | 0.07103 | 0.09447 | 0 |  | 1.2551 | 12.9504 | 0.64752 | 1.2191 | 0.8612 |  | 10.2226 | 5.4587 | 5.8881 | 0.29441 | 0.438 | 0.39156 |  | 4.7641
18 | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-28 | M/s Integration Builders and Enterprises | Sewerage | 11.282 | 10.772 |  | 0 | 0 | 0 | 0 |  | 0 | 5.8224 | 0.29112 | 0.36576 | 0.38719 |  | 4.7783 | 2.9646 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 5.8224 | 0.29112 | 0.36576 | 0.38719 |  | 4.7783 | 2.9646 | 2.0528 | 0.10264 |  | 0.13651 |  | 1.8137
19 | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-29 | M/s Ejaz & Co | Sewerage | 10.232 | 9.912 |  | 0 | 0 | 0 | 0 |  | 0 | 1.3949 | 0.069746 | 0.155 | 0.092763 |  | 1.0774 | 0.71882 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 1.3949 | 0.069746 | 0.155 | 0.092763 |  | 1.0774 | 0.71882 | 0.40589 | 0.020294 |  | 0.026991 |  | 0.3586
20 | C/2022/P0460/Chaharbagh Sch-Lhr-01 | M/s Z.K Builders | OWHT 1,2 & 4 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
21 | C/2022/P0460/Chaharbagh Sch-Lhr-02 | M/s Bhatti Associates | OWHT 3 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
22 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-23 | M/s Bhatti Associates | OWHT 5 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
23 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-32 | RBS | Asphalt | 13.674 | 12.238 |  | 0 | 0 | 0 | 0 |  | 0 | 12.238 | 0.6119 | 0 | 0.81382 |  | 10.8122 | 11.7031 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 12.238 | 0.6119 | 0 | 0.81382 |  | 10.8122 | 11.7031 | 0 | 0 | 0 | 0 |  | 0
24 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-33 | M/s Junaid Sindhu | Sub Base & base Course | 16.776 | 14.342 |  | 0 | 0 | 0 | 0 |  | 0 | 6.1904 | 0.30952 | 5.595 | 0.47047 |  | -0.18453 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 6.1904 | 0.30952 | 5.595 | 0.47047 |  | -0.18453 |  | 6.1904 | 0.30952 | 5.595 | 0.47047 |  | -0.18453
25 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-35 | M/s Junaid Sindhu | Sub Base & base Course | 17.399 | 14.875 |  | 0 | 0 | 0 | 0 |  | 0 | 5.0193 | 0.25096 | 6.8339 | 0.38146 |  | -2.447 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 5.0193 | 0.25096 | 6.8339 | 0.38146 |  | -2.447 |  | 5.0193 | 0.25096 | 6.8339 | 0.38146 |  | -2.447
26 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-36 | M/s Junaid Sindhu | Sub Base & base Course | 16.595 | 14.188 |  | 0 | 0 | 0 | 0 |  | 0 | 7.8682 | 0.39341 | 10.7195 | 0.59798 |  | -3.8427 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 7.8682 | 0.39341 | 10.7195 | 0.59798 |  | -3.8427 |  | 7.8682 | 0.39341 | 10.7195 | 0.59798 |  | -3.8427
27 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-44 | RBS | Asphalt | 15.8528 | 14.2854 |  | 0 | 0 | 0 | 0 |  | 0 | 14.2757 | 0.71379 | 0 | 1.085 |  | 12.477 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 14.2757 | 0.71379 | 0 | 1.085 |  | 12.477 |  | 14.2757 | 0.71379 | 0 | 1.085 |  | 12.477
28 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-45 | RBS | Asphalt | 16.6751 | 14.9359 |  | 0 | 0 | 0 | 0 |  | 0 | 11.0494 | 0.55247 | 0 | 0.83975 |  | 9.6571 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 11.0494 | 0.55247 | 0 | 0.83975 |  | 9.6571 |  | 11.0494 | 0.55247 | 0 | 0.83975 |  | 9.6571
29 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-43 | Ms Ali Engineering | Brick Work | 15.1098 | 14.9849 |  | 0.1996 | 0.0099799 | 0.013273 | 0 |  | 0.17634 | 9.3881 | 0.4694 | 0.1934 | 0.71349 |  | 8.0118 |  | 0.1996 | 0.0099799 | 0 | 0.015169 |  | 0.17445 | 0 | 0 | 0 | 0 |  | 0 | 9.1885 | 0.45942 | 0.149 | 0.69832 |  | 7.8817 |  | 9.1885 | 0.45942 | 0.149 | 0.69832 |  | 7.8817
30 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-42 | Ms Adan Construction | Brick Work | 15.1098 | 14.9849 |  | 0.38678 | 0.019339 | 0.025721 | 0 |  | 0.34172 | 10.4658 | 0.52329 | 1.1147 | 0.7954 |  | 8.0325 |  | 0.38678 | 0.019339 | 0 | 0.029395 |  | 0.33804 | 0 | 0 | 0 | 0 |  | 0 | 10.0791 | 0.50395 | 1.1147 | 0.76601 |  | 7.6944 |  | 10.0791 | 0.50395 | 1.1147 | 0.76601 |  | 7.6944
31 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-46 | Ms Ali Engineering | Sand Filling | 19.152 | 14.938 |  | 0 | 0 | 0 | 0 |  | 0 | 13.4708 | 0.67354 | 0 | 1.0238 |  | 11.7735 |  | 0 | 0 | 0 | 0 |  | 0 | 7.0245 | 0.35122 | 0.53386 | 0 |  | 6.1394 | 13.4708 | 0.67354 | 0 | 1.0238 |  | 11.7735 |  | 13.4708 | 0.67354 | 0 | 1.0238 |  | 11.7735
32 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-48 | Ms Ali Engineering | Man Hole Covers | 11.536 | 14.978 |  | 0 | 0 | 0 | 0 |  | 0 | 16.2842 | 0.81421 | 0 | 1.2376 |  | 14.2324 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 16.2842 | 0.81421 | 0 | 1.2376 |  | 14.2324 |  | 16.2842 | 0.81421 | 0 | 1.2376 |  | 14.2324
33 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-47 | Ms Ali Engineering | Hand Holes | 12.682 | 9.2736 |  | 0 | 0 | 0 | 0 |  | 0 | 4.8993 | 0.24497 | 0 | 0.37235 |  | 4.282 |  | 0 | 0 | 0 | 0 |  | 0 | 2.1974 | 0.10987 | 0.167 | 0 |  | 1.9205 | 4.8993 | 0.24497 | 0 | 0.37235 |  | 4.282 |  | 4.8993 | 0.24497 | 0 | 0.37235 |  | 4.282
34 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-49 | MRC | Earth Work | 19.899 | 14.924 |  | 0 | 0 | 0 | 0 |  | 0 | 14.5543 | 0.72772 | 0 | 1.1061 |  | 12.7205 |  | 0 | 0 | 0 | 0 |  | 0 | 1.5 | 0.074999 | 0.099749 | 0 |  | 1.3252 | 14.5543 | 0.72772 | 0 | 1.1061 |  | 12.7205 |  | 14.5543 | 0.72772 | 0 | 1.1061 |  | 12.7205
| C/2022/P0460/Chaharbagh Sch-Lhr-Petty-66 | MRC | Earth Work | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 3.1882 | 0.15941 | 0 | 0.2423 |  | 2.7865 |  | 0 | 0 | 0 | 0 |  | 0 | 3.1882 | 0.15941 | 0.21202 | 0 |  | 2.8168 | 3.1882 | 0.15941 | 0 | 0.2423 |  | 2.7865 |  | 3.1882 | 0.15941 | 0 | 0.2423 |  | 2.7865
35 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-38 | SS Enterprises | Ancilary | 15.828 | 13.862 |  | 0 | 0 | 0 | 0 |  | 0 | 10.9237 | 0.54619 | 0 | 0.8302 |  | 9.5473 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 10.9237 | 0.54619 | 0 | 0.8302 |  | 9.5473 |  | 10.9237 | 0.54619 | 0 | 0.8302 |  | 9.5473
36 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-41 | AL Nasir Eng Services | Tube Well Chamber | 14.731 | 14.489 |  | 0 | 0 | 0 | 0 |  | 0 | 7.328 | 0.3664 | 2.0488 | 0.55692 |  | 4.3558 |  | 0 | 0 | 0 | 0 |  | 0 | 5.9153 | 0.29576 | 0.44956 | 0 |  | 5.17 | 7.328 | 0.3664 | 0.24083 | 0.55692 |  | 6.1638 |  | 7.328 | 0.3664 | 0.24083 | 0.55692 |  | 6.1638
37 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-50 | Farco Builders | Asphalt | 16.431 | 14.85 |  | 0 | 0 | 0 | 0 |  | 0 | 7.6008 | 0.38004 | 0 | 0.57766 |  | 6.6431 |  | 0 | 0 | 0 | 0 |  | 0 | -0.80979 | -0.040489 | -0.061544 | 0 |  | -0.70775 | 7.6008 | 0.38004 | 0 | 0.57766 |  | 6.6431 |  | 7.6008 | 0.38004 | 0 | 0.57766 |  | 6.6431
38 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-53 | Ms GR Engineer | Boundry Wall | 14.005 | 11.505 |  | 0 | 0 | 0 | 0 |  | 0 | 3.539 | 0.17695 | 0 | 0.26896 |  | 3.0931 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 3.539 | 0.17695 | 0 | 0.26896 |  | 3.0931 |  | 3.539 | 0.17695 | 0 | 0.26896 |  | 3.0931
39 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-54 | Ms Ali Engineering | Sewer House Con | 6.658 | 7.5 |  | 0 | 0 | 0 | 0 |  | 0 | 4.2805 | 0.21403 | 0 | 0.32532 |  | 3.7412 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 4.2805 | 0.21403 | 0 | 0.32532 |  | 3.7412 |  | 4.2805 | 0.21403 | 0 | 0.32532 |  | 3.7412
40 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-39 | SS Enterprises | Ancilary | 11.049 | 10.068 |  | 0 | 0 | 0 | 0 |  | 0 | 7.2696 | 0.36348 | 0 | 0.55249 |  | 6.3537 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 7.2696 | 0.36348 | 0 | 0.55249 |  | 6.3537 |  | 7.2696 | 0.36348 | 0 | 0.55249 |  | 6.3537
41 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-61 | MS Rashid Minhas | Civil Work | 15 | 13.125 |  | 0 | 0 | 0 | 0 |  | 0 | 11.8125 | 0.59062 | 0 | 0.89775 |  | 10.3241 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 11.8125 | 0.59062 | 0 | 0.89775 |  | 10.3241 |  | 11.8125 | 0.59062 | 0 | 0.89775 |  | 10.3241
42 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-62 | MS Rashid Minhas | Civil Work | 16.97 | 14.993 |  | 0 | 0 | 0 | 0 |  | 0 | 13.2737 | 0.66369 | 0 | 1.0088 |  | 11.6013 |  | 0 | 0 | 0 | 0 |  | 0 | 1.4612 | 0.073062 | 0.11105 | 0 |  | 1.2771 | 13.2737 | 0.66369 | 0 | 1.0088 |  | 11.6013 |  | 13.2737 | 0.66369 | 0 | 1.0088 |  | 11.6013
43 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-63 | MS Rashid Minhas |  | 16.593 | 14.27 |  | 0 | 0 | 0 |  |  | 0 | 14.362 | 0.7181 |  | 1.0915 |  | 12.5524 |  | 0 | 0 | 0 | 0 |  | 0 | 5.252 | 0.2626 | 0.39915 |  |  | 4.5903 | 14.362 | 0.7181 |  | 1.0915 |  | 12.5524 |  | 14.362 | 0.7181 | 0 | 1.0915 |  | 12.5524
44 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-34 | Integration |  | 4.9104 | 4.104 |  | 0 | 0 | 0 | 0 |  | 0 | 3.0523 | 0.15261 | 0.19308 | 0.23197 |  | 2.4746 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 3.0523 | 0.15261 | 0.19308 | 0.23197 |  | 2.4746 |  | 3.0523 | 0.15261 | 0.19308 | 0.23197 |  | 2.4746
45 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-51 | M/S FARCO |  | 16.0847 | 14.2505 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 | -6.2018 | -0.31009 | -0.47134 |  |  | -5.4204 | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0
46 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-52 | M/S FARCO |  | 16.82 | 14.902 |  | 0 | 0 | 0 |  |  | 0 | 5.4974 | 0.27487 |  | 0.41781 |  | 4.8048 |  | 0 | 0 | 0 | 0 |  | 0 | -0.70435 | -0.035217 | -0.05353 |  |  | -0.6156 | 5.4974 | 0.27487 |  | 0.41781 |  | 4.8048 |  | 5.4974 | 0.27487 | 0 | 0.41781 |  | 4.8048
47 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-60 | M/S Nasir |  | 18.0684 | 14.9688 |  | 0 | 0 | 0 |  |  | 0 | 13.8426 | 0.69213 |  | 1.052 |  | 12.0984 |  | 0 | 0 | 0 | 0 |  | 0 | 4.4479 | 0.2224 | 0.33804 |  |  | 3.8875 | 13.8426 | 0.69213 |  | 1.052 |  | 12.0984 |  | 13.8426 | 0.69213 | 0 | 1.052 |  | 12.0984
48 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-59 | Integration |  | 6.6518 | 6.3396 |  | 0 | 0 | 0 |  |  | 0 | 5.8175 | 0.29088 |  | 0.44213 |  | 5.0845 |  | 0 | 0 | 0 | 0 |  | 0 | 2.9583 | 0.14792 | 0.22483 |  |  | 2.5856 | 5.8175 | 0.29088 |  | 0.44213 |  | 5.0845 |  | 5.8175 | 0.29088 | 0 | 0.44213 |  | 5.0845
49 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-58 | M/S ACC Associates |  | 4.4998 | 4.4769 |  | 0 | 0 | 0 |  |  | 0 | 2.7857 | 0.13929 |  | 0.21171 |  | 2.4347 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 2.7857 | 0.13929 |  | 0.21171 |  | 2.4347 |  | 2.7857 | 0.13929 | 0 | 0.21171 |  | 2.4347
50 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-40 | M/S Sindhu |  | 17.1652 | 14.9768 |  | 0 | 0 | 0 | 0 |  | 0 | 2.1813 | 0.10906 | 0.74533 | 0.14505 |  | 1.1818 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 2.1813 | 0.10906 | 0.74533 | 0.14505 |  | 1.1818 |  | 2.1813 | 0.10906 | 0.74533 | 0.14505 |  | 1.1818
51 | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-64 | MS Rashid Minhas |  | 12.3615 | 11.306 |  | 0 | 0 | 0 |  |  | 0 | 11.4601 | 0.573 |  | 0.87096 |  | 10.0161 |  | 0 | 0 | 0 | 0 |  | 0 | 3.813 | 0.19065 | 0.28979 |  |  | 3.3326 | 11.4601 | 0.573 |  | 0.87096 |  | 10.0161 |  | 11.4601 | 0.573 | 0 | 0.87096 |  | 10.0161
| C/2022/P0460/Chaharbagh Sch-Lhr-Petty-65 | Ms Ali Engineering |  | 8.67 | 1.8182 |  | 0 | 0 | 0 |  |  | 0 | 0.19158 | 0.0095788 |  | 0.01456 |  | 0.16744 |  | 0 | 0 | 0 | 0 |  | 0 | 0.19158 | 0.0095788 | 0.01456 |  |  | 0.16744 | 0.19158 | 0.0095788 |  | 0.01456 |  | 0.16744 |  | 0.19158 | 0.0095788 | 0 | 0.01456 |  | 0.16744
| C/2022/P0460/Chaharbagh Sch-Lhr-Petty-56 | M/s Horti Group |  | 15.999 | 12.799 |  | 0 | 0 | 0 |  |  | 0 | 10.6198 | 0.53099 |  | 0.80711 |  | 9.2817 |  | 0 | 0 | 0 | 0 |  | 0
| C/2022/P0460/Chaharbagh Sch-Lhr-Petty-30 | M/s Malik Faisal |  | 1.63 | 1.482 |  | 1.482 | 0.0741 | 0.11263 |  |  | 1.2953 | 1.482 | 0.0741 |  | 0.11263 |  | 1.2953 |  | 1.482 | 0.0741 | 0 | 0.11263 |  | 1.2953
Total Cost (Rs in Million) |  |  |  | 874.8972 | 755.4885 | 0.71186 | 2.0684 | 0.10342 | 0.15163 | 0 | 0 | 1.8133 | 447.0952 | 22.3548 | 70.3477 | 32.1239 | 0.753 | 321.5158 | 116.6474 | 2.0684 | 0.10342 | 0 | 0.1572 | 0 | 1.8078 | 33.5475 | 1.6774 | 2.4736 | 0 | 0 | 29.3965 | 434.4069 | 21.7203 | 68.4953 | 31.1596 | 0.753 | 312.2787 | 116.6474 | 255.469 | 12.7734 | 26.2922 | 19.2602 | 0 | 197.1432
|  |  |  | 119.4087 |  |  | 100 | [24 empty] | 400.8595 | 20.043 | 68.4953 | 28.6414 | 0.753 | 282.9267 | 116.6474 | 221.9215 | 11.0961 | 26.2922 | 16.7421 | 0 | 167.7912
|  |  |  | 13.6483 | 8722% |  | % | 100%
77.28%
[5 empty] | 119.4087 |  |  | 22.72%
13.6483
-6.067
-29.2343
70.77

## Anx F Contr
Anx "F"
MONTH - July 2025
PAYMENT DETAIL OF SUB CONTRACTORS
PMU NLC INFRA DEV WORKS at Chahar Bagh (RUDA )
Rs in Million
S.No | Contr | Description of Work | Upto Date | [10 empty] | Cheque No | Date
|  |  | RAR No | Sub Contr's Vetted Work Done | Retention Money | Material Recovery | Earnest Money 2% | Sec Adv Recovery | I. T@ 7% on WD after ded of POL and Mat Rec | Secured Adv rel | Net Payment Due | Paid Amount | Less / (Over) Paid
1 | M/s Muhammad Rafique Contractor (MRC) | CA No. C/2022/P0460/Chaharbagh SchemeLhr-Petty-4 | 1 | 3.177 | 0.15885 |  |  |  | 0.21127 |  | 2.8069 | 2.807 | -0.0001205 | 144870 | 2023-02-20 |  | 1435000 | 100450 | 1334550
|  |  | 2 | 4.994 | 0.2497 |  |  |  | 0.3321 |  | 4.4122 | 4.412 | 0.000199 | 145824 & 146749 | 21-03-2023 & 31-03-2023
|  |  | 3 | 0 | -0.376 | [5 empty] | 0.376 | 0.376 | 0 | 169826 | 2024-01-19
|  |  |  | 8.171 | 0.03255 | 0 | 0 | 0 | 0.54337 | 0 | 7.5951 | 7.595 | 7.85e-05 |  |  | 7.5951 | 0
2 | M/s Bhatti Associates | C/2022/P0460/chaharbagh schemeLhr-petty-6 | 1 | 1.253 | 0.06265 |  |  |  | 0.083 |  | 1.1073 | 1.107 | 0.00035 | 148569 | 2023-04-18 | 1.1073 | 0
|  |  | 2 | 0.521 | 0.026 |  |  |  | 0.03465 |  | 0.46035 | 0.46 | 0.00035 | 152605 | 2023-06-13 | 0.46035 | 0
|  |  | 3 | 1.543 | 0.077 |  |  |  | 0.10262 |  | 1.3634 | 1.363 | 0.00038 | 153561 | 2023-06-24 | 1.3634 | 0
|  |  | Final |  | -0.152 | [5 empty] | 0.152 | 0.152 |  | 177955 | 2024-06-12 | 0.152 | 0
|  |  |  | 3.317 | 0.01365 | 0 | 0 | 0 | 0.22027 | 0 | 3.0831 | 3.082 | 0.00108 |  |  | 3.0831 | 0
3 | M/s Muhammad Rafique Contractor (MRC) | C/2022/P0460/chaharbagh schemeLhr-petty-14 | 1 | 0.951 | 0.04755 |  |  |  | 0.063 |  | 0.84045 | 0.84 | 0.00045 | 148668 | 2023-04-18 | 0.84045 | 0
|  |  | 2 | 0.407 | 0.02 |  |  |  | 0.02709 |  | 0.35991 | 0.36 | -9e-05 | 151414 | 2023-06-05 | 0.35991 | 0
|  |  | 3 | 1.368 | 0.068 |  |  |  | 0.091 |  | 1.209 | 1.209 | 0 | 152504 | 2023-06-07 | 1.209 | 0
|  |  | 4 | 0.531 | 0.012 |  |  |  | 0.041 |  | 0.478 | 0.478 | 0 | 168328 | 2024-01-01 | 0.478 | 0
|  |  | Final |  | -0.148 | [5 empty] | 0.148 | 0.148 | 0 | 183095 | 2024-11-07 | 0.148 | 0
|  |  |  | 3.257 | -0.00045 | 0 | 0 | 0 | 0.22209 | 0 | 3.0354 | 3.035 | 0.00036 |  |  | 3.0354 | 0
4 | M/s Muhammad Rafique Contractor (MRC) | C/2022/P0460/chaharbagh schemeLhr-petty-15 | 1 | 0.806 | 0.04 |  |  |  | 0.054 |  | 0.712 | 0.712 | 0 | 148669 | 2023-04-18 | 0.712 | 0
|  |  | 2 | 0.345 | 0.017 |  |  |  | 0.02296 |  | 0.30504 | 0.305 | 4e-05 | 153555 | 2023-06-24 | 0.30504 | 0
|  |  | 3 | 1.069 | 0.053 |  |  |  | 0.07112 |  | 0.94488 | 0.945 | -0.00012 | 153568 | 2023-06-24 | 0.94488 | 0
|  |  | 4 | 1.077 | 0.05385 |  |  |  | 0.082 |  | 0.94115 | 0.941 | 0.00015 | 159663 | 2023-09-22 | 0.94115 | 0
|  |  | Final |  | -0.151 | [5 empty] | 0.151 | 0.151 | 0 | 183098 | 2024-11-07 | 0.151 | 0
|  |  |  | 3.297 | 0.01285 | 0 | 0 | 0 | 0.23008 | 0 | 3.0541 | 3.054 | 7e-05 |  |  | 3.0541 | 0
5 | M/s Muhammad Rafique Contractor (MRC) | C/2022/P0460/chahar bagh schemeLhr petty-16 | 1 | 3.275 | 0.16375 |  |  |  | 0.21779 |  | 2.8935 | 2.893 | 0.0004625 | 149388 | 2023-05-04 | 2.8935 | 0
|  |  | 2 | 1.179 | 0.059 |  |  |  | 0.0784 |  | 1.0416 | 1.042 | -0.0004 | 151311 | 2023-05-30 | 1.0416 | 0
|  |  | 3 | 2.7799 | 0.139 |  |  |  | 0.18486 |  | 2.456 | 2.456 | 3.7e-05 | 153633 | 2023-06-26 | 2.456 | 0
|  |  | 4 | 4.145 | 0.20725 |  |  |  | 0.315 |  | 3.6227 | 3.623 | -0.00025 | 154334 | 2023-07-18 | 3.6227 | 0
|  |  | 5 | 1.669 | 0.08345 |  |  |  | 0.1268 |  | 1.4587 | 1.459 | -0.00025 | 157731 | 2023-09-08 | 1.4587 | 0
|  |  | Final | 0 | -0.545 | [5 empty] | 0.545 | 0.545 | 0 | 170625 | 2024-01-29 | 0.545 | 0
[16 empty] | 0 | 0
|  |  |  | 13.0479 | 0.10745 | 0 | 0 | 0 | 0.92285 | 0 | 12.0176 | 12.018 | -0.0004005 |  |  | 12.0176 | 0
6 | M/s Muhammad Rafique Contractor (MRC) | C/2022/P0460/chahar bagh schemeLhr petty-17 | 1 | 2.792 | 0.14 |  |  |  | 0.18564 |  | 2.4664 | 2.466 | 0.00036 | 151424 | 2023-06-06 | 2.4664 | 0
|  |  | 2 | 2.761 | 0.13805 |  |  |  | 0.18361 |  | 2.4393 | 2.439 | 0.0003435 | 153445 | 2023-06-22 | 2.4393 | 0
|  |  | 3 | 2.193 | 0.10965 |  |  |  | 0.167 |  | 1.9164 | 1.916 | 0.00035 | 156304 | 2023-08-18 | 1.9164 | 0
|  |  | 4 | 4.789 | 0.23945 |  |  |  | 0.318 |  | 4.2316 | 4.231 | 0.00055 | 148648 | 2023-04-18 | 4.2316 | 0
|  |  | Final | 0 | -0.741 | [5 empty] | 0.741 | 0.639 | 0.102 | 170626 | 2024-01-29 | 0.741 | 0
[13 empty] | 0 |  |  | 0 | 0
|  |  |  | 12.535 | -0.11385 | 0 | 0 | 0 | 0.85425 | 0 | 11.7946 | 11.691 | 0.1036 |  |  | 11.7946 | 0
7 | M/s Muhammad Rafique Contractor (MRC) | C/2022/P0460/chahar bagh schemeLhr petty-19 | 1 | 2.995 | 0.14975 |  |  |  | 0.228 |  | 2.6172 | 2.617 | 0.00025 | 157770 | 2023-09-12 | 2.6172 | 0
|  |  | 2 | 2.0766 | 0.10383 |  |  |  | 0.1578 |  | 1.815 | 1.815 | -3e-05 | 159879 | 2023-10-06 | 1.815 | 0
|  |  | 3 | 1.841 | 0.09205 |  |  |  | 0.1399 |  | 1.6091 | 1.609 | 5e-05 | 163448 | 2023-10-27 | 1.6091 | 0
|  |  | 4 | 1.6789 | 0.083945 |  |  |  | 0.1276 |  | 1.4674 | 1.467 | 0.000355 | 168330 | 2024-01-01 | 1.4674 | 0
|  |  | Final |  | -0.429 |  |  |  | 0.034 |  | 0.395 | 0.395 | 0 | 172168 | 2024-03-20 | 0.395 | 0
[16 empty] | 0 | 0
|  |  |  | 8.5915 | 0.000575 | 0 | 0 | 0 | 0.6873 | 0 | 7.9036 | 7.903 | 0.000625 |  |  | 7.9036 | 0
8 | M/s Muhammad Rafique Contractor (MRC) | C/2022/P0460/chahar bagh schemeLhr petty-21 | 1 | 1.501 | 0.07505 |  |  |  | 0.114 |  | 1.3119 | 1.312 | -5e-05 | 157860 | 2023-09-19 | 1.3119 | 0
|  |  | 2 | 3.32 | 0.166 |  |  |  | 0.252 |  | 2.902 | 2.902 | 0 | 165273 & 165301 | 28/11/2023 & 29-11-2023 | 2.902 | 0
|  |  | 3 | 2.066 | 0.1033 |  |  |  | 0.157 |  | 1.8057 | 1.806 | -0.0003 | 169178 | 2024-01-16 | 1.8057 | 0
|  |  | Final |  | -0.344 |  |  |  | 0.027 |  | 0.317 | 0.317 | 0 | 172119 | 2024-03-15 | 0.317 | 0
[16 empty] | 0 | 0
|  |  |  | 6.887 | 0.00035 | 0 | 0 | 0 | 0.55 | 0 | 6.3366 | 6.337 | -0.00035 |  |  | 6.3366 | 0
9 | M/s Muhammad Rafique Contractor (MRC) | C/2022/P0460/chahar bagh schemeLhr petty-27 | 1 | 6.002 | 0.3001 |  |  |  | 0.456 |  | 5.2459 | 5.246 | -0.0001 | 168948 & 169052 | 08/01/2024 & 11-01-2024 | 5.2459 | 0
|  |  | 2 | 3.133 | 0.15665 |  |  |  | 0.238 |  | 2.7384 | 2.738 | 0.00035 | 169900 | 2024-01-23 | 2.7384 | 0
|  |  | Final | 0 | -0.42 |  |  |  | 0 |  | 0.42 | 0.42 | 0 | 171880 | 2024-02-29 | 0.42 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
|  |  |  | 9.135 | 0.03675 | 0 | 0 | 0 | 0.694 | 0 | 8.4042 | 8.404 | 0.00025 |  |  | 8.4043 | 0
10 | Focus Engg Svcs | Petty -13 | 1 | 3.36 | 0.168 |  |  |  | 0.22344 |  | 2.9686 | 2.53 | 0.43856 | 147311 | 2023-04-10 | 2.9686 | 0
|  |  | 2 | 0.924 | 0.0462 |  |  |  | 0.061446 |  | 0.81635 | 1.254 | -0.43765 | 148705 | 2023-04-19 | 0.81635 | 0
|  |  | 3 | 1.277 | 0.064 |  |  |  | 0.08491 |  | 1.1281 | 1.128 | 9e-05 | 151391 | 2023-06-05 | 1.1281 | 0
|  |  | 4 | 1.482 | 0.074 |  |  |  | 0.09856 |  | 1.3094 | 1.309 | 0.00044 | 152552 | 2023-06-08 | 1.3094 | 0
|  |  | 5 | 3.259 | 0.163 |  |  |  | 0.21672 |  | 2.8793 | 2.879 | 0.00028 | 153562 | 2023-06-24 | 2.8793 | 0
|  |  | 6 | 0.953 | 0.04765 |  |  |  | 0.072 |  | 0.83335 | 0.833 | 0.00035 | 154451 | 2023-07-27 | 0.83335 | 0
|  |  | 7 | 0.614 | 0.0307 |  |  |  | 0.047 |  | 0.5363 | 0.536 | 0.0003 | 157815 | 2023-09-15 | 0.5363 | 0
|  |  | Final |  | -0.594 | [5 empty] | 0.594 | 0.594 |  | 165496 | 2023-12-05 | 0.594 | 0
[16 empty] | 0 | 0
|  |  |  | 11.869 | -0.00045 | 0 | 0 | 0 | 0.80408 | 0 | 11.0654 | 11.063 | 0.002374 |  |  | 11.0654 | 0
11 | M/s Zaid Waqas Engg & Trading | C/2022/P0460/Chahar Bagh/Lhr/Petty-5 (Const of Bdry / Wall Pkg-1 L=5267 Ft | 1 | 0.196 | 0.0098 |  |  |  | 0.013034 |  | 0.17317 | 0.173 | 0.000166 | 153522 | 2023-06-23 | 0.17317 | 0
|  |  | Final |  | -1.857 |  |  |  | 0.12999 |  | 1.727 | 1.727 | 1e-05 |  |  | 1.727 | 0
[16 empty] | 0 | 0
|  |  |  | 0.196 | -1.8472 | 0 | 0 | 0 | 0.14302 | 0 | 1.9002 | 1.9 | 0.000176 |  |  | 1.9002 | 0
12 | M/s Zaid Waqas Engg & Trading | C/2022/P0460/Chahar Bagh/Lhr/Petty-25 (Const of Bdry / Wall | 1 | 3.539 | 0.17695 | 1.401 |  |  | 0.157 |  | 1.804 | 1.804 | 5e-05 | 169096 & 169827 | 12/01/2024 & 19-01-2024 | 1.804 | 0
|  |  | 2 | 3.271 | 0.16355 | 1.026 |  |  | 0.166 |  | 1.9155 | 1.915 | 0.00045 | 170894 | 2024-02-14 | 1.9155 | 0
|  |  | 3 | 1.6613 | 0.083065 | 0.2626 |  |  | 0.10525 |  | 1.2104 | 1.21 | 0.00038805 | 174727 | 2024-04-04 | 1.2104 | 0
|  |  | 4 | 0.71198 | 0.035599 | 0 |  |  | 0.054111 |  | 0.62227 | 0.62228 | -2.25e-06 | 176300 | 2024-05-09 | 0.62227 | 0
|  |  | 5 | 1.1519 | 0.057595 | 0.62115 |  |  | 0.037853 |  | 0.43531 | 0.43531 | -2e-07 | 180357 | 2024-07-17 | 0.43531 | 0
|  |  | 6 | 1.273 | 0.06365 |  |  |  | 0.0968 |  | 1.1125 | 1.113 | -0.00045 | 182185 | 2024-10-01 | 1.1125 | 0
Final
|  |  |  | 11.6082 | 0.58041 | 3.3107 | 0 | 0 | 0.61701 | 0 | 7.1 | 7.0996 | 0.0008858 |  |  | 7.1 | 0
13 | M/s Z.K Builders | C/2022/P0460/Chaharbagh Sch-Lhr-01 | 1 | 11.098 | 0.5549 | 8.554 |  |  | 0.149 |  | 1.8401 | 1.84 | 0.0001 | 154424 | 2023-07-25 | 1.8401 | 0
|  |  | 2 | 5.774 | 0.2887 | 4.231 |  |  | 0.094 |  | 1.1603 | 1.16 | 0.0003 | 163426 | 2023-10-27 | 1.1603 | 0
|  |  | 3 | 7.057 | 0.35285 | 4.702 |  |  | 0.15 |  | 1.8522 | 1.852 | 0.00015 | 163613 | 2023-11-06 | 1.8522 | 0
|  |  | 4 | 3.086 | 0.1543 | 2.496 |  |  | 0.0327 |  | 0.403 | 0.403 | 0 | 169828 | 2024-01-19 | 0.403 | 0
|  |  | 5 | 3.457 | 0.17285 | 1.051 |  |  | 0.1675 |  | 2.0657 | 2.066 | -0.00035 | 170895 | 2024-02-14 | 2.0657 | 0
|  |  | Final |  | -2.75 | [5 empty] | 2.75 | 2.75 |  |  |  | 2.75 | 0
|  |  |  | 30.472 | -1.2264 | 21.034 | 0 | 0 | 0.5932 | 0 | 10.0712 | 10.071 | 0.0002 |  |  | 10.0712 | 0
14 | M/s Bhatti Associates | C/2022/P0460/Chaharbagh Sch-Lhr-02 | 1 | 6.084 | 0.3042 | 4.654 | 0.753 |  | 0.0298 |  | 0.343 | 0.343 | 0 | 159725 | 2023-09-26 | 0.343 | 0
|  |  | 2 | 2.607 | 0.13035 | 1.995 |  |  | 0.038 |  | 0.44365 | 0.444 | -0.00035 | 164653 | 2023-11-13 | 0.44365 | 0
|  |  | 3 | 0.931 | 0.04655 | 0.298 |  |  | 0.047 |  | 0.53945 | 0.539 | 0.00045 | 169829 | 2024-01-19 | 0.53945 | 0
|  |  | 4 | 2.203 | 0.11015 | 0.795 |  |  | 0.104 |  | 1.1938 | 1.194 | -0.00015 | 171900 | 2024-02-29 | 1.1938 | 0
[5 empty] | -1.956 | [5 empty] | 1.956 |  | 1.956 |  |  | 1.956 | 0
|  |  |  | 11.825 | -1.3647 | 7.742 | 0.753 | 0 | 0.2188 | 0 | 4.476 | 2.52 | 1.956 |  |  | 4.476 | 0
15 | M/s Bhatti Associates | C/2022/P0460/Chaharbagh Sch-Lhr-Petty-23 | 1 | 0.722 | 0.0361 | 0.35 |  |  | 0.027 |  | 0.3089 | 0.309 | -0.0001 | 164728 | 20-11-23 | 0.3089 | 0
|  |  | 2 | 6.359 | 0.31795 | 4.689 |  |  | 0.108 |  | 1.2441 | 1.244 | 5e-05 | 169214 | 18-01-24 | 1.2441 | 0
|  |  | 3 | 2.725 | 0.13625 | 2.01 |  |  | 0.046 |  | 0.53275 | 0.533 | -0.00025 | 171253 | 2024-02-15 | 0.53275 | 0
|  |  | 4 | 2.824 | 0.1412 | 1.082 |  |  | 0.128 |  | 1.4728 | 1.473 | -0.0002 | 173015 | 2024-03-27 | 1.4728 | 0
|  |  | Final |  | -0.632 |  |  |  | 0.05056 |  | 0.58144 | 0.581 | 0.00044 | 179599 | 2024-07-05 | 0.58144 | 0
|  |  |  | 12.63 | -0.0005 | 8.131 | 0 | 0 | 0.35956 | 0 | 4.1399 | 4.14 | -6e-05 |  |  | 4.1399 | 0
16 | M/s Al-Hafiz Management Works | C/2022/P0460/Chahar Bagh/Lhr/Petty-24 (Const of Sewerage | 1 | 6.2418 | 0.31209 | 0.4905 |  |  | 0.435 |  | 5.0042 | 5.004 | 0.00021 | 171886,171943 & 172065 | 29/02/2024 & 05-03-2024 & 14-03-2024 | 5.0042 | 0
|  |  | 2 | 2.9646 | 0.14823 | 0.45607 |  |  | 0.18882 |  | 2.1714 | 2.171 | 0.0004457 | 176301&176357 | 09May24-15May24 | 2.1714 | 0
|  |  | 3 | 2.841 | 0.14205 |  |  |  | 0.21593 |  | 2.483 | 2.483 | 2e-05 | 176301&176357 | 09-05-2024-10-05-24 | 2.483 | 0
|  |  | 4 | 2.028 | 0.10141 |  |  |  | 0.154 |  | 1.7726 | 1.773 | -0.000409 | 184150 | 2024-12-16 | 1.7726 | 0
|  |  | Final |  | -0.647 |  |  |  | 0 |  | 0.647 | 0.647 | 0 | 192883 | 2025-01-16 | 0.647 | 0
|  |  |  | 14.0754 | 0.056777 | 0.94657 | 0 | 0 | 0.99375 | 0 | 12.0783 | 12.078 | 0.0002667 |  |  | 12.0783 | 0
17 | M/s The Muhandis | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-26 | 1 | 2.845 | 0.14225 | 0.421 |  |  | 0.183 |  | 2.0988 | 2.099 | -0.00025 | 172019 & 172166 | 12/03/2024 & 20-03-2024 | 2.0988 | 0
|  |  | 2 | 5.1455 | 0.25728 | 0.35987 |  |  | 0.36227 |  | 4.1661 | 4.166 | 0.00010775 | 177900-180162-180457 | 12-06-2024-11June-24-19June-24 | 4.1661 | 0
|  |  | 3 | 4.943 | 0.247 | 0.4382 |  |  | 0.3406 |  | 3.9172 | 3.917 | 0.0002 | 182096-182186 | 27-Sep-01Oct-24 | 3.9172 | 0
|  |  | 4 | 1.3889 | 0.069 |  |  |  | 0.1055 |  | 1.2144 | 1.214 |  | 193741 | 2025-02-12 | 1.2144 | 0
|  |  |  | 14.3224 | 0.71553 | 1.2191 | 0 | 0 | 0.99137 | 0 | 11.3965 | 11.396 | 5.775e-05 |  |  | 11.3965 | 0
18 | M/s Integration Builders and Enterprises | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-28 | 1 | 0.366 | 0.0183 | 0.037 |  |  | 0.025 |  | 0.2857 | 0.286 | -0.0003 | 172067 | 2024-03-14 | 0.2857 | 0
|  |  | 2 | 3.6761 | 0.18381 | 0.32876 |  |  | 0.25308 |  | 2.9105 | 2.91 | 0.0004707 | 176585 | 2024-05-23 | 2.9105 | 0
|  |  | 3 | 2.112 | 0.105 |  |  |  | 0.1605 |  | 1.8465 | 1.847 | -0.0005 | 181235 | 2024-08-16 | 1.8465 | 0
[16 empty] | 0 | 0
|  |  |  | 6.1541 | 0.30711 | 0.36576 | 0 | 0 | 0.43858 | 0 | 5.0427 | 5.043 | -0.0003293 |  |  | 5.0427 | 0
19 | M/s Ejaz & Co | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-29 | 1 | 0.633 | 0.03165 | 0.155 |  |  | 0.036 |  | 0.41035 | 0.41 | 0.00035 | 172884 | 2024-03-22 | 0.41035 | 0
|  |  | 2 | 0.28431 | 0.014216 | 0 |  |  | 0.021608 |  | 0.24849 | 0.24849 | 3.5e-07 | 177901 | 2024-06-12 | 0.24849 | 0
|  |  | 3 | 0.347 | 0.0173 |  |  |  | 0.0264 |  | 0.3033 | 0.303 | 0.0003 | 181331 | 2024-08-23 | 0.3033 | 0
|  |  | 4 | [10 empty] | 197868 | 2025-04-24 | 0 | 0
|  |  |  | 1.2643 | 0.063166 | 0.155 | 0 | 0 | 0.084008 | 0 | 0.96214 | 0.96149 | 0.00065035 |  |  | 0.96214 | 0
20 | RBS | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-32 | 1 | 11.85 | 0.592 |  |  |  | 0.90061 |  | 10.3574 | 10.357 | 0.000392 | 174831-180166-180347 | 05-Apr-11July-12July-24 | 10.3574 | 0
|  |  | Final |  | -0.592 |  |  |  | 0.0473 |  | 0.5447 | 0.545 | -0.0003 | 183094 | 2024-11-07 | 0.5447 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
|  |  |  | 11.85 | 0 | 0 | 0 | 0 | 0.94791 | 0 | 10.9021 | 10.902 | 9.2e-05 |  |  | 10.9021 | 0
[16 empty] | 0 | 0
21 | RBS | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-44 | 1 | 14.276 | 0.7138 |  |  |  | 1.084 |  | 12.4782 | 12.478 | 0.0002 | 193123-193690 | 4-Feb&10-Feb-25 | 12.4782 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
|  |  |  | 14.276 | 0.7138 | 0 | 0 | 0 | 1.084 | 0 | 12.4782 | 12.478 | 0.0002 |  |  | 12.4782 | 0
22 | RBS | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-45 | 1 | 11.02 | 0.551 |  |  |  | 0.83754 |  | 9.6315 | 9.631 | 0.000455 | 193691-193784 | 10-Feb&14-Feb-25 | 9.6315 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
|  |  |  | 11.02 | 0.551 | 0 | 0 | 0 | 0.83754 | 0 | 9.6315 | 9.631 | 0.000455 |  |  | 9.6315 | 0
23 | M/s Integration Builders and Enterprises | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-34 | 1 | 1.0473 | 0.052364 | 0.19308 |  |  | 0.064147 |  | 0.73769 | 0.738 | -0.000311 | 182181 | 2024-10-01 | 0.73769 | 0
|  |  | 2 | 2.0941 | 0.10471 |  |  |  | 0.15915 |  | 1.8302 | 1.83 | 0.000235 | 193021 | 2025-01-28 | 1.8302 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
|  |  |  | 3.1414 | 0.15707 | 0.19308 | 0 | 0 | 0.2233 | 0 | 2.5679 | 2.568 | -7.6e-05 |  |  | 2.5679 | 0
24 | M/s Junaid Sindhu Construction | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-33 | 1 | 2.3562 | 0.11781 |  |  |  | 0.17907 |  | 2.0593 | 2.059 | 0.000326 | 182184 | 2024-10-01 | 2.0593 | 0
|  |  | 2 | 0.68678 | 0.034339 |  |  |  | 0.052195 |  | 0.60025 | 0.6 | 0.000248 | 184236 | 2024-12-26 | 0.60025 | 0
|  |  | 3 | 0.51323 | 0.02566 |  |  |  | 0.039006 |  | 0.44856 | 0.449 | -0.000435 | 184102 | 2024-12-16 | 0.44856 | 0
|  |  | 4 | 1.9887 | 0.099434 | 1.2239 |  |  | 0.0532 |  | 0.61217 | 0.6121 | 7.4e-05 | 188022 | 2025-01-07 | 0.61217 | 0
|  |  | 5 | 5.3898 | 0.26949 | 4.3711 |  |  | 0.059938 |  | 0.68928 | 0.6891 | 0.000184 | 193938 | 2025-02-26 | 0.68928 | 0
|  |  | Final | 0 | -0.547 |  |  |  | 0.044 |  | 0.503 | 0.503
|  |  |  | 10.9347 | -0.000267 | 5.595 | 0 | 0 | 0.42741 | 0 | 4.9126 | 4.9122 | 0.000397 |  |  | 4.9126 | 0
25 | M/s Junaid Sindhu Construction | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-35 | 1 | 1.4691 | 0.073453 |  |  |  | 0.11165 |  | 1.284 | 1.284 | -4.8e-05 | 182191 | 2024-10-01 | 1.284 | 0
|  |  | 2 | 0.76833 | 0.038417 |  |  |  | 0.058393 |  | 0.67152 | 0.672 | -0.000476 | 183088 | 2024-11-07 | 0.67152 | 0
|  |  | 3 | 0.33343 | 0.01667 |  |  |  | 0.02534 |  | 0.29141 | 0.291 | 0.000415 | 184240 | 2024-12-26 | 0.29141 | 0
|  |  | 4 | 2.053 | 0.10265 | 1.3622 |  |  | 0.047056 |  | 0.54113 | 0.541 | 0.000134 | 188021 | 2025-01-07 | 0.54113 | 0
|  |  | 5 | 6.9668 | 0.34834 | 5.4717 |  |  | 0.091743 |  | 1.055 | 1.055 | 4.8e-05 | 194562 | 2025-03-10 | 1.055 | 0
|  |  | 6 |  | -1.224 |  |  |  | 0.098 |  | 1.126 | 1.126 | 0 | 198033 | 2025-05-02
|  |  |  | 11.5907 | -0.64447 | 6.8339 | 0 | 0 | 0.43218 | 0 | 4.9691 | 4.969 | 7.3e-05 |  |  | 4.9691 | 0
26 | M/s Junaid Sindhu Construction | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-36 | 1 | 1.8534 | 0.092669 | 0.32579 |  |  | 0.11479 |  | 1.3201 | 1.32 | 0.000131 | 182095 | 2024-09-27 | 1.3201 | 0
|  |  | 2 | 0.50837 | 0.025415 |  |  |  | 0.0386 |  | 0.44435 | 0.444 | 0.000354 | 183087 | 2024-11-07 | 0.44435 | 0
|  |  | 3 | 1.0085 | 0.05042 |  |  |  | 0.07668 |  | 0.88143 | 0.881 | 0.000426 | 184149 | 2024-12-16 | 0.88143 | 0
|  |  | 4 | 3.6502 | 0.18251 | 3.062 |  |  | 0.032415 |  | 0.37322 | 0.373 | 0.000223 | 188020 | 2025-01-07 | 0.37322 | 0
|  |  | 5 | 7.9664 | 0.39832 | 7.3316 |  |  | 0.01897 |  | 0.2175 | 0.217 | 0.000496 | 193937 | 2025-02-26 | 0.2175 | 0
[5 empty] | -0.749 |  |  |  | 0.0599 |  | 0.6891 | 0.689 | 0.0001 | 200701 | 2025-06-02
|  |  |  | 14.9869 | 0.000333 | 10.7195 | 0 | 0 | 0.34136 | 0 | 3.9257 | 3.924 | 0.001134 |  |  | 3.9257 | 0
27 | M/s Junaid Sindhu Construction | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-40 | 1 | 0.83902 | 0.041951 | 0.74533 |  |  | 0.004139 |  | 0.047599 | 0.048 | -0.000401 | 183097 | 2024-11-07 | 0.047599 | 0
|  |  | 2 | 0.6056 | 0.03028 |  |  |  | 0.046026 |  | 0.5293 | 0.529 | 0.000298 | 188102 | 2025-01-15 | 0.5293 | 0
[11 empty] | 0 |  | 0 |  |  | 0 | 0
[11 empty] | 0 |  | 0 |  |  | 0 | 0
[11 empty] | 0 |  | 0 |  |  | 0 | 0
|  |  |  | 1.4446 | 0.072231 | 0.74533 | 0 | 0 | 0.050165 | 0 | 0.5769 | 0.577 | -0.000103 |  |  | 0.5769 | 0
28 | M/s SS Enterprises | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-38 | 1 | 0.14491 | 0.007245 |  |  |  | 0.011 |  | 0.12666 | 0.127 | -0.000336 |  |  | 0.12666 | 0
|  |  | 2 | 0.93251 | 0.04625 |  |  |  | 0.0708 |  | 0.81546 | 0.815 | 0.000457 | 192971 | 2025-01-23 | 0.81546 | 0
|  |  | 3 | 0.322 | 0.016 |  |  |  | 0.024 |  | 0.282 | 0.282 | 0 | 196574 | 2025-04-10 | 0.282 | 0
[11 empty] | 0 |  | 0 |  |  | 0 | 0
[11 empty] | 0 |  | 0 |  |  | 0 | 0
|  |  |  | 1.3985 | 0.070555 | 0 | 0 | 0 | 0.1064 | 0 | 1.2241 | 1.224 | 0.000121 |  |  | 1.2215 | -0.0025765
29 | M/s SS Enterprises | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-39 | 1 | 0.75242 | 0.037621 |  |  |  | 0.057184 |  | 0.65761 | 0.658 | -0.000386 | 192972 | 2025-01-23 | 0.65761 | 0
|  |  | 2 | 4.7975 | 0.23988 |  |  |  | 0.36461 |  | 4.1931 | 4.193 | 5.6e-05 | 192970 | 2025-01-23 | 4.1931 | 0
|  |  | 3 | 1.72 | 0.086 |  |  |  | 0.13072 |  | 1.5033 | 1.503 | 0.00028 | 196484 | 2025-03-28 | 1.5033 | 0
[11 empty] | 0 |  | 0 |  |  | 0 | 0
[11 empty] | 0 |  | 0 |  |  | 0 | 0
|  |  |  | 7.27 | 0.3635 | 0 | 0 | 0 | 0.55252 | 0 | 6.354 | 6.354 | -5e-05 |  |  | 6.3539 | 0
30 | M/s Adan Construction Services | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-42 | 1 | 2.9769 | 0.14885 | 0.28161 |  |  | 0.20372 |  | 2.3427 | 2.343 | -0.000274 | 184138 | 2024-12-16 | 2.3427 | 0
|  |  | 2 | 1.9956 | 0.09978 | 0.77982 |  |  | 0.089281 |  | 1.0267 | 1.027 | -0.000277 | 193018 | 2025-01-28 | 1.0267 | 0
|  |  | 3 | 1.0532 | 0.052659 | 0.053225 |  |  | 0.075783 |  | 0.8715 | 0.872 | -0.000495 | 194736 | 2025-03-25 | 0.8715 | 0
|  |  | 4 | 2.107 | 0.105 |  |  |  | 0.16 |  | 1.842 | 1.842 | 0 | 200840 | 2025-06-04 | 1.842 | 0
[11 empty] | 0 |  | 0 |  |  | 0 | 0
|  |  |  | 8.1327 | 0.40628 | 1.1147 | 0 | 0 | 0.52878 | 0 | 6.083 | 6.084 | -0.001046 |  |  | 6.083 | 0
31 | M/s Ali Engineering Associates | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-43 | 1 | 2.6503 | 0.13251 | 0.149 |  |  | 0.1895 |  | 2.1792 | 2.179 | 0.000247 | 183096 | 2024-11-07
|  |  | 2 | 0.90881 | 0.04544 |  |  |  | 0.069069 |  | 0.7943 | 0.794 | 0.000299 | 192879 | 2025-01-16
|  |  | 3 | 0.79076 | 0.039504 |  |  |  | 0.06004 |  | 0.69122 | 0.691 | 0.000216 | 188099 | 2025-01-15
|  |  | 4 | 0.6855 | 0.035 |  |  |  | 0.05204 |  | 0.59846 | 0.599 | -0.00054 | 198924 | 2025-05-15
|  |  |  | 0.587 | 0.0294 | 0.0444 |  |  | 0.04 |  | 0.4732 | 0.4732 | 0
|  |  |  | 5.6223 | 0.28186 | 0.1934 | 0 | 0 | 0.41065 | 0 | 4.7364 | 4.7362 | 0.000222
32 | M/s Ali Engineering Associates | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-46 | 1 | 2.9825 | 0.14912 |  |  |  | 0.22667 |  | 2.6067 | 2.607 | -0.000321 | 193826 | 2025-02-17 |  |  | 9.0185
|  |  | 2 | 2.09 | 0.104 |  |  |  | 0.15884 |  | 1.8271 | 1.827 | 0.000145 | 196374 | 2025-03-25
|  |  | 3 | 1.491 | 0.075 |  |  |  | 0.113 |  | 1.303 | 1.303 | 0 | 198034 | 2025-05-02
|  |  | 4 | 1.182 | 0.059 |  |  |  | 0.09 |  | 1.033 | 1.033 | 0
|  |  | 5 | 2.851 | 0.143 |  |  |  | 0.217 |  | 2.491 | 2 | 0.491 | 201774 | 2025-07-18
|  |  |  | 10.5965 | 0.53012 | 0 | 0 | 0 | 0.80551 | 0 | 9.2608 | 8.77 | 0.49082
33 | M/s Ali Engineering Associates | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-47 | 1 | 1.3159 | 0.065796 |  |  |  | 0.1001 |  | 1.15 | 1.15 | 3e-05 | 193745 | 2025-02-12
|  |  | 2 | 1.0406 | 0.05202 |  |  |  | 0.07912 |  | 0.90943 | 0.909 | 0.000431 | 197768 | 2025-04-16
|  |  | 3 | 0.34517 | 0.017259 |  |  |  | 0.026424 |  | 0.30149 | 0.301 | 0.00049 | 197871 | 2025-04-24
|  |  | 4 | 0.348 | 0.017 |  |  |  | 0.026 |  | 0.305 | 0.305 | 0 | 200815 | 2025-06-04
|  |  | 5 | 1.437 | 0.0718 |  |  |  | 0.1092 |  | 1.256 |  | 1.256
|  |  |  | 4.4867 | 0.22388 | 0 | 0 | 0 | 0.34084 | 0 | 3.922 | 2.665 | 0.000951 |  |  |  |  | 0.1092
34 | M/s Ali Engineering Associates | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-48 | 1 | 6.1586 | 0.30793 |  |  |  | 0.46805 |  | 5.3826 | 5.383 | -0.000384 | 193969-194494 | 27 Feb & 6 March-25
|  |  | 2 | 8.82 | 0.441 |  |  |  | 0.67032 |  | 7.7086 | 7.709 | -0.0003696 | 196640-197815-197867 | 14-Apr & 18-Apr & 24-Apr 25
[11 empty] | 0 |  | 0
[11 empty] | 0 |  | 0
[11 empty] | 0 |  | 0
|  |  |  | 14.9786 | 0.74893 | 0 | 0 | 0 | 1.1384 | 0 | 13.0912 | 13.092 | -0.0007536
35 | M/s Muhammad Rafique Contractor (MRC) | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-49 | 1 | 13.0544 | 0.65272 |  |  |  | 0.99213 |  | 11.4095 | 11.41 | -0.000463 | 193884-193968-194529-194559-194598-196438-196646 | 21 Feb & 27 Feb & 6 Mar & 10 Mar & 11 Mar & 27 Mar&14 Apr-2025
|  |  | 2 | 1.862 | 0.093 |  |  |  | 0.1415 |  | 1.6275 | 1.6275 | 0 | 200813 | 2025-06-04
[11 empty] | 0 |  | 0
[11 empty] | 0 |  | 0
[11 empty] | 0 |  | 0
|  |  |  | 14.9164 | 0.74572 | 0 | 0 | 0 | 1.1336 | 0 | 13.037 | 13.0375 | -0.000463
36 | M/s Ali Engineering Associates | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-54 | 1 | 3.3934 | 0.16967 |  |  |  | 0.25789 |  | 2.9658 | 2.966 | -0.000208 | 196486 | 2025-03-28
|  |  | 2 | 1.278 | 0.0639 |  |  |  | 0.097 |  | 1.1171 | 1.117 | 0.0001 | 198974 | 2025-05-19
|  |  | 3 | 0.2174 | 0.011 |  |  |  | 0.016 |  | 0.1904 | 0.1904 | 0 | 200814 | 2025-06-04
[11 empty] | 0 |  | 0
[11 empty] | 0 |  | 0
|  |  |  | 4.8888 | 0.24457 | 0 | 0 | 0 | 0.37089 | 0 | 4.2733 | 4.2734 | -0.000108
37 | M/s Integration Builders and Enterprises | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-59 | 1 | 3.223 | 0.16115 |  |  |  | 0.24459 |  | 2.8173 | 2.8173 | 0 | 196487 | 2025-03-28
|  |  | 2 | 2.627 | 0.131 |  |  |  | 0.2 |  | 2.296 | 2 | 0.296 | 201775 | 2025-07-18
[11 empty] | 0 |  | 0
[11 empty] | 0 |  | 0
[11 empty] | 0 |  | 0
|  |  |  | 5.85 | 0.29215 | 0 | 0 | 0 | 0.44459 | 0 | 5.1133 | 4.8173 | 0.296
38 | M/s GR Engineer Construction Co | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-53 | 1 | 1.8376 | 0.091881 |  |  |  | 0.13966 |  | 1.6061 | 1.606 | 7.5e-05 | 196642 | 2025-04-14
|  |  | 2 | 1.6115 | 0.08145 |  |  |  | 0.1224 |  | 1.4076 | 1.4076 | 0 | 200856 | 2025-06-05
[11 empty] | 0 |  | 0
[11 empty] | 0 |  | 0
[11 empty] | 0 |  | 0
|  |  |  | 3.4491 | 0.17333 | 0 | 0 | 0 | 0.26206 | 0 | 3.0137 | 3.0137 | 7.5e-05
39 | M/s Al Nasir Engineering Svs | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-41 | 1 | 1.4134 | 0.070668 | 0.24083 |  |  | 0.088149 |  | 1.0137 | 1.0137 | 0 | 198964 | 2025-05-16
|  |  | 2 | 5.993 | 0.3 | 1.808 |  |  | 0.311 |  | 3.574 | 3 | 0.574 | 201776-201674 | 2025-07-18
[11 empty] | 0 |  | 0
[11 empty] | 0 |  | 0
[11 empty] | 0 |  | 0
|  |  |  | 7.4064 | 0.37067 | 2.0488 | 0 | 0 | 0.39915 | 0 | 4.5877 | 4.0137 | 0.574
40 | M/s ACC Associates | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-58 | 1 | 1.6108 | 0.08054 |  |  |  | 0.12242 |  | 1.4079 | 1.408 | -0.000149 | 197830 | 2025-04-22
|  |  | 2 | 0.903 | 0.045 |  |  |  | 0.069 |  | 0.789 |  | 0.789
[11 empty] | 0 |  | 0
[11 empty] | 0 |  | 0
[11 empty] | 0 |  | 0
|  |  |  | 2.5138 | 0.12554 | 0 | 0 | 0 | 0.19142 | 0 | 2.1969 | 1.408 | 0.78885
41 | M/s FARCO | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-50 | 1 | 8.4113 | 0.42057 |  |  |  | 0.63926 |  | 7.3515 | 5 | 2.3515 | 200772 | 2025-06-02
[11 empty] | 0 |  | 0
[11 empty] | 0 |  | 0
[11 empty] | 0 |  | 0
[11 empty] | 0 |  | 0
|  |  |  | 8.4113 | 0.42057 | 0 | 0 | 0 | 0.63926 | 0 | 7.3515 | 5 | 2.3515
42 | M/s FARCO | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-51 | 1 | 6.2058 | 0.31029 |  |  |  | 0.47164 |  | 5.4239 | 5.424 | -9.22e-05 | 194660-194700 | 13-Mar & 19-Mar-2025
[11 empty] | 0 |  | 0
[11 empty] | 0 |  | 0
[11 empty] | 0 |  | 0
[11 empty] | 0 |  | 0
|  |  |  | 6.2058 | 0.31029 | 0 | 0 | 0 | 0.47164 | 0 | 5.4239 | 5.424 | -9.22e-05
43 | M/s FARCO | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-52 | 1 | [7 empty] | 0 |  | 0
[11 empty] | 0 |  | 0
[11 empty] | 0 |  | 0
[11 empty] | 0 |  | 0
[11 empty] | 0 |  | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | M/s Al Nasir Engineering Svs | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-60 | 1 | 9.6899 | 0.48449 |  |  |  | 0.73643 |  | 8.4689 | 8.4689 | 0 | 196503-196648-197814 | 28-Mar & 14-Apr & 18Apr-25
|  |  | 2 | 4.153 | 0.208 |  |  |  | 0.316 |  | 3.63 | 3.63 | 0
[11 empty] | 0 |  | 0
[11 empty] | 0 |  | 0
[11 empty] | 0 |  | 0
|  |  |  | 13.8429 | 0.69249 | 0 | 0 | 0 | 1.0524 | 0 | 12.0989 | 12.0989 | 0
45 | M/s Rashid Minhas | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-61 | 1 | 1.2068 | 0.06034 |  |  |  | 0.091717 |  | 1.0548 | 1.055 | -0.000248 | 196422 | 2025-03-26
|  |  | 2 | 2.88 | 0.144 | 2.557 |  |  | 0.01432 |  | 0.16468 | 0.16468 | 0 | 199113 | 2025-05-27
|  |  | Final |  |  | -4.165 |  |  | 0.33325 |  | 3.8318 | 3.832 | -0.000248 | 201760 | 2025-07-15
[11 empty] | 0 |  | 0
[11 empty] | 0 |  | 0
|  |  |  | 4.0868 | 0.20434 | -1.608 | 0 | 0 | 0.43928 | 0 | 5.0512 | 5.0517 | -0.000496
46 | M/s Rashid Minhas | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-62 | 1 | 8.5581 | 0.4279 |  |  |  | 0.65042 |  | 7.4798 | 7.48 | -0.000215 | 197759-197831-197869 | 16Apr-22Apr-24Apr-2025
|  |  | 2 | 2.9424 | 0.14712 |  |  |  | 0.22363 |  | 2.5717 | 2.572 | -0.00031006 | 199031 | 2025-05-20
|  |  | Final |  | -2.4942 | [5 empty] | 2.4942 |  | 2.4942
[11 empty] | 0 |  | 0
[11 empty] | 0 |  | 0
|  |  |  | 11.5005 | -1.9191 | 0 | 0 | 0 | 0.87404 | 0 | 12.5456 | 10.052 | 2.4936
47 | M/s Rashid Minhas | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-63 | 1 | 13.4998 | 0.67499 |  |  |  | 1.026 |  | 11.7988 | 11.799 | -0.00017285 | 196515-196576-196602-197759 | 26Mar-28Mar-10Apr-11Apr-16Apr-2025
|  |  | 2 | 0.452 | 0.0226 |  |  |  | 0.034352 |  | 0.39505 | 0.39505 | 0 | 199114 | 2025-05-27
[11 empty] | 0 |  | 0
[11 empty] | 0 |  | 0
[11 empty] | 0 |  | 0
|  |  |  | 13.9518 | 0.69759 | 0 | 0 | 0 | 1.0603 | 0 | 12.1939 | 12.194 | -0.00017285
47 | M/s Rashid Minhas | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-64 | 1 | 7.8411 | 0.39205 |  |  |  | 0.59592 |  | 6.8531 | 6.853 | 7.8574e-05 | 198923-198956 | 2025-05-15 |  | 7448999 | 595920 |  | 6853079 | 45792 | 198923
[11 empty] | 0 |  | 0 | [6 empty] | 0 | 45793 | 198956
[11 empty] | 0 |  | 0
[11 empty] | 0 |  | 0 |  |  |  | 7841051.5789
[11 empty] | 0 |  | 0
|  |  |  | 7.8411 | 0.39205 | 0 | 0 | 0 | 0.59592 | 0 | 6.8531 | 6.853 | 7.8574e-05
47 | M/S Muhammad Rafique Contractor (MRC | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-66 | 1 | 2.826 | 0.1413 |  |  |  | 0.21478 |  | 2.4699 | 0 | 2.4699
[11 empty] | 0 |  | 0
[11 empty] | 0 |  | 0
[11 empty] | 0 |  | 0
[11 empty] | 0 |  | 0
|  |  |  | 2.826 | 0.1413 | 0 | 0 | 0 | 0.21478 | 0 | 2.4699 | 0 | 2.4699
48 | M/s Ali Engineering Associates | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-65 | 1 | 0.47556 | 0.023778 |  |  |  | 0.036142 |  | 0.41564 | 0 | 0.41564
|  |  | 2 | 0.20034 | 0.010017 |  |  |  | 0.015226 |  | 0.17509 | 0.175 | 9.4538e-05 | 201773 | 2025-07-18
[11 empty] | 0 |  | 0
[11 empty] | 0 |  | 0
[11 empty] | 0 |  | 0
|  |  |  | 0.67589 | 0.033795 | 0 | 0 | 0 | 0.051368 | 0 | 0.59073 | 0.175 | 0.41573
48 | M/s Horti Group | C/2022/P0460/Chahar Bagh Sch-Lhr-Petty-56 | 1 | 7.288 | 0.3644 |  |  |  | 0.55389 |  | 6.3697 | 0 | 6.3697
|  |  |  | 7.288 | 0.3644 | 0 | 0 | 0 | 0.55389 | 0 | 6.3697 | 0 | 6.3697
|  |  |  | 430.0388 | 4.1381 | 68.7397 | 0.753 | 0 | 27.1492 | 0 | 329.2624 | 309.6897 | 18.3161 | 0 | 0 | 323.9094
|  |  |  | -17.0564 | [13 empty] | 227500
|  |  | 0.12195 | 0.17073 | 2.439
|  |  | 0 | 17.0564 | [8 empty] | 19.5726
|  |  |  | 3.815% | [6 empty] | 329.2588

## Anx F Petty
PAYMENT DETAIL OF PETTY CONTRACTORS
PMU NLC INFRA DEV WORKS at Chahar Bagh (RUDA )
Payment Detail
S.No | Contr | Description of Work
|  |  | RAR No | RAR No | Sub Contr's VWD | Retention Money | Material Recovery | Elect Recovery | Sec Adv Recovery | Income Tax 7% | GST | Secured Adv rel | Net Payment Due | Paid Amount | Less / (Over) Paid
1 | [5 empty] | 0
0
| Total |  |  |  | 0 | 0 | 0 | 0 | 0

## Anx G
Anx "G"
[15 empty] | 5.693 | [7 empty] | MONTH - July 2025
DETAIL OF CONST MATERIAL
PMU NLC INFRA DEV WORKS at Chahar Bagh (RUDA )
[23 empty] | Rs in Million | Previous
Item | Unit | Avg Rate | Purchases | [5 empty] | Received from Other Proj |  | Consumed / Recovered | [5 empty] | Tfr to Other Proj |  | Issue To Contractor |  | Balance |  | Remarks | Purchase |  |  |  | Received from Other Proj |  | Consumed/Recovered |  |  |  | Tfr to Other Proj | [6 empty] | Purchases | [6 empty] | Consumed / Recovered | [5 empty] | Balance |  | Remarks
|  |  | During the Month |  | Upto Date |  | Year to Date |  |  |  | During the Month |  | Upto Date |  | Year to Date |  |  |  | Upto date |  | Upto date |  |  | Upto Date |  | Year to Date |  |  |  | Upto Date |  | Year to Date | [8 empty] | Total Qty Req (approx) | During the Month |  | Upto Date |  | Year to Date |  | During the Month |  | Upto Date |  | Year to Date |  | Upto date
|  |  | Qty | Cost | Qty | Cost | Qty | Cost | Qty | Cost | Qty | Cost | Qty | Cost | Qty | Cost | Qty | Cost | Qty | Cost | Qty | Cost |  | Qty | Cost | Qty | Cost | Qty | Cost | Qty | Cost | Qty | Cost | Qty | Cost | [6 empty] | Qty | Cost | Qty | Cost | Qty | Cost | Qty | Cost | Qty | Cost | Qty | Cost | Qty | Cost
Material Purchased
Borrow Material | Cft | 19.2253 |  | 0 | 13249644.25 | 254.728 | 0 | 0 |  |  |  | 0 | 13249644.25 | 254.728 | 0 | 0 |  |  |  |  | 0 | 0 |  | 13249644.25 | 254.728 | 362682 | 6.9727 |  |  | 13249644.25 | 254.728 | 362682 | 1.0878 |  |  | 254.728 |  |  |  | 0 | [7 empty] | 0 | 0
Sub Base | Cft | 89.2665 |  | 0 | 954961 | 85.246 | 0 | 0 |  |  |  | 0 | 954961 | 85.246 | 0 | 0 |  |  |  |  | 0 | 0 |  | 954961 | 85.246 | 324213 | 28.9414 |  |  | 954961 | 85.246 | 419964 | 34.341 |  |  | 77.343 | 85.246
Crush all size | Cft | 138.5671 |  | 0 | 480278 | 66.5507 | 0 | 0 | 301 | 0.040927 |  | 0 | 480278 | 66.5507 | 0 | 0 |  |  |  |  | 301 | 0.040927 |  | 480278 | 66.5507 | 95331.12 | 13.2098 | 301 | 0.040927 | 480278 | 66.5507 | 114034 | 15.61 |  |  | 65.4217 |  | 66.5507 | 64.7249 | 0 | 11.58 | 0 | 0 | 11.58 | 2.3097 | 0 | 0.01158 | 5.143 | 0.098635 | 9.2 | 1.8258 | 5.64 | 1.1193 | 8.02 | 1.5916
Stone Aggregate | Cft | 97.772 |  | 0 | 30162 | 2.949 | 0 | 0 |  |  |  | 0 | 30162 | 2.949 | 0 | 0 |  |  |  |  | 0 | 0 |  | 30162 | 2.949 | 9707 | 0.94907 |  |  | 30162 | 2.949 | 9707 | 0.949 |  |  | 2.949
Stone Dust | Cft | 91.3063 |  | 0 | 457624 | 41.784 | 0 | 0 |  |  |  | 0 | 451653 | 41.2388 | 0 | 0 | 2400 | 0.219 |  |  | 3571 | 0.32619 |  | 457624 | 41.784 | 295451 | 26.9765 |  |  | 451653 | 41.2388 | 348187 | 32.3348 | 2400 | 0.219 | 30.308
Water Bound | Rft | 123.8774 |  | 0 | 1276827 | 158.17 | 0 | 0 |  |  |  | 0 | 1274622 | 157.8968 | 0 | 0 |  |  |  |  | 2205 | 0.27315 |  | 1276827 | 158.17 | 756398 | 93.7006 |  |  | 1274622 | 157.8968 | 860769 | 108.3138 |  |  | 131.837
Cement | Ton | 25571.3479 | 0 | 0 | 6932.285 | 177.2679 | 0 | 0 | 346.2 | 9.3597 | 22 | 0.56257 | 6954.11 | 177.826 | 22 | 0.56257 | 311.025 | 7.9533 |  |  | 13.35 | 0.84828 |  | 6932.285 | 177.2679 | 367.065 | 9.3863 | 346.2 | 9.3597 | 6932.11 | 177.2634 | 1802.11 | 47.3924 | 311.025 | 11.1969 | 161.729
Sand Lawrancpur | Cft | 161.7462 |  | 0 | 354177 | 57.2868 | 0 | 0 |  |  |  | 0 | 354177 | 57.2868 | 0 | 0 |  |  |  |  | 0 | 0 |  | 354177 | 57.2868 | 102985 | 16.6574 |  |  | 354177 | 57.2868 | 107485 | 22.8458 |  |  | 55.454
Sand Chenab | Cft | 66.8 |  | 0 | 1090 | 0.072812 | 0 | 0 |  |  |  | 0 | 1090 | 0.072812 | 0 | 0 |  |  |  |  | 0 | 0 |  | 1090 | 0.072812 | 0 | 0 |  |  | 1090 | 0.072812 | 0 | 0 |  |  | 0.072812
Sand Ravi | Cft | 28.5549 |  | 0 | 520050 | 14.85 | 0 | 0 |  |  |  | 0 | 520050 | 14.85 | 0 | 0 |  |  |  |  | 0 | 0 |  | 520050 | 14.85 | 134874 | 3.8513 |  |  | 520050 | 14.85 | 183020 | 4.759 |  |  | 14.85 |  | 26200
1st Class Bricks | Nos | 17.3004 |  | 0 | 358235 | 6.1976 | 0 | 0 |  |  |  | 0 | 358235 | 6.1976 | 0 | 0 |  |  |  |  | 0 | 0 |  | 358235 | 6.1976 | 11000 | 0.1903 |  |  | 358235 | 6.1976 | 23125 | 0.40361 |  |  | 5.974 |  | 6075.5
2nd Class Bricks | Nos | 12 |  | 0 | 1500 | 0.018 | 0 | 0 |  |  |  | 0 | 1500 | 0.018 | 0 | 0 |  |  |  |  | 0 | 0 |  | 1500 | 0.018 | 0 | 0 |  |  | 1500 | 0.018 | 0 | 0 |  |  | 0.018 |  | 36911700.25
Dry Rammed Bricks | Cft | 87.8156 |  | 0 | 9291.07 | 0.8159 | 0 | 0 |  |  |  | 0 | 9291.07 | 0.8159 | 0 | 0 |  |  |  |  | 0 | 0 |  | 9291.07 | 0.8159 | 0 | 0 |  |  | 9291.07 | 0.8159 | 0 | 0 |  |  | 0.8159 |  | 36.9117
Rec Coat 678 SE | Kg | 1712.605 |  | 0 | 1260 | 2.1579 | 0 | 0 |  |  |  | 0 | 1190 | 2.038 | 0 | 0 |  |  |  |  | 70 | 0.11988 |  | 1260 | 2.1579 | -1910 | -3.2711 |  |  | 1190 | 2.038 | 0 | 0 |  |  | 2.038
Rec Plast SP 42 | Kg | 91.9409 |  | 0 | 35415 | 3.2561 | 0 | 0 |  |  |  | 0 | 35066 | 3.224 | 0 | 0 |  |  |  |  | 349 | 0.032087 |  | 35415 | 3.2561 | 0 | 0 |  |  | 35066 | 3.224 | 890 | 0.082 |  |  | 3.224
Curing Compound | Kg | 120 |  | 0 | 2000 | 0.24 | 0 | 0 |  |  |  | 0 | 100 | 0.012 | 0 | 0 |  |  |  |  | 1900 | 0.228 |  | 2000 | 0.24 | 0 | 0 |  |  | 100 | 0.012 | 0 | 0 |  |  | 0.012 |  |  |  |  | 26250
Fast Grout | Kg | 45 |  | 0 | 1000 | 0.045 | 0 | 0 |  |  |  | 0 | 1000 | 0.045 | 0 | 0 |  |  |  |  | 0 | 0 |  | 1000 | 0.045 | 0 | 0 |  |  | 1000 | 0.045 | 0 | 0 |  |  | 0.045
Expanplast Sp-42 | Kg | 81.9695 |  | 0 | 35050 | 2.873 | 0 | 0 |  |  |  | 0 | 19370 | 1.5877 | 0 | 0 |  |  |  |  | 15680 | 1.2853 |  | 35050 | 2.873 | 2000 | 0.16394 |  |  | 19370 | 1.5877 | 5000 | 0.41 |  |  | 1.5877
Bitumen Gde 800 | Kg | 213.5928 |  | 0 | 5209 | 1.1126 | 0 | 0 |  |  |  | 0 | 5209 | 1.1126 | 0 | 0 |  |  |  |  | 0 | 0 |  | 5209 | 1.1126 | 1449 | 0.3095 |  |  | 5209 | 1.1126 | 1449 | 0.316 |  |  | 1.1126
Ultra Acc 727 | Kg | 146.9388 |  | 0 | 245 | 0.036 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 245 | 0.036 |  | 245 | 0.036 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | [5 empty] | 122000
Rec Flex PV-425 | Tube | 1650 |  | 0 | 240 | 0.396 | 0 | 0 |  |  |  | 0 | 120 | 0.198 | 0 | 0 |  |  |  |  | 120 | 0.198 |  | 240 | 0.396 | 0 | 0 |  |  | 120 | 0.198 | 0 | 0 |  |  | 0.198 |  |  | 30500
Concrete Column, Planks | Rft | 1663 |  | 0 | 1000 | 1.663 | 0 | 0 |  |  |  | 0 | 1000 | 1.663 | 0 | 0 |  |  |  |  | 0 | 0 |  | 1000 | 1.663 | 0 | 0 |  |  | 1000 | 1.663 | 0 | 0 |  |  | 1.663 |  |  | 122000
Binding Wire | Kg | 395.9363 |  | 0 | 7284 | 2.884 | 0 | 0 |  |  |  | 0 | 7284 | 2.884 | 0 | 0 |  |  |  |  | 0 | 0 |  | 7284 | 2.884 | 4304 | 1.7041 |  |  | 7284 | 2.884 | 5304 | 2.1 |  |  | 2.884
Main Hole Cast Iron Rungs | Nos | 1120.2614 |  | 0 | 1508 | 1.6894 | 0 | 0 |  |  |  | 0 | 1508 | 1.6894 | 0 | 0 |  |  |  |  | 0 | 0 |  | 1508 | 1.6894 | 0 | 0 |  |  | 1508 | 1.6894 | 590 | 0.66095 |  |  | 1.0284
Main Hole CI Rings | Kg | 235 |  | 0 | 13855 | 3.2559 | 0 | 0 |  |  |  | 0 | 200 | 1.76 | 0 | 0 |  |  |  |  | 13655 | 1.4959 |  | 13855 | 3.2559 | 3850 | 0.90475 |  |  | 200 | 1.76 | 0 | 0 |  |  | 1.76
High Octagonal Arm Pole | Nos | 143125 |  | 0 | 112 | 16.03 | 0 | 0 |  |  |  | 0 | 109 | 15.6006 | 0 | 0 |  |  |  |  | 3 | 0.42938 |  | 112 | 16.03 | 12 | 1.7175 |  |  | 109 | 15.6006 | 109 | 13.3156 |  |  | 10.305
ASTM 615, Gr-60 #3 (10mm) | Ton | 268216.6104 |  | 0 | 305.135 | 81.8423 | 0 | 0 | 43.81 | 11.7506 | 0.9 | 0.24139 | 261.045 | 70.4994 | 0.9 | 0.24139 | 87 | 21.017 | 0.9 | 0.24139 | -2.276e-14 | 1.8351 |  | 305.135 | 81.8423 | 40 | 10.7287 | 43.81 | 9.31 | 261.045 | 70.258 | 154.277 | 42.0713 | 87 | 21.017 | 70.258 |  | 70.258 | 70.258 |  |  | 0 | 0
ASTM 615, Gr-60 #4 (12mm) | Ton | 272370.0234 |  | 0 | 828.257 | 225.5924 | 0 | 0 |  |  |  | 0 | 797.355 | 217.1756 | 0 | 0 | 30.902 | 8.4168 |  | 0 | 1.5632e-13 | 1.0658e-14 |  | 828.257 | 225.5924 | 142.797 | 38.8936 |  |  | 797.355 | 217.1756 | 184.607 | 48.248 | 30.902 | 8.95 | 217.1756 |  | 217.1756 | 215.3875 |  | 7000 | 2800 | 0.18018 | 24000 | 1.7881 | 19800 | 1.5272 | 7500 | 0.048262 | 24000 | 1.7881 | 20463.1 | 1.5606 | 2713.1 | 0.16524
ASTM 615, Gr-60 #5 | Ton | 282000 |  | 0 | 2 | 0.564 | 0 | 0 |  |  |  | 0 | 2 | 0.564 | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 2 | 0.564 | 0 | 0 |  |  | 2 | 0.564 | 0 | 0 |  | 0 | 0.564
ASTM 615, Gr-60 #6 | Ton | 265440.4248 |  | 0 | 575.4 | 152.7344 | 0 | 0 | 25.741 | 6.8327 |  | 0 | 587.921 | 156.058 | 0 | 0 | 13.22 | 3.1175 |  | 0 | -8.5265e-14 | 0.39162 |  | 575.4 | 152.7344 | 40.48 | 10.745 | 25.741 | 7.639 | 587.921 | 156.058 | 122.082 | 32.6055 | 13.22 | 3.1175 | 156.058
ASTM 615, Gr-60 #8 | Ton | 251325.1941 |  | 0 | 127.835 | 32.1282 | 0 | 0 | 24.524 | 6.1635 | 3.711 | 0.93267 | 142.5 | 37.6777 | 3.711 | 0.93267 |  |  | 3.708 | 0.93191 | 6.151 | -0.31793 |  | 127.835 | 32.1282 | 25 | 6.2831 | 24.524 | 4.869 | 142.497 | 36.745 | 51.681 | 13.466 |  |  | 35.78
ASTM 615, Gr-60 #10 |  | 134156.9396 |  | 0 | 0 | 0 | 0 | 0 | 23.474 | 3.1492 |  | 0 | 0 | 0 | 0 | 0 | 0.68 | 0.0939 |  | 0 | 22.794 | 3.0553 |  | 0 | 0 | 0 | 0 | 23.474 | 3.1492 | 0 | 0 | 0 | 0 | 0.68 | 0.0939
ASTM 615, Gr-60 #11 |  | 275475.3615 |  | 0 | 0 | 0 | 0 | 0 | 29.872 | 8.229 |  | 0 | 0 | 0 | 0 | 0 | 6.419 | 1.7682 |  | 0 | 23.453 | 6.4608 |  | 0 | 0 | 0 | 0 | 29.872 | 8.229 | 0 | 0 | 0 | 0 | 6.419 | 1.7682
HDPE Pipe 90mm PN-10 | Mtr | 779.8663 |  | 0 | 7182 | 5.601 | 0 | 0 |  |  | 0 | 0 | 7182 | 5.601 | 0 | 0 |  |  |  |  | 0 | 0 |  | 7182 | 5.601 | 1590 | 1.24 |  |  | 7182 | 5.601 | 2817 | 2.197 |  |  | 5.601
HDPE Pipe 125mm PN-10 | Mtr | 912.81 |  | 0 | 5453.49 | 4.978 | 0 | 0 |  |  |  | 0 | 5453.49 | 4.978 | 0 | 0 |  |  |  |  | 0 | 0 |  | 5453.49 | 4.978 | 2900.49 | 2.6476 |  |  | 5453.49 | 4.978 | 2900.49 | 1.212 |  |  | 4.978
HDPE Pipe 160mm PN-6 | Mtr | 985.1429 |  | 0 | 24500 | 24.136 | 0 | 0 |  |  |  | 0 | 24500 | 24.136 | 0 | 0 |  |  |  |  | 0 | 0 |  | 24500 | 24.136 | 14000 | 13.792 |  |  | 24500 | 24.136 | 20000 | 16.756 |  |  | 24.136
HDPE Pipe 180mm PN-10 | Mtr | 1952.1368 |  | 0 | 2340 | 4.568 | 0 | 0 |  |  |  | 0 | 2340 | 4.568 | 0 | 0 |  |  |  |  | 0 | 0 |  | 2340 | 4.568 | 0 | 0 |  |  | 2340 | 4.568 | 990 | 0.895 |  |  | 4.568
HDPE Pipe 250mm PN-10 | Mtr | 2672.2973 |  | 0 | 1184 | 3.164 | 0 | 0 |  |  |  | 0 | 1184 | 3.164 | 0 | 0 |  |  |  |  | 0 | 0 |  | 1184 | 3.164 | 0 | 0 |  |  | 1184 | 3.164 | 1069 | 2.487 |  |  | 3.164
HDPE Pipe 315mm PN-10 | Mtr | 9295.7536 |  | 0 | 668.8 | 6.217 | 0 | 0 |  |  |  | 0 | 668.8 | 6.217 | 0 | 0 |  |  |  |  | 0 | 0 |  | 668.8 | 6.217 | 0 | 0 |  |  | 668.8 | 6.217 | 668.8 | 6.217 |  |  | 6.217
HDPE Pipe 355mm PN-10 | Mtr | 11828.2989 |  | 0 | 62.9 | 0.744 | 0 | 0 |  |  |  | 0 | 62.9 | 0.744 | 0 | 0 |  |  |  |  | 0 | 0 |  | 62.9 | 0.744 | 0 | 0 |  |  | 62.9 | 0.744 | 62.9 | 0.744 |  |  | 0.744
UPVC Lasani Pipe 8" | Rft | 725.8557 |  | 0 | 20540 | 14.9091 | 0 | 0 |  |  |  | 0 | 18027 | 13.085 | 0 | 0 |  |  |  |  | 2513 | 1.8241 |  | 20540 | 14.9091 | 5220 | 3.789 |  |  | 18027 | 13.085 | 2821 | 2.116 |  |  | 13.085
UPVC Lasani Pipe 4" | Rft | 256.6138 |  | 0 | 6080 | 1.5602 | 0 | 0 |  |  |  | 0 | 4914 | 1.261 | 0 | 0 |  |  |  |  | 1166 | 0.29921 |  | 6080 | 1.5602 | 1400 | 0.35926 |  |  | 4914 | 1.261 | 280 | 0.07 |  |  | 1.261
RCC Pipes 8"x9" | Nos | 4771.7308 |  | 0 | 156 | 0.74439 | 0 | 0 |  |  |  | 0 | 156 | 0.74439 | 0 | 0 |  |  |  |  | 0 | 0 |  | 156 | 0.74439 | 104 | 0.49626 |  |  | 156 | 0.74439 | 104 | 0.51039 |  |  | 0.31489 | [7 empty] | 12705 | 0.88935 | 12705 | 0.88935 |  |  | 11679.39 | 0.81756 | 11679.39 | 0.81756
RCC Pipes 8"x12" | Nos | 6125.0183 |  | 0 | 273 | 1.6721 | 0 | 0 |  |  |  | 0 | 273 | 1.6721 | 0 | 0 |  |  |  |  | 0 | -2.2204e-16 |  | 273 | 1.6721 | 17 | 0.10413 |  |  | 273 | 1.6721 | 17 | 0.10413 |  |  | 1.6293
RCC Pipes 8"x15" | Nos | 7375.7576 |  | 0 | 165 | 1.217 | 0 | 0 |  |  |  | 0 | 165 | 1.217 | 0 | 0 |  |  |  |  | 0 | 0 |  | 165 | 1.217 | 0 | 0 |  |  | 165 | 1.217 | 0 | 0 |  |  | 1.217
RCC Pipes 8"x18" | Nos | 9166.6667 |  | 0 | 60 | 0.55 | 0 | 0 |  |  |  | 0 | 60 | 0.55 | 0 | 0 |  |  |  |  | 0 | 0 |  | 60 | 0.55 | 0 | 0 |  |  | 60 | 0.55 | 60 | 0.55 |  |  | 0.55
RCC Pipes 8"x21" | Nos | 12504.7368 |  | 0 | 152 | 1.9007 | 0 | 0 |  |  |  | 0 | 152 | 1.9007 | 0 | 0 |  |  |  |  | 0 | 0 |  | 152 | 1.9007 | 0 | 0 |  |  | 152 | 1.9007 | 36 | 0.238 |  |  | 1.9007
RCC Pipes 8"x24" | Nos | 13758.6207 |  | 0 | 261 | 3.591 | 0 | 0 |  |  |  | 0 | 261 | 3.591 | 0 | 0 |  |  |  |  | 0 | 0 |  | 261 | 3.591 | 0 | 0 |  |  | 261 | 3.591 | 99 | 1.327 |  |  | 3.686
RCC Pipes 8"x30" | Nos | 32310.3448 |  | 0 | 116 | 3.748 | 0 | 0 |  |  |  | 0 | 116 | 3.748 | 0 | 0 |  |  |  |  | 0 | 0 |  | 116 | 3.748 | 1 | 0.03231 |  |  | 116 | 3.748 | 1 | 0.03231 |  |  | 3.748
RCC Pipes 8"x36" | Nos | 50000 |  | 0 | 42 | 2.1 | 0 | 0 |  |  | -11 | -0.55 | 42 | 2.1 | -11 | -0.55 |  |  |  |  | 0 | 4.4409e-16 |  | 42 | 2.1 | 0 | 0 |  |  | 53 | 2.65 | 53 | 2.65 |  |  | 2.65
Water Stopper | Rft | 541.6667 |  | 0 | 27000 | 14.625 | 0 | 0 |  |  |  | 0 | 27000 | 14.625 | 0 | 0 |  |  |  |  | 0 | -1.7764e-15 |  | 27000 | 14.625 | 400 | 0.21667 |  |  | 27000 | 14.625 | 9478 | 4.9285 |  |  | 14.625
Fiber Glass Pipe Dia 10'' 6.35 MM Thickness BailPlug | Rft | 2598.05 |  | 0 | 40 | 0.10392 | 0 | 0 |  |  |  | 0 | 40 | 0.10392 | 0 | 0 |  |  |  |  | 0 | 0 |  | 40 | 0.10392 | 0 | 0 |  |  | 40 | 0.10392 | 30 | 0.077961 |  |  | 0.10392 |  | 0.10392 | -0.33233 |  |  |  |  | 1750 | 0.4375 | 1750 | 0.4375 |  |  | 1745 | 0.43625 | 1745 | 0.43625
Fiber Glass Pipe Dia 10'' 6.35 MM Thickness Blind | Rft | 2595.8033 |  | 0 | 1600 | 4.1533 | 0 | 0 |  |  |  | 0 | 1600 | 4.1533 | 0 | 0 |  |  |  |  | 0 | 8.8818e-16 |  | 1600 | 4.1533 | 0 | 0 |  |  | 1600 | 4.1533 | 1200 | 3.1148 |  |  | 3.1669
Fiber Glass Pipe Dia 10'' 6.35 MM Thickness Filter | Rft | 2690.2 |  | 0 | 720 | 1.9369 | 0 | 0 |  |  |  | 0 | 720 | 1.9369 | 0 | 0 |  |  |  |  | 0 | -2.2204e-16 |  | 720 | 1.9369 | 0 | 0 |  |  | 720 | 1.9369 | 540 | 1.4527 |  |  | 0.96847
MS Nipple Dia'' 10'' | Nos | 13750 |  | 0 | 4 | 0.055 | 0 | 0 |  |  |  | 0 | 4 | 0.055 | 0 | 0 |  |  |  |  | 0 | 0 |  | 4 | 0.055 | 0 | 0 |  |  | 4 | 0.055 | 3 | 0.0465 |  |  | 0.055
Ms Well Cap Dia 18'' | Nos | 15750 |  | 0 | 4 | 0.063 | 0 | 0 |  |  |  | 0 | 4 | 0.063 | 0 | 0 |  |  |  |  | 0 | 0 |  | 4 | 0.063 | 0 | 0 |  |  | 4 | 0.063 | 3 | 0.04725 |  |  | 0.0315
Asphat Base course | TOn | 13100.0521 |  | 0 | 7641.42 | 100.103 | 0 | 0 |  |  |  | 0 | 7641.42 | 100.103 | 0 | 0 |  |  |  |  | 0 | 0 |  | 7641.42 | 100.103 | 4941.42 | 64.7329 |  |  | 7641.42 | 100.103 | 4941.42 | 64.733 |  |  | 100.103
HDPE Pipe 50mm | Mtr | 209.8701 |  | 0 | 58717 | 12.3229 | 0 | 0 |  |  |  | 0 | 55390.3066 | 11.6248 | 0 | 0 |  |  |  |  | 3326.6934 | 0.69817 |  | 58717 | 12.3229 | 58717 | 12.3229 |  |  | 55390.3066 | 11.6248 | 55390.3066 | 11.6248 |  |  | 0.808
Sluice Valve 3'' PN-16 | Nos | 12750 |  | 0 | 24 | 0.306 | 0 | 0 |  |  |  | 0 | 10 | 0.1275 | 0 | 0 |  |  |  |  | 14 | 0.1785 |  | 24 | 0.306 | 24 | 0.306 |  |  | 10 | 0.1275 | 10 | 0.1275
Sluice Valve 4'' PN-16 | Nos | 17000 |  | 0 | 26 | 0.442 | 0 | 0 |  |  |  | 0 | 12 | 0.204 | 0 | 0 |  |  |  |  | 14 | 0.238 |  | 26 | 0.442 | 26 | 0.442 |  |  | 12 | 0.204 | 12 | 0.204
Sluice Valve 6'' PN-16 | Nos | 25500 |  | 0 | 2 | 0.051 | 0 | 0 |  |  |  | 0 | 2 | 0.051 | 0 | 0 |  |  |  |  | 0 | 0 |  | 2 | 0.051 | 2 | 0.051 |  |  | 2 | 0.051 | 2 | 0.051
Sluice Valve 8'' PN-16 | Nos | 45000 |  | 0 | 5 | 0.225 | 0 | 0 |  |  |  | 0 | 5 | 0.225 | 0 | 0 |  |  |  |  | 0 | 0 |  | 5 | 0.225 | 5 | 0.225 |  |  | 5 | 0.225 | 5 | 0.225
Sluice Valve 10'' PN-16 | Nos | 70000 |  | 0 | 4 | 0.28 | 0 | 0 |  |  |  | 0 | 4 | 0.28 | 0 | 0 |  |  |  |  | 0 | 0 |  | 4 | 0.28 | 4 | 0.28 |  |  | 4 | 0.28 | 4 | 0.28
UPVC Pipe Conduit Class D Dia 4" | Mtr | 1286.2547 |  | 0 | 396.5 | 0.51 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 396.5 | 0.51 |  | 396.5 | 0.51 | 396.5 | 0.51 |  |  | 0 | 0 | 0 | 0
UPVC Pipe Conduit Class B Dia 4" | Mtr | 743.8399 |  | 0 | 4971.5 | 3.698 | 0 | 0 |  |  |  | 0 | 4971.5 | 3.698 | 0 | 0 |  |  |  |  | 0 | 0 |  | 4971.5 | 3.698 | 4971.5 | 3.698 |  |  | 4971.5 | 3.698 | 4971.5 | 3.698
UPVC 200mm | RFT | 691.2322 |  | 0 | 20540 | 14.1979 | 0 | 0 |  |  |  | 0 | 20540 | 14.1979 | 0 | 0 |  |  |  |  | 0 | 0 |  | 20540 | 14.1979 | 20540 | 14.1979 |  |  | 20540 | 14.1979 | 20540 | 14.1979
HDPE Pipe PN-10 160mm | Nos | 482 |  | 0 | 34347 | 16.5553 | 0 | 0 |  |  |  | 0 | 34347 | 16.5553 | 0 | 0 |  |  |  |  | 0 | 0 |  | 34347 | 16.5553 | 34347 | 16.5553 |  |  | 34347 | 16.5553 | 34347 | 16.5553
Asphalt Wearing | Ton | 14500.0905 |  | 0 | 5527 | 80.142 | 0 | 0 |  |  |  | 0 | 5527 | 80.142 | 0 | 0 |  |  |  |  | 0 | 0 |  | 5527 | 80.142 | 5527 | 80.142 |  |  | 5527 | 80.142 | 5527 | 80.142
1x16mm Circular Compact Green | Mtr | 105.6198 |  | 0 | 6050 | 0.639 | 0 | 0 |  |  |  | 0 | 6050 | 0.639 | 0 | 0 |  |  |  |  | 0 | 0 |  | 6050 | 0.639 | 6050 | 0.639 |  |  | 6050 | 0.639 | 6050 | 0.639
4 x 25mm2 90Al PVC 600/1000V | Mtr |  |  | 0 | 4573 | 0 | 0 | 0 |  |  |  | 0 | 2020 | 0 | 0 | 0 |  |  |  |  | 2553 | 0 |  | 4573 | 0 | 4573 | 0 |  |  | 2020 | 0 | 2020 | 0 |  |  |  |  | 0 | 0
1 X 25MM2 Cu PVC RED 450/750V | Coil |  |  | 0 | 60 | 0 | 0 | 0 |  |  |  | 0 | 15 | 0 | 0 | 0 |  |  |  |  | 45 | 0 |  | 60 | 0 | 60 | 0 |  |  | 15 | 0 | 15 | 0
MS Pipe 8" | Rft | 3398 |  | 0 | 850 | 2.8883 | 0 | 0 |  |  |  | 0 | 850 | 2.8883 | 0 | 0 |  |  |  |  | 0 | 0 |  | 850 | 2.8883 | 850 | 2.8883 |  |  | 850 | 2.8883 | 850 | 2.8883
MS Pipe 10" | Rft | 4193.5496 |  | 0 | 1310 | 5.4935 | 0 | 0 |  |  |  | 0 | 1310 | 5.4935 | 0 | 0 |  |  |  |  | 0 | 0 |  | 1310 | 5.4935 | 1310 | 5.4935 |  |  | 1310 | 5.4935 | 1310 | 5.4935
MS Pipe 12" | Rft | 6076.0526 |  | 0 | 1140 | 6.9267 | 0 | 0 |  |  |  | 0 | 688 | 4.1803 | 0 | 0 |  |  |  |  | 452 | 2.7464 |  | 1140 | 6.9267 | 1140 | 6.9267 |  |  | 688 | 4.1803 | 688 | 4.1803
SLCP | Nos |  |  | 0 | 2 |  | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2 | 0 |  | 2 |  | 2 | 0 |  |  | 0 | 0 | 0 | 0
Graval | Cft | 250 |  | 0 | 9993 | 2.4983 | 0 | 0 |  |  |  | 0 | 9993 | 2.4983 | 0 | 0 |  |  |  |  | 0 | 0 |  | 9993 | 2.4983 | 9993 | 2.4983 |  |  | 9993 | 2.4983 | 9993 | 2.4983
[5 empty] | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
[15 empty] | 0 | 0
[15 empty] | 0 | 0
0
|  |  | 0 | 0 | 18061571.842 | 1744.0533 | 0 | 0 | 794.621 | 45.5256 | 15.611 | 1.1866 | 18010865.6676 | 1722.6836 |  | 1.2826 | 2849.246 | 42.5857 |  |  | 48646.9414 | 23.2323 |  |  | 1744.1493 |  | 503.6965 |  |  |  | 1721.497 |  | 676.7201 |  | 46.4585 |  |  | 1721.497 | 1718.455 |  |  |  |  | 38455 | 3.115 | 34255 | 2.8541 | 7500 |  | 37424.39 | 3.042 | 33887.49 | 2.8144 | 2713.1 | 0.16524
[38 empty] | 0 | 0
[24 empty] | 17922986.492 | 1682.3478 | 2143488.022 | 441.7739 |  |  | 17676785.966 | 1621.2098 |  | 576.4329 |  |  |  |  | 0 | -1.7298 |  |  | 0 | 0 | 8000 | 2.7672 | 8000 | 2.7672 | 1000 | 0 | 5000 | 1.7298 | 5000 | 1.7298 | 0 | 0 |  | 1729760 | 345.952 | 346.18
[38 empty] | 0 | 0
[38 empty] | 0 | -1.7298 |  | 0 | 0 | 0 | 8000 | 2.7672 | 8000 | 2.7672 | 1000 | 0 | 5000 | 1.7298 | 5000 | 1.7298 | 0 | 0
[38 empty] | 0 | 0
[38 empty] | 0 | 0
Grand Total |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 | [15 empty] | 0 | -313.3312 | Grand Total |  | 0 | 0 | 583908.05 | 589.0157 | 455320.77 | 513.0221 | 90605.176 | 0 | 469738.825 | 313.3312 | 361897.698 | 264.6962 | 0 | 0
[8 empty] | 0 | [38 empty] | 248.3258
49.9177
Note : Req Quantities might be change in future due to change in design and deletion / addition of works | [50 empty] | -263.4134
[12 empty] | 6.4584 | [5 empty] | 21.3697 |  |  | -1.8626 | [26 empty] | 8 | 1800 | 14400 |  | 78
[12 empty] | 6.4584 | [35 empty] | 8 | 1200 | 9600
#REF!
[8 empty] | Steel |  |  |  | 229660
[8 empty] | Steel |  |  |  | 232000
[8 empty] | Steel |  |  |  | 215000
676660
[8 empty] | Av Rate |  |  |  | 225553.3333
131714
| 1371.5857 |  | 449500.88 |  | 47340 |  |  | Sand Larancepur |  |  |  | 143
[8 empty] | Sand Larancepur |  |  |  | 146.13
|  |  | 438545 |  |  |  |  | Basra |  |  |  | 125.49
414.62
[8 empty] | Av Rate |  |  |  | 138.2067
[5 empty] | 2324053 |  |  | Sand Chenab |  |  |  | 66
[5 empty] | 2.3241 |  |  | Sand Chenab |  |  |  | 67.92
438708
133.92
[8 empty] | Av Rate |  |  |  | 66.96
[8 empty] | Crush |  |  |  | 142
[8 empty] | Sand Chenab |  |  |  | 152.84 | 147.68
[8 empty] | Sand Chenab |  |  |  | 147.68
442.52
[8 empty] | Av Rate |  |  |  | 147.5067
64.35
[8 empty] | Ultra Chemical |  |  |  | 64.35
[8 empty] | Sand Chenab |  |  |  | 81.9
146.25
[8 empty] | Av Rate |  |  |  | 73.125
Roof Grip Line Modified Bitumen | Sft |  | 0 | 0 | 60000 | 4.2 | 0 | 0 |  |  | 55629 | 3.894 | 55629 | 3.894 |  | 3.894 |  |  |  |  | 4371 | 0.30597 | [18 empty] | 7000 | 0 | 0 | 60000 | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 4.2
[8 empty] | 3 |  |  | 11.269
[8 empty] | 4 |  |  | 33.936
5
6
8
11

## Anx H
Anx "H"
MONTH - July 2025
DETAIL OF EQPTS, PLANTS, MACHINERY
PMU NLC INFRA DEV WORKS at Chahar Bagh (RUDA )
Ser | Description | During the Month | [5 empty] | Upto Date | [5 empty] | Year to Date | [6 empty] | Upto Date | [5 empty] | Year to Date
|  | Hours/Kms | Amount of hiring* (Rs) | Qty of POL Issued | Amount of Fuel Issued (Rs) | Repair/ Maint (Rs) | Total Amount (Rs) | Hours/Kms | Amount of hiring* (Rs) | Qty of POL Issued | Amount of Fuel Issued (Rs) | Repair/ Maint (Rs) | Total Amount (Rs) | Hours/Kms | Amount of hiring* (Rs) | Qty of POL Issued | Amount of Fuel Issued (Rs) | Repair/ Maint (Rs) | Total Amount (Rs) | Diff | Hours/Kms | Amount of hiring* (Rs) | Qty of POL Issued | Amount of Fuel Issued (Rs) | Repair/ Maint (Rs) | Total Amount (Rs) | Hours/Kms | Amount of hiring* (Rs) | Qty of POL Issued | Amount of Fuel Issued (Rs) | Repair/ Maint (Rs) | Total Amount (Rs)
[7 empty] | 0 | - |  |  |  | 0 | 0 | - |  |  |  | 0 | 0 |  | - |  |  |  | 0 | 0 | - |  |  |  | 0 | 0
1 | Hired Vehicle |  | 0 |  |  |  | 0 | [5 empty] | 0 | [18 empty] | 0
[7 empty] | 0 |  |  |  |  | 0 | 0 | [6 empty] | 0 |  | 1.1233 | 13637 | 1.5781 | 0 | 2.7013 |  | 0.215 | 850 | 0.19788 | 0 | 0.41288 |  | Al Makkah Generator Concern
|  | 0 |  |  |  |  | 0 | - |  |  |  | 0 | 0 | - | [5 empty] | 0 | - | 0.40897 | 7995 | 0.94006 | 0 | 1.349 | - | 0 | 0 | 0 | 0 | 0 |  | Al Makkah Generator Concern
|  | 0 |  |  |  |  | 0 | - |  |  |  | 0 | 0 | - | [6 empty] | - | 0.072702 | 150 | 0.036861 | 0 | 0.10956 | - | 0.036351 | 150 | 0.036861 | 0 | 0.073212 |  | Al Makkah Generator Concern
|  | 0 |  |  |  |  | 0 | - |  |  |  | 0 | 0 | - | [5 empty] | 0 | - | 0.40754 | 1315 | 0.26292 | 0 | 0.67046 | - | 0.33253 | 710 | 0.14852 | 0 | 0.48105 |  | Al Makkah Generator Concern
[7 empty] | 0 |  |  |  |  | 0 | 0 | [6 empty] | 0 |  | 0.42405 | 1155 | 0.11189 | 0 | 0.53594 |  | 0.225 | 400 | 0.076702 | 0 | 0.3017 |  | Aswa Construction
[7 empty] | 0 |  |  |  |  | 0 | 0 | [6 empty] | 0 |  | 0.26539 | 825 | 0.053145 | 0 | 0.31853 |  | 0.075 | 0 | 0 | 0 | 0.075 |  | Aswa Construction
[7 empty] | 0 |  |  |  |  | 0 | 0 | [8 empty] | 0.12117 | 0 | 0 | 0 | 0.12117 |  | 0.060585 | 0 | 0 | 0 | 0.060585 |  | Muhammad Shahid
[7 empty] | 0 |  |  |  |  | 0 | 0 | [8 empty] | 0.17955 | 0 | 0 | 0 | 0.17955 |  | 0.089775 | 0 | 0 | 0 | 0.089775 |  | Muhammad Shahid
[7 empty] | 0 |  |  |  |  | 0 | 0 | [6 empty] | 0 |  | 0 | 225 | 0.059175 | 0 | 0.059175 |  | 0 | 0 | 0 | 0 | 0 |  | Muhammad Shahid
[7 empty] | 0 |  |  |  |  | 0 | 0 | [6 empty] | 0 |  | 0 | 2476 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Muhammad Shahid
[7 empty] | 0 |  |  |  |  | 0 | 0 | [6 empty] | 0 |  | 0 | 230 | 0.05685 | 0 | 0.05685 |  | 0 | 230 | 0.05685 | 0 | 0.05685
[7 empty] | 0 |  |  |  |  | 0 | 0 | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  |  |  |  | 0 | 0 | [6 empty] | 0 |  | 0 | 70 | 0.017202 | 0 | 0.017202 |  | 0 | 70 | 0.017202 | 0 | 0.017202
[7 empty] | 0 |  |  |  |  | 0 | 0 | [6 empty] | 0 |  | 0 | 380 | 0.093381 | 0 | 0.093381 |  | 0 | 380 | 0.093381 | 0 | 0.093381 |  | ASWA Construction
[7 empty] | 0 |  |  |  |  | 0 | 0 | [8 empty] | 0.092285 | 0 | 0 | 0 | 0.092285 |  | 0.092285 | 0 | 0 | 0 | 0.092285
[7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | [8 empty] | 0.32306 | 0 | 0 | 0 | 0.32306 |  | 0.16153 | 0 | 0 | 0 | 0.16153 |  | E & W Building Contractor
[7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | E & W Building Contractor
[7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | E & W Building Contractor
[7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | E & W Building Contractor
[7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | [8 empty] | 0.91528 | 0 | 0 | 0 | 0.91528 |  | 0.5666 | 0 | 0 | 0 | 0.5666 |  | Three Star Crane
[7 empty] | 0 |  |  |  |  | 0 | 0 | [6 empty] | 0 |  | 0 | 1070 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Three Star Crane
[7 empty] | 0 |  |  |  |  | 0 | 0 | [6 empty] | 0 |  | 0 | 400 | 0.1052 | 0 | 0.1052 |  | 0 | 0 | 0 | 0 | 0 |  | Three Star Crane
[7 empty] | 0 |  |  |  |  | 0 | 0 | [6 empty] | 0 |  | 0 | 400 | 0.1052 | 0 | 0.1052 |  | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 |  |  |  |  | 0 | 0 | [6 empty] | 0 |  | 0.93288 | 3795 | 0.58003 | 0 | 1.5129 |  | 0.534 | 2245 | 0.49601 | 0 | 1.03 |  | Baber Ali Baber
[7 empty] | 0 |  |  |  |  | 0 | 0 | [6 empty] | 0 |  | 1.1579 | 2549 | 0.39919 | 0 | 1.5571 |  | 0.669 | 1560 | 0.34173 | 0 | 1.0107 |  | MAAKSON Engineering
[7 empty] | 0 |  |  |  |  | 0 | 0 | [6 empty] | 0 |  | 1.1579 | 2305 | 0.37461 | 0 | 1.5325 |  | 0.669 | 1460 | 0.31716 | 0 | 0.98616 |  | MAAKSON Engineering
[7 empty] | 0 |  |  |  |  | 0 | 0 | [6 empty] | 0 |  | 0 | 1250 | 0.31061 | 0 | 0.31061 |  | 0 | 1250 | 0.31061 | 0 | 0.31061 |  | Muhammad Shahbaz
|  |  | 0 | 0 | 0 | 0 | 0 | [22 empty] | 0.26837 | 0 | 0.26837 |  | ASWA Construction
[5 empty] | 0 | 0 | 0 | [22 empty] | 0.1261 | 0 | 0.1261
[5 empty] | 0 | 0 | 0 | [22 empty] | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | [22 empty] | 0 | 0 | 0.239 |  | Shani Travels
[5 empty] | 0 | 0 | 0 | [22 empty] | 0 | 0 | 0.5 |  | Saad Tours & Rent A Car |  | 250000
[5 empty] | 0 | 0 | 0 | [22 empty] | 0 | 0 | 0.5 |  | Saad Tours & Rent A Car |  | 250000
[5 empty] | 0 | 0 | 0 | [22 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | [22 empty] | 0.093488 | 0 | 0.13849
[6 empty] | 0 | 0 | [22 empty] | 0 | 0 | 0.045
1 | Land Cruiser (AEC-242) V8 Model 2012 (HOBC) |  |  |  |  | 0 | 0 | [22 empty] | 0.095836 | 0 | 0.67084
NLC Own Vehicle
1 | E - 655 Gen Set 225 KVA |  | 0 | 0 | 0 | 0 | 0 | [22 empty] | 0.18303 | 0 | 0.18303
2 | 895523 - Toyota Hilux D/C |  | 0 | 0 | 0 | 0 | 0 | [22 empty] | 0 | 0 | 0
3 | 895525 - Toyota Hilux D/C |  | 0 | 0 | 0 | 0 | 0 | [22 empty] | 0.16104 | 0 | 0.16104 |  | 0 | 220
4 | GBA - 128 Toyota D/C |  | 0 | 0 | 0 | 0 | 0 | [22 empty] | 0.074499 | 0 | 0.074499 |  | 0 | 40
5 | GAA - 878 Toyota D/C |  | 0 | 0 | 0 | 0 | 0 | [22 empty] | 0.15698 | 0 | 0.15698 |  | 0 | 40
6 | GBA - 105 Isuzu Pickup |  | 0 | 0 | 0 | 0 | 0 | [22 empty] | 0.075415 | 0 | 0.075415 |  | 0 | 40
7 | 882456 Toyota Hilux D/C |  | 0 |  | 0 | 0 | 0 | [22 empty] | 0 | 0 | 0 |  | 0 | 210
8 | GAA - 2418 Motorcycle Honda CG 125 (Petrol) |  | 0 |  | 0 | 0 | 0 | [22 empty] | 0.017151 | 0 | 0.017151
9 | GAA - 2419 Motorcycle Honda CG 125 (Petrol) |  | 0 |  | 0 | 0 | 0 | [22 empty] | 0.029233 | 0 | 0.029233
10 | LEG-1464 Dump Truck Renault |  | 0 |  | 0.16 | 0 | 0.16 | [22 empty] | 0.29313 | 0 | 0.29313
11 | E-457 Dozor Komatsu size 2 |  | 0 |  | 0 | 0 | 0 | [22 empty] | 0 | 0 | 0
| Conc Pump - 4665 |  |  |  | 0.21177 |  | 0.21177
12 | 7614 - TM ASTRA |  | 0 |  | 0 | 0 | 0 | [22 empty] | 0 | 0 | 0
13 | 0 - Gen Set 2.5 KVA |  | 0 | 0 | 0 | 0 | 0 | [22 empty] | 0 | 0 | 0
14 | E-659 Gen Set 25 KVA (Tranf from Salam Sargodha) |  | 0 | 0 | 0 | 0 | 0 | [22 empty] | 0.039758 | 0 | 0.039758 | 27.06.2022 | E-659 Gen Set 25 KVA (Tranf from Salam Sargodha as on 27.6.2022)
15 | 194 - Gen Set 3 KVA (Petrol) |  | 0 |  |  | 0 | 0 | [22 empty] | 0 | 0 | 0
16 | Motor Grader 558934 |  | 0 | 1090 | 0.25648 | 0 | 0.25648 | [22 empty] | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
Total Amounts (M) |  |  | 0 | 1090 | 0.62825 | 0 | 0.62825 | [22 empty] | 3.7069 | 0 | 9.3376

## Anx J
Anx "J"
MONTH - July 2025
STATUS OF INTERIM PAYMENT CERTIFICATES
PMU NLC INFRA DEV WORKS at Chahar Bagh (RUDA )
Ser | IPC No | Submission Date | Date of approval | Workdone |  |  | Vetted Work Done | Deduction | [5 empty] | Net Receivable | Status | Received From Client | Bal Against UV WD | Bal Against VWD | Remarks
[5 empty] | PST | Variation |  | Retention Money | Mob Adv | Insurance | 5% PST Deduction | Income Tax | Total
1 | Mob Adv Part 1 | [12 empty] | 151.71 |  | 151.71 |  |  | Mob Adv (5%) Chq
2 | Mob Adv Part 2 | [12 empty] | 151.71 |  | 151.71 |  |  | Mob Adv (5%) Chq
3 | IPC No. 3 (Incl PST) | 2022-12-23 | 2023-01-06 | 76.023 | 3.801 |  | 79.824 | 3.9912 | 3.9912 | 2.2806 |  |  | 10.263 | 69.561 |  | 69.561 |  | 0 | IPC # 3 Chq
4 | IPC No. 4 (Incl PST) | 2023-02-13 | 2023-03-07 | 111.231 | 5.662 | 2.028 | 118.921 | 5.946 | 11.892 | -2.281 |  |  | 15.557 | 103.364 |  | 103.364 |  | 0 | IPC # 4 Chq
5 | IPC No. 5 (Incl PST) | 2023-04-10 | 2023-04-20 | 88.371 | 4.419 |  | 92.79 | 4.6395 | 9.279 |  | 0 |  | 13.9185 | 78.8715 |  | 78.8724 |  | 0 | IPC#5 Chq
6 | IPC No. 6 (Incl PST) | 2023-05-27 | 2023-06-08 | 68.158 | 3.631 | 4.453 | 76.242 | 3.8121 | 11.616 |  |  |  | 15.4281 | 60.8139 |  | 60.814 |  | -0.0001 | IPC#6 Chq
7 | IPC No. 7 (Incl PST) | 2023-06-16 | 2023-06-19 | 103.822 | 5.191 |  | 109.013 | 5.4507 | 10.901 |  |  |  | 16.3516 | 92.6613 |  | 92.661 |  | 0.00035 | IPC#7 Chq
8 | IPC No. 8 (Incl PST) | 2023-08-08 | 2023-08-26 | 83.931 | 4.22 | 0.494 | 88.645 | 4.4322 | 8.8645 |  |  |  | 13.2967 | 75.3482 |  | 75.35 |  | -0.00175 | IPC#8 Chq
9 | IPC No. 9 (Incl PST) | 2023-10-16 | 2023-10-26 | 107.757 | 5.5 | 2.148 | 115.405 | 5.7703 | 11.5405 |  |  |  | 17.3108 | 98.0943 |  | 98.09 |  | 0.00425 | IPC#9 Chq
10 | IPC No. 10 (Incl PST) | 2023-11-22 | 2023-12-15 | 136.516 | 7.47 | 12.957 | 156.943 | 7.8471 | 15.6943 |  |  |  | 23.5414 | 133.4015 |  | 133.404 |  | -0.00245 | IPC#10 Chq |  | 118554840
11 | IPC No. 11 (Incl PST) | 2024-01-25 | 2024-01-30 | 322.176 | 16.531 | 8.443 | 347.15 | 17.3575 | 34.715 |  |  |  | 52.0725 | 295.0775 |  | 295.078 |  | -0.0005 | IPC#11 Chq |  | 130967846
12 | IPC No. 12 (Incl PST) | 2024-03-25 | 2024-04-06 | 212.671 | 11.91 | 25.467 | 250.048 | 12.5024 | 25.0048 |  |  |  | 37.5072 | 212.5408 |  | 212.538 |  | 0.0028 |  |  | 175624846
| IPC No. 13 (Incl PST) |  |  | 91.754 | 5.149 | 11.227 | 108.13 | 5.4065 | 43.2521 |  |  | 4.46 | 53.1186 | 55.0114 |  | 55.0112 |  | 0.000169 |  |  | 13171863.45
| IPC No. 14 (Incl PST) |  |  | 225.851 | 12.41 | 22.409 | 260.67 | 13.0335 | 116.671 |  |  | 13.17 | 142.8745 | 117.7955 |  | 117.798 |  | -0.0025 |  |  | 162452982.55
| IPC No.15(Incl PST) | 2024-09-30 | 2024-10-10 | 217.74 | 10.89 |  | 228.63 | 11.4315 |  |  | 198.758 | 16.2899 | 226.4794 | 2.1506 |  | 2.154 |  | 0 | PST of other ruda proj also ded req to be recon Rs 62.00 Million |  | 117795982.55
| IPC No.16(Incl PST) | 2024-12-16 | 2024-12-19 | 219.032 | 10.951 |  | 229.983 | 11.4992 |  |  | 10.951 | 16.3863 | 38.8364 | 191.1466 |  | 191.147 |  | -0.00043875 | 26.95 against Over Ded of PST in next IPC
| IPC No.17(Incl PST) | 2025-02-12 | 2025-02-17 | 235.3934 | 11.7697 |  | 247.1631 | 12.3582 |  |  | 11.7697 | 17.6104 | 41.7382 | 205.4249 |  | 205.425 |  | -8.1179e-05 |  |  | 1074.5761
| IPC No.18 (Incl PST) | 2025-05-23 | 2025-05-27 | 306.8396 | 15.342 |  | 322.1816 | 16.1091 |  |  | 0 | 9.1822 | 25.2913 | 296.8904 |  | 296.89 |  | 0.00036467
|  |  |  | 2607.2661 | 134.8467 | 89.626 | 2831.7387 | 141.5869 | 303.4214 | -0.0004 | 221.4787 | 77.0987 | 743.5853 | 2391.5735 | 0 | 2391.5776 | 0 | 0.00011374 |  | 2972.3904 | 213.6519 | 2451.4756 | -59.8979
[20 empty] | 148.6195 | 860.9242
1 | EPC-01 Upto IPC-7 | 2023-08-08 | 2023-08-26 | 13.255 | 0.66275 |  | 13.9178 | [6 empty] | 13.9178 |  | 13.918 |  | -0.00025 | IPC#8 Chq |  | 68.8739
2 | EPC-02 Upto IPC-9 | 2023-10-16 | 2023-10-26 | 6.097 | 0.30485 |  | 6.4019 | [6 empty] | 6.4019 |  | 6.402 |  | -0.00015 | IPC#9 Chq | 72.8591
3 | EPC-03 Upto IPC-10 | 2023-11-22 | 2023-12-15 | 12.234 | 0.6117 |  | 12.8457 | [6 empty] | 12.8457 |  | 12.847 |  | -0.0013 | IPC#10 Chq
4 | EPC Upto IPC-12 | 2024-03-25 | 2024-04-06 | 59.838 | 2.9919 |  | 62.8299 | [6 empty] | 62.8299 |  | 62.83 |  | -0.0001 | ch #
5 | EPC Upto IPC-14 |  |  | 42.53 | 2.1265 |  | 44.6565 | [6 empty] | 44.6565 |  | 44.657 |  | -0.0005
| Total EPC |  |  | 133.954 | 6.6977 |  | 140.6517 | 0 | 0 | 0 | 0 |  | 0 | 140.6517 | 0 | 140.654 | 0 | -0.0023
Grand Total |  |  |  | 2741.2201 | 141.5444 |  | 2972.3904 | 141.5869 | 303.4214 | -0.0004 | 221.4787 | 77.0987 | 743.5853 | 2532.2252 |  | 2532.2316 | 0 | -0.0021863
[13 empty] | 303.42 | [7 empty] | 260673131 |  | 116671628 | 13033657 | 130967846 | 6548392.3
[5 empty] | 119.7034 |  | 2513.7774 | 118.6562 |  |  |  |  | -0.001385 | [11 empty] | 42530476 | 2126523.8
[18 empty] | -682.446 | [7 empty] | 8674916.1
1849.7856
|  |  |  | 2315.4001 | 2181.4441
|  |  | 0.017 | 0.017
|  |  | 0.014 | 0.014

## Anx k
Anx "K"
MONTH - July 2025
STATE OF CLAIMS / VARIATION ORDERS
PMU NLC INFRA DEV WORKS at Chahar Bagh (RUDA )
Previous
Ser | Type of Claim | Revenue Claimed Expected |  |  | Vetted Cost by Client |  | Contr Exp | NLC Profit | Remarks | Revenue Claimed Expected |  |  | Vetted Cost by Client |  | Contr Exp | NLC Profit | Remarks
|  | During Month | Update | YTD | Update | YTD |  |  |  | During Month | Update | YTD | Update | YTD
EPC (Upto IPC-09) |  | 0 | 141.877 | 0 | 133.954 | 0 | 0 | 0 | NLC Self Execution Work | 0 | 141.877 | 0 | 133.954 | 42.5305 | 0 | 42.5305 |  | 9.3737 | 0
Escl claim unvwd |  | 23 | 63.5 | 23 |  |  |  |  | NLC Self Execution Work | 40.5 | 40.5 | 40.5
PST 5% |  | 0 | 7.0939 | 0 | 6.6977 | 0 |  |  |  | 0 | 7.0939 | 0 | 6.6977 | 2.1265 | 0 |  |  | 0.46869
G.Total Amount in Million |  | 23 | 212.4709 | 23 | 140.6517 | 0 | 0 | 0 |  | 40.5 | 189.4709 | 40.5 | 140.6517 | 44.657 | 0 | 42.5305 |  | 9.8424
0.456
|  |  | 19.049 | 13.419
25.399
-34.9731
[6 empty] | 175.6248 | 8.7812
95.997
79.6278
114.601

## Anx L
Anx "L"
MONTH - July 2025
LIST OF ASSETS
PMU NLC INFRA DEV WORKS at Chahar Bagh (RUDA )
Ser | Category of Asset | Purchase Cost (Rs) | Monthly Depreciation | Depreciation Year to Date | Depreciation up to Date | Accum Dep Adj | Asset's Value | Remarks
1 | Toyota Revo Double Cabin 4x4 GBB-031 | 9251500 | 77095.8333 | 385480 | 1696111.4667 | 0 | 7555388.5333 |  | 77095.8333 | 308384 | 1619015.4667 | 77096 | 77096 | 0
1 | Toyota Hilux Single Cabin 2021 GBA-062 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0
1 | Toyota Hilux Single Cabin 2007 895310 | 942603 | 7855.025 | 39275 | 172810.08 | 0 | 769792.92 |  | 7855.025 | 31420 | 164955.08 | 7855 | 7855 | 0
| Water Bowzer |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0
1 | Issuzu Truck GBA-753 | 3932000 | 32766.6667 | 163834 | 720870.3333 | 0 | 3211129.6667 |  | 32766.6667 | 131067 | 688103.3333 | 32767 | 32767 | 0
| Grader E558 | 7922480 | 66020.6667 | 330105 | 1452460.3333 |  | 6470019.6667 |  | 66020.6667 | 264084 | 1386439.3333 | 66021 | 66021 | 0
| Grader New from Karachi |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
1 | Plain Roller E636 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0
| Motor Cycle GAA-4177 | 168500 | 1404.1667 | 7020 | 30888.3333 |  | 137611.6667 |  | 1404.1667 | 5616 | 29484.3333 | 1404 | 1404 | 0
| Motor Cycle GAA-4178 | 168500 | 1404.1667 | 7020 | 30888.3333 |  | 137611.6667 |  | 1404.1667 | 5616 | 29484.3333 | 1404 | 1404 | 0
| Motor Cycle GAA-4179 | 168500 | 1404.1667 | 7020 | 30888.3333 |  | 137611.6667 |  | 1404.1667 | 5616 | 29484.3333 | 1404 | 1404 | 0
| Computures & IT Eqpts | 312500 | 2604.1667 | 13020 | 34488.3333 |  | 278011.6667 |  | 2604.1667 | 10416 | 31884.3333 | 2604 | 2604 | 0
| Office Eqpts / ICT etc |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
| IT Eqpts | 539690 | 4497.4167 | 22485 | 98934.8333 |  | 440755.1667 |  | 4497.4167 | 17988 | 94437.8333 | 4497 | 4497 | 0
| Photostate Machine | 105007 | 875.0583 | 4375 | 19250.1167 |  | 85756.8833 |  | 875.0583 | 3500 | 18375.1167 | 875 | 875 | 0
| Porta cabin 10x20 with AC 1 Ton | 600750 | 5006.25 | 25030 | 110132.5 |  | 490617.5 |  | 5006.25 | 20024 | 105126.5 | 5006 | 5006 | 0
| Porta cabin with AC & Water Tank | 975162 | 8126.35 | 40630 | 178772.7 |  | 796389.3 |  | 8126.35 | 32504 | 170646.7 | 8126 | 8126 | 0
| Porta cabin with AC 1.5 Ton | 554513 | 4620.9417 | 23105 | 101661.8833 |  | 452851.1167 |  | 4620.9417 | 18484 | 97040.8833 | 4621 | 4621 | 0
| Porta cabin with Wash Room 10x20 | 570521 | 4754.3417 | 23768 | 104588.6833 |  | 465932.3167 |  | 4754.3417 | 19014 | 99834.6833 | 4754 | 4754 | 0
| Porta cabin with AC-1.5 Ton & Wash Room |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
| Porta cabin with AC-1.5 Ton & Wash Room |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
| Porta cabin with AC-1.5 Ton & Wash Room | 1050000 | 8750 | 43750 | 192500 |  | 857500 |  | 8750 | 35000 | 183750 | 8750 | 8750 | 0
| Porta cabin with AC-1.5 Ton 10x20 | 1040000 | 8666.6667 | 43335 | 190673.3333 |  | 849326.6667 |  | 8666.6667 | 34668 | 182006.3333 | 8667 | 8667 | 0
| Furniture | 913966 | 7616.3833 | 38080 | 167552.7667 |  | 746413.2333 |  | 7616.3833 | 30464 | 159936.7667 | 7616 | 7616 | 0
| Lab Eqpts | 745754 | 6214.6167 | 31075 | 127949 |  | 617805 |  | 6214.6167 | 24860 | 121734 | 6215 | 6215 | 0
| Svy Eqpts |  | 0 |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0
| 2x AC 1 Ton | 61340 | 511.1667 | 2555 | 8176 |  |  |  | 511.1667 | 2044 | 7665 | 511 | 511 | 0
| Vibrator Engine | 26000 | 216.6667 | 1085 | 3472 |  |  |  | 216.6667 | 868 | 3255 | 217 | 217 | 0
| Transformer 200KVA | 0 | 0 |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0
| Hair AC 1.5 Ton | 147900 | 1232.5 | 6165 | 14796 |  |  |  | 1232.5 | 4932 | 13563 | 1233 | 1233 | 0
| Hair LCD 65" | 219901 | 1832.5083 | 9165 | 20163 |  |  |  | 1832.5083 | 7332 | 18330 | 1833 | 1833 | 0
| Jumping Compactor Machine | 91500 | 0 | [5 empty] | 0
|  | 30508587 | 253475.725 | 1267377 | 5508028.3633 | 0 | 24500524.6367
Total (Rs in Million) |  | 30.5086 | 0.25348 | 1.2674 | 5.508 | 0 | 24.5005

## Anx M
Anx "M"
MONTH - July 2025
DETAILS OF LIABILITIES
PMU NLC INFRA DEV WORKS at Chahar Bagh (RUDA )
1 | Against Contractor/Supplier |  |  |  |  | Amount (M)
|  | a. | Payable to contrs ( VWD) |  | - | 18.3161
|  |  | Payable against Un Vetted Work Done |  |  | 17.0564
|  | b. | Rentention Money Payable |  | - | 4.1381
|  | c. | Income tax payable |  | - | 0 | Already paid amount
|  | d. | Const Mat |  | - | 52.848 | 506355
|  |  | Sub Total |  |  | 92.3585 | 2558858
1614311
4679524
2 | Other Payables | [5 empty] | 17.98
|  | a. | Payable against Mob Adv received from Client |  | - | -0.001385
|  | b. | Payable against Hiring Charges |  | - | 0
|  | c | Muster Roll |  |  | 0
|  | d | Recoupment |  |  | 0
|  |  | Provision for PST accrued ( exp ) |  |  | 0
|  |  | Sub Total |  |  | -0.001385
|  |  | Grand Total |  |  | 92.3571
|  |  | 0.093 | 0.093
|  |  | 0.017 | 0.017
|  |  | 0.014 | 0.014

## Anx N
Anx "N"
MONTH - July 2025
BUDGETING OF PROJECT
PMU NLC INFRA DEV WORKS at Chahar Bagh (RUDA )
Total Expenditure as per Exec Plan |  | 3171.245 | Million
Already Expended Amount Uptodate |  | 3255.7099 | Million
Work Done Uptodate |  | 3501.3231 | Million
Bal Amount to be Expended |  | -84.4649 | Million
Bal Work Done to be Done |  | 61.8749 | Million |  |  | Rs. In Million
Ser | Description | Exp as per Rev Exec Plan | Already Expended |  | Exp on Bal Work
|  |  | Amount In Million | %age | Amount In Million | %age | [8 empty] | 2267.02
Work Expenditures
1 | Stores | [9 empty] | 511.551
| Const Mat & EQPT | 1183.25 | 1722.6836 | 0 | 0 |  |  |  | 94.308 |  | 41.386
| Engr Facility | 0 | 0 | 0 | 0 |  |  |  | 523.551 |  |  |  | 78.76
2 | Sub Contr Cost | 1346.397 | 375.9944 | 0 | 0 |  |  |  | 470.165
3 | Plants and Machinery | 0 | 0 | 0 | 0 |  |  |  | 462.784 |  |  |  |  | 511.551
| a. Hiring Charges / POL | 260 | 261.7931 | 0 | 0 | [8 empty] | 470.165
| b. Repair/ Maint | 0 | 10.6372 | 0 | 0
|  | 0 | 0 | 0 | 0 | [6 empty] | 1346.531 | 1306.031 | 41.386
4 | Direct Labour | 0 | 0 | 0 | 0 | [6 empty] | 159.481 | 1187.05
| a. Labour Cost | 36.54 | 0 | 0 | 0 |  | 18 | [5 empty] | 118.981
| b. Salaries Civilian Personals | 0 | 0 | 0 | 0
| c. Wages/ Muster Roll | 0 | 23.9851 | 0 | 0
5 | Any Other | 0 | 0 | 0 | 0
| a. Depreciation against FA | 0 | 0 | 0 | 0
| b. Office Estb | 12.103 | 12.103 | 0 | 0
| c. Other Expenditure |  | 65.551 |  | 0
| d. PST 5% | 169.676 | 157.1398 | 0 | 0
| e. Proj Maint cost | 33.93 | 31.0495 | 0 | 0 |  | 118.091
| Total Work Expenditure | 3041.896 | 2660.9369 | 87.48% | 380.9591 | 12.52%
Overhead Expenditures
1 | Pay & Allowances | 0 | 0 |  | 0
| a. Army Personals | 0 | 0 |  | 0
| b. Civ Personals | 82.477 | 147.588 |  | 0 |  | 0.076659
2 | Over Head Exp | 0 | 0 |  | 0
| a. POL Exp | 6 | 2.3785 |  | 0
| b. Depriciation | 6.24 | 7.534 |  | 0
| c. Other Expenditure | 34.632 | -77.5055 |  | 0
| Total Overhead Expenditure | 129.349 | 79.995 | 61.84% | 49.354 | 38.16%
| Total Expenditure | 3171.245 | 2740.9319 | 149.3% | 430.3131 | 50.68%
| Total Expected Revenue Incl Claims / VOs |  | 3563.195 | M
| Total Expected Expenditure on Completion |  | 3001.571 | M |  |  | 35.632 | 2427.362 | 2268.03 | 2427.36
| PST Deduction |  | 169.676 | M |  |  |  |  | 2361.75 | 121.368
| Other Income |  | 0 | M | [5 empty] | 2548.728
| Net Profit / (Loss) |  | 391.948 | M
| Net Profit %age |  | 11% |  |  |  | 3034.216
2701.58
332.636

## Anx O
Anx "O"
MONTH - July 2025
DETAIL OF MT,LAB AND HANDLING CHARGES RECOVERIES
PMU NLC INFRA DEV WORKS at Chahar Bagh (RUDA )
Ser | Activity | Amount in Rs
|  | During the Month | Total up to Date | Running Total YTD
1 | Plant & Machinery Hiring Income | 0 | 0 | 0
2 | Bank Profit |  | 0.23398 | 0 | 0.025985
3 | Veh on payment
4 | Temp work claim | 0 | 0 | 0 |  | 0.00669
a) | Concrete Sale | 0 | 40.121 | 0
b) | 3% Handling Charges | 0 | 0.0013 | 0
c) | POL issue to CB-II ( Already exp in anx D) | 4.469 | 4.469 | 4.469
d) |  | 0 | 0 | 0
e) |  | 0 | 0 | 0
f) |  | 0 | 0 | 0
| Total (Rs in Million) | 4.469 | 44.8253 | 4.469
544774
544773.766
|  |  | 0.093 | 0.093
|  |  | 0.017 | 0.017
|  |  | 0.014 | 0.014

## Appx I to Anx A
Appx I to Anx "A"
PMU NLC INFRA DEV WORKS at Chahar Bagh (RUDA )
CA Amount (As per Ltr of Award) |  | 3034.34 |  | Revised CA Amount Addl Work |  | 3563.198
Re-revise CA Amount
Start Date (As per Ltr of Award) |  | 2022-11-02 |  | Completion Date (As per Ltr of Award) |  | 2024-11-02 | 6.9503
Month | During the Month |  | Progressive (Upto Date) |  | Upto Date Progress % |  | 145.9563
| Planned | Achieved | Planned | Achieved | Planned | Achieved
2022-11-01 | 28.586 | 28.586 | 28.586 | 28.586 | 0.80226 | 0.8023%
2022-12-01 | 60.945 | 60.945 | 89.531 | 89.531 | 2.513% | 2.513%
2023-01-01 | 49.475 | 49.475 | 139.006 | 139.006 | 3.901% | 3.901%
2023-02-01 | 70.994 | 70.994 | 210 | 210 | 5.894% | 5.894%
2023-03-01 | 63.102 | 63.102 | 273.102 | 273.102 | 7.665% | 7.665%
2023-04-01 | 62.479 | 62.479 | 335.581 | 335.581 | 9.418% | 9.418%
2023-05-01 | 82.552 | 82.552 | 418.133 | 418.133 | 11.73% | 11.73%
2023-06-01 | 104.596 | 104.596 | 522.729 | 522.729 | 14.67% | 14.67%
2023-07-01 | 63.712 | 63.712 | 586.441 | 586.441 | 16.46% | 16.46%
2023-08-01 | 60.849 | 60.849 | 647.29 | 647.29 | 18.17% | 18.17%
2023-09-01 | 96.74 | 96.74 | 744.03 | 744.03 | 20.88% | 20.88%
2023-10-01 | 83.362 | 83.362 | 827.392 | 827.392 | 23.22% | 23.22%
2023-11-01 | 153.031 | 153.031 | 980.423 | 980.423 | 27.52% | 27.52%
2023-12-01 | 169.576 | 169.576 | 1149.999 | 1149.999 | 32.27% | 32.27%
2024-01-01 | 98.921 | 98.921 | 1248.92 | 1248.92 | 35.05% | 35.05%
2024-02-01 | 105.161 | 105.161 | 1354.081 | 1354.081 | 38% | 38%
2024-03-01 | 92.495 | 92.495 | 1446.576 | 1446.576 | 40.6% | 40.6%
2024-04-01 | 86.417 | 86.417 | 1532.993 | 1532.993 | 43.02% | 43.02%
2024-05-01 | 133.379 | 133.379 | 1666.372 | 1666.372 | 46.77% | 46.77%
2024-06-01 | 107.552 | 107.552 | 1773.924 | 1773.924 | 49.78% | 49.78%
2024-07-01 | 111.719 | 111.719 | 1885.643 | 1885.643 | 52.92% | 52.92%
2024-08-01 | 113.751 | 113.751 | 1999.394 | 1999.394 | 56.11% | 56.11%
2024-09-01 | 61.313 | 61.313 | 2060.707 | 2060.707 | 57.83% | 57.83%
2024-10-01 | 143.962 | 143.962 | 2204.669 | 2204.669 | 61.87% | 61.87%
2024-11-01 | 145.995 | 145.995 | 2350.664 | 2350.664 | 65.97% | 65.97%
2024-12-01 | 58.8 | 58.8 | 2409.464 | 2409.464 | 67.62% | 67.62%
2025-01-01 | 90 | 83.586 | 2499.464 | 2493.05 | 70.15% | 69.97%
2025-02-01 | 160 | 152.171 | 2659.464 | 2645.221 | 74.64% | 74.24%
2025-03-01 | 102.275 | 102.275 | 2761.739 | 2747.496 | 77.51% | 77.11%
2025-04-01 | 210.484 | 210.484 | 2972.223 | 2957.98 | 83.41% | 83.01%
2025-05-01 | 85 | 55.1496 | 3057.223 | 3013.1296 | 85.8% | 84.56%
2025-06-01 | 250 | -25.6198 | 3307.223 | 2987.5098 | 92.82% | 83.84%
2025-07-01 | 156 |  | 3463.223 |  |  |  |  | 86.2 | 86.2 | 86.2 | 101 | 150.79
2025-08-01 | 100 |  | 3563.223
[8 empty] | 100 | 60

## w.d detail
INFRASTRUCTURAL DEVELOPMENT WORKS AT CHAHAR BAGH (RUDA) LAHORE
Employer: RAVI URBAN DEVELOPMENT ATHORITY (RUDA) AT CHAHAR BAGH |  | Main Summary
Consultant: M/S National Engineering Services Pakistan |  | Month of November Work Done
Contractor: National Logistic Cell (NLC)
BILL NO. 1: EARTH WORK AND ALLIED ACTIVITIES
Pay Item No. | Description | Unit | Quantity | Original BOQ |  | Total To Date |  | %age Completed Todate
|  |  |  | Rate | Amount (Rs.) | Quantity | Amount (Rs.)
1 | Clearing, Grubbing with Stripping. Removal and Disposal of Unsuitable & Surplus material from the project area including all lead & lift. | CM | 17116 | 478 | 8181448 | 3383.65 | 1617385 | 19.77%
2 | Peparation of natural ground by Compaction of earthwork with power road roller, including ploughing, mixing, moistening earth to optimum moisture content in layers, etc. complete 6 inches |  |  |  | 0 | 0 | 0
| With 90% minimum compaction of modified AASHTO dry Density | CM | 22821.6 | 55 | 1255188 | 4445.1048 | 244481 | 19.48%
6 | Making Embankment With Borrow in ordinary soil for embankments lead upto 100 ft. (30 m), including ploughing and mixing with blade grade or disc harrow or other suitable equipment, and compaction by mechanical means at optimum moisture content and dressing to designed section, complete in all respects:- |  |  |  | 0 | 0 | 0
| With 90% Compaction of AASHTO dry density. | CM | 163623 | 1385 | 226617855 | 18313.385 | 25364039 | 11.19%
| Total of Bill 1 - Carried to Summary |  |  |  | 236054491 |  | 27225905 | 11.53%
886666.6667

## Tax on Jul to Oct-24
PMU Chahar Bagh Project
Ser | Proj Name | Un-Vetted W.D ( Jun 24 ) | VWD Receivable( Jun 24) | Exeucted W.D Jul to Oct-24 | Total Revenue | Tax Amount
a | b | g | h |  | I=g+h | J=I*7.5%
1 | Chahar Bagh | 283.31 | 0 | 577.148 | 860.458 | 64.5344