## Summary
SUMMARY OF MONTHLY MONITORING REPORT
Re-Modelling and Up Gradation of ADA Nullah and Walton Road Pkg-I
Rs in Million
1 | Proj Con
2 | Name of Proj
3 | Month |  | JUL, 2025
4 | Progress
| a. | Physical | As per Contract Cost
|  | (1) Planned Targets | 1553.652
|  | (2) Achieved | 2353.649
5 | Schedule of Proj
| a. | Start Date of Project | 2023-10-16
| b. | CA Date of Completion | 2025-04-08
| c. | Date of Completion as per actual site.
6 | Financial State
| a. | Original Cost of Proj | 9573.926
| b. | Revised Cost (approx) Addl Work | 0
| c. | Funds Received from Client | 1202.7942
| d. | Cost of Work upto Previous Month Incl Escl | 2461.0505
| e. | Cost of Work Done during the month by Proj Con / Own WD
| f. | Cost of Work Done during the month by Petty Contrs
| g. | Total Cost of Work Done during the month by Proj Con / Hired Lab & Petty Contrs (e+f) incl ESCL
| h. | Total Cost of Work Done till to date (g+d)
| j. | Other Income against (MT, Lab & Handling Charges)
| k. | Total Revenue (j+h)
| l. | Assets
| m. | Exp upto last month
| n. | Exp during the month
| o. | Total Exp till to date (m+n)
| p. | Liabilities till to date as per Anx 'M'
| q. | Total Cost of work done excl Escl
| r. | Total Cost of vetted work
| s. | Slippage (q-r)
| t. | Escalation claimed / Other Claims
| u. | Any Other Claims
| v. | Financial Health
(1) Based on vetted work done
(2) Based on Work Done
7 | Reasons for Delay in Progress
8 | Any Special Activity Carried out
9 | Remarks:
Formulas:
As per Contract Cost = '[2]Anx A'!H6

## Anx-A
Anx 'A'
PROJ HIGHLIGHTS AS ON JUL-25
Re-Modelling and Up Gradation of ADA Nullah and Walton Road Pkg-I
1 | Schedule of Project
| a. Date of Commencement | [5 empty] | 2023-10-16
| b. Date of Completion | [5 empty] | 2025-04-08
| c. 1st EOT | [5 empty] | 2025-07-05
2 | Client / Consultant | [5 empty] | CBD /NESPAK
3 | Progress |  |  |  |  | UPTO DATE WORK
| Work Done |  |  |  |  | Rs (Million) | %age
|  | (1) Planned Targets |  |  |  | 9899.999 | 100%
|  | (2) Achieved (As per Expected Completion Cost) |  |  |  | 9571.3758 | 96.68%
4 | Financial State | [5 empty] | Rs (Million)
| a. Original Cost of Project as per Contract Agreement | [5 empty] | 9573.926
| b. Revised Cost Est Cost ( Incl PSt 5% ) (VO in process) | [5 empty] | 9900
| c. Total Funds Received from Client incl Mob Adv and income tax | [5 empty] | 7442.3379 |  |  | 18600
| d. Total Funds Released to Project by PD Office | [5 empty] | 3877.571
Anx-J
5 | Income State (Based on Actual Profit Achieved) | [14 empty] | Vetted
[9 empty] | 7406552168 |  |  |  |  | #REF! |  | #REF!
|  |  | Work Done |  |  | Vetted Work |  |  | Work Done |  |  | Vetted Work
|  |  | During The Month | Upto Date | Year to Date | Upto Date | Year to Date | 18.2 | During The Month | Upto Date | Year to Date | Upto Date | Year to Date | Upto Date | Year to Date | Upto Date | Year to Date
|  | Revenue of Proj | [5 empty] | 49
|  | Workdone | 37.4955 | 9571.3756 | 37.4955 | 8624.2706 | 0 | #REF! | 0 | 9533.8801 | 0 | 8624.2706 | 0 | 37.4955 | 37.4955 | 0 | 0 | 0
|  | EPC's / Other Claims | 0 | 134.4137 | 0 | 134.4137 | 0 | #REF! | 0 | 134.414 | 0 | 134.414 | 0 | -0.00035 | 0 | -0.00035 | 0
|  | Total Work Done | 37.4955 | 9705.7892 | 37.4955 | 8758.6842 | 0 | 391.82 | 0 | 9668.2941 | 0 | 8758.6846 | 0
|  | Direct Cost | 16.4584 | 8579.6277 | 16.4586 | 8579.6277 | 16.4586 | 405.82 | 0 | 8563.1694 | 0 | 8563.1694 | 0 | 16.4582 | 16.4586 | 16.4582 | 16.4586 | 0.00015337 | -0.0003538
|  | Gross Profit | 21.0371 | 1126.1616 | 21.0369 | 179.0565 | -16.4586 | 485.2895 | 0 | 1105.1247 | 0 | 195.5151 | 0 | 21.0369 | 21.0369 | -16.4586 | -16.4586
|  | Gen & Adm Exp | 10.518 | 219.9149 | 10.518 | 219.9149 | 10.518 |  | 0 | 209.3969 | 0 | 209.3969 | 0 | 10.518 | 10.518 | 10.518 | 10.518
|  | Operating Profit | 10.5191 | 906.2467 | 10.5189 | -40.8584 | -26.9766 |  | 0 | 895.7278 | 0 | -13.8818 | 0 | 10.5189 | 10.5189 | -26.9766 | -26.9766
|  | Financial Charges | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Other Income | -9.466 | 103.8249 | -9.466 | 103.8249 | -9.466 |  | 0 | 113.2909 | 0 | 113.2909 | 79.5866 | -9.466 | -9.466 | -9.466 | -89.0526 | 0
|  | Net Profit before Income Tax (Million) | 1.0531 | 1010.0716 | 1.0529 | 62.9666 | -36.4426 |  | 0 | 977.2715 | 650.1755 | 357.3169 | 298.282 | 32.8001 | -649.1226
|  | Net Profit %age | 2.809% | 10.41% | 2.808% | 0.7189% | #DIV/0! |  | 0% | 10.42% | 13.97% | 4.08% | 6.932%
|  | tax deduction at source | 5.07 | 353.2198 | 5.07 | 353.2198 | 5.07 | 2.8122
|  | Profit after Tax | -4.0169 | 656.8518 | -4.0171 | -290.2533 | -41.5126
|  | Net Profit %age | -10.71% | 6.768% | -10.71% | -3.314% | #DIV/0! |  | #REF!
[8 empty] | 460.327 | 5520%
6 | Income State as per IFRS-15 (Based on Estimated/Initial Profit) | [7 empty] | 3700 |  | 7951.11
|  |  | Work Done |  |  | Vetted Work |  |  | 79% |  | 397.5555
|  |  | During The Month | Upto Date | Year to Date | Upto Date | Year to Date |  |  |  | 8348.6655 | 7460
|  | Revenue of Proj | [6 empty] | 7937.87 |  | Oct | 8758.6846
|  | Workdone | 37.4955 | 9571.3756 | 37.4955 | 0 | 0 |  | 396.8935 |  | Nov | #REF!
|  | EPC's / Other Claims | 0 | 134.4137 | 0 | 0 | 0 |  | 8334.7635 |  |  | #REF!
|  | Total Work Done | 37.4955 | 9705.7892 | 37.4955 | 0 | 0 |  | 1236.6121
|  | Direct Cost | 33.566 | 8688.6225 | 33.566 | 0 | 0
|  | Gross Profit | 3.9295 | 1017.1667 | 3.9295 | 0 | 0
|  | Gross Profit % | 10.48% | 10.48% | 10.48% | 0 | 0
|  | Financial Charges | 0 | 0 | 0 | 0 | 0
|  | Other Income | 0 | 0 | 0 | 0 | 0
|  | Net Profit (Million) | 3.9295 | 1017.1667 | 3.9295 | 0 | 0
|  |  | 10.48% | 10.48% | 10.48% | 0 | 0
|  | tax deduction at source | 5.07 | 353.2198 | 5.07 | 0 | 0
|  | Profit after Tax | -1.1405 | 663.9469 | -1.1405 | 0 | 0
|  | Net Profit %age | -3.042% | 6.841% | -3.042%

## Anx-B
DETAIL OF WORK DONE BY NLC / HIRED LABOUR
Re-Modelling and Up Gradation of ADA Nullah and Walton Road Pkg-I
SELF EXECUTION WORK
Bill | Activity | Amount Rs in Million
|  | Work Done |  |  |  | Vetted Workdone up to Date |  |  | 0 | 0
|  | Approx cost of own works | Work Done During the Month | Running Total up to Date | Running Total YTD | Vetted Workdone up to Date | Vetted Workdone Year to Date
A | ROAD WORKS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
1 | Earthwork and Allied Activities | 1.75 | 0 | 1.75 | 0 | 1.75 | 0 | 1.75 | 1.75 | 0 | -1.75
2 | Sub-Base & Base Course | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Asphalt Works | 1094.5992 | -2.431 | 1168.05 | -2.431 | 1069.122 | 0 | 1031.732 | 1031.732 | 37.39 | -1031.732 | 1029.301
4 | 1.Drainage, Erosion Works & Box Culverts (630mm HDPE Pipe with Chamber | 0 | 0 | 110.147 | 0 | 103.79 | 0 | 103.79 | 103.79 | 0 | -103.79
| ii.Utilities Crossing 4"6"8" |  | 0 | 9.786 | 0 | 7.34 | 0 | 7.34 | 7.34 | 0 | -7.34
| iii.Utilities Crossing 250" & 315" dia pipe |  | 0 | 2.77 | 0 | 2.77 | 0 | 2.77 | 2.77 | 0 | -2.77
5 | Ancillary Works - Kerber | 306.539 | 0 | 23.223 | 0 | 23.223 | 0 | 23.223 | 23.233 | 0 | -23.233
| Cobble Stone | [8 empty] | 0 | 0
6 | Sewerage Works (Rcc Pipe 72" & 66" | 200 | 0 | 179.618 | 0 | 171.784 |  | 171.784 |  | 0 | 0
B | CONDUIT WORKS | 0 | [7 empty] | 0 | 0
1 | Conduit Works 8' x 6' | 0 | [7 empty] | 0 | 0
2 | Conduit Works 10' x 6' | 0 | [7 empty] | 0 | 0
3 | Sump & Pump Disposal Station |  | 0 | [6 empty] | 0 | 0
i | Pump Motor & Mechinal | 204.341 | 0 | 204.341 | 0 | 164.341 | 0 | 164.341 | 164.341 | 0 | -164.341
| Providing & Installing M.S Blind Pipe Socketed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ii | Forceman HDPE Pipe 1200 mm & 900 | 247.5 | 0 | 249.472 | 0 | 128.185 | 0 | 128.185 | 128.185 | 0 | -128.185
iii | Paid against Provisioanl Exp (POL) Reoceverd from Contr (Shift To Other Income |  | 0 | 0 | 0 | 0 | 0 | 30.5 | 30.5 | -30.5 | -30.5
iv | Cement Concrete Plain incl placing ration 1.2.4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C | ELEVATED U-TURNS (1 Nos) NEAR QAINCHI CHOWK | 0 | 0 | [6 empty] | 0 | 0
1 | Civil Works | 77.5631 | [7 empty] | 0 | 0
D | ADA NULLAH | 0 | [7 empty] | 0 | 0
1 | Civil Works Bailing Water Pump | 649.8955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E | AT GRADE U-TURN (2 Nos) (NEAR KORA STOP & NEAR TAIMUR ASLAM CHOWK) | 0 | [7 empty] | 0 | 0
1 | Earthwork and Allied Activities | 0 | [7 empty] | 0 | 0
2 | Sub-Base & Base Course | 0 | [7 empty] | 0 | 0
3 | Asphalt Works | 17.2366 | [7 empty] | 0 | 0
4 | Drainage, Erosion Works & Box Culverts | 0 | [7 empty] | 0 | 0
F | ELECTRICAL WORKS | 0 | 0 | [6 empty] | 0 | 0
1 | Road Works | 326.6059 | 0 | 172.782 | 0 | 93.883 | 0 | 93.883 | 93.883 | 0 | -93.883
2 | Elevated U-Turn | 0 | [7 empty] | 0 | 0
3 | Underground Pedestarian | 0 | [7 empty] | 0 | 0
G | ARCHITECTURAL WORKS | 0 | [7 empty] | 0 | 0
1 | Elevated U-Turn | 0 | [7 empty] | 0 | 0
2 | Underground Pedestarian | 0 | [7 empty] | 0 | 0
H | UNDERGROUND PEDESTRIAN WAY (2 Nos.) | 0 | [7 empty] | 0 | 0
I | PEDESTRIAN BRIDGE (4 Nos.) | 0 | [7 empty] | 0 | 0
J | SHIFTING OF TUBEWELLS (PROVISIONAL SUM) | 130 | [7 empty] | 0 | 0
L | DIVERSION WORKS | 20.4581 | 0 | 19.915 | 0 | 19.096 | 0 | 19.096 | 19.096 | 0 | -19.096
G Total (Rs inMillion) |  | 3276.4884 | -2.431 | 2141.854 | -2.431 | 1785.284 | 0
Add PST 5% |  | 163.8244 | -0.12155 | 107.0927 | -0.12155 | 89.2642 | 0
Add PST 5% Anx C |  | 346.5038 | 1.907 | 348.6871 | 1.9071 | 321.4154 | 0
|  |  | 1.7855 | 455.7798 | 1.7855 | 410.6796 | 0
Total Work Done |  | 3786.8166 | -0.6455 | 2597.6338 | -0.6455 | 2195.9635 | 0
Previous month |  |  |  | 2144.285 |  | 1785.284
Diff |  |  |  | -2.431 | -2.431 | 0 | 0
9115.5958
|  |  |  | 45578% | 45578% |  | 455.7798
6.7
462.4798

## Anx-C
Anx "C"
[12 empty] | 2025-06-01 |  | 0
DETAIL OF WORK DONE BY SUB CONTRACTORS
Re-Modelling and Up Gradation of ADA Nullah and Walton Road Pkg-I
[14 empty] | -2.7427e-12 |  |  | 0
Ser | CA No. | Contractor | Activity | Amount Rs in Million | [12 empty] | 0
VWD
|  |  |  | NLC Cost | Sub Contr Cost |  | Saving | Work Done During the Month | Running Total Upto Date | Running Total YTD | Vetted Work Done up to Date | Vetted Work Done YTD
Petty Contract
1 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I/Petty-3 | (M/S Saddaqat Builders) Part A | Road Diversion Work | 16.709 | 14.784 | 100% | 11.52% | 0 | 16.8392 | 0 | 16.839 |  | 100% | 88.48% | 14.8992 |  | 15.4032 | 1.436
2 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I/Petty-4 | (M/S Saddaqat Builders) Part B | Road Diversion Work | 16.702 | 14.777 | 100% | 11.53% | 0 | 16.8441 | 0 | 16.844 |  | 100% | 88.47% | 14.9027 |  | 15.2361 | 1.608
3 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I/Petty-5 | (M/S Saddaqat Builders) Part C | Road Diversion Work | 16.7 | 14.775 | 100% | 11.53% | 0 | 13.4321 | 0 | 13.2 | 0 | 100% | 88.47% | 11.8838 |  | 11.7471 | 1.685
4 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I/Petty | (M/S Saddaqat Builders) Part D | Road Diversion Work | 16.7 | 14.775 |  | 11.53% | 0 | 10.252 | 0 | 10.252 | 0 | 100% | 88.47% | 9.0703
5 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I/Petty-6 | (M/S Saddaqat Builders) | 72 Pipe Sewrage Work | 12.14 | 10.421 |  | 14.16% | 0 | 8.048 | 0 | 8.048 |  | 100% | 85.84% | 6.9084 |  | 8.048 | 0
6 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I/Petty-11 | (M/S BA Construction & Co) | 66 Pipe Sewrage Work | 5.967 | 5.894 |  | 1.223% | 0 | 3.421 | 0 | 3.421 |  | 100% | 98.78% | 3.3791 |  | 3.421 | 0
7 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-1 | (M/S Zashpak Engineering Service) | Diversion Acillary Work | 5.008 | 4.355 | 100% | 13.04% | 0 | 4.049 | 0 | 4.049 |  | 100% | 86.96% | 3.521 |  | 4.049 | 0
8 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-2 | (M/S Choudary Son) | Diversion Work | 17.127 | 14.565 | 100% | 14.96% | 0 | 16.3795 | 0 | 16.334 |  | 100% | 85.04% | 13.9293 |  | 16.3335 | 0.046
9 | Petty-7,8,9,10 | (M/S Sapper & Co) | Disposal - 02 | 67.379 | 55.661 | 100% | 17.39% | 0 | 70.968 | 0 | 70.85 | 0 | 100% | 82.61% | 58.6258 |  | 65.3 | 5.668
10 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-2 | (M/S Sapper & Co) | Electric Work Part A&B | 18.535 | 5.038 |  | 72.82% | 0 | 28.899 | 0
11 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-12 | (M/S BA Construction & Co) | ADA Nullah Part-A | 16.4922 | 14.843 |  | 10% | 0 | 16.826 | 0 | 16.826 |  | 100% | 90% | 15.1434 |  | 16.826 | 0
12 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-13 | (M/S BA Construction & Co) | ADA Nullah Part-B | 16.6456 | 14.9811 |  | 10% | 0 | 15.362 | 0 | 15.362 |  | 100% | 90% | 13.8258 |  | 15.362 | 0
13 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-14 | (M/S Reckon Enterprises) | Sewerage & Conduit Work | 13.6807 | 10.9445 |  | 20% | 0 | 15.9465 | 0 | 13.575 | 0 | 100% | 80% | 12.7572 |  | 13.575 | 2.3715
14 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-15 | (M/S Reckon Enterprises) | Sewerage & Conduit Work | 13.6878 | 10.9502 |  | 20% | 0 | 17.694 | 0 | 17.694 |  | 100% | 80% | 14.1552 |  | 15 | 2.694
15 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-34 & 36 | M/S North Land | Sewerage Thrust Bore | 27.587 | 24.74 |  | 10.32% | 0 | 25.341 | 0 | 25.206 | 0 | 100% | 89.68% | 22.7258 | 18.01 | 18.01 | 7.331
16 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-26 | (M/S Reckon Enterprises) | Sewerage & Conduit Work | 16.104 | 12.884 |  | 20% | 0 | 15.944 | 0 | 15.944 | 0 | 100% | 80% | 12.756 |  | 14.966 | 0.978
17 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-27 | (M/S Reckon Enterprises) | Sewerage & Conduit Work | 16.064 | 12.852 |  | 20% | 0 | 14.797 | 0 | 14.797 | 0 | 100% | 80% | 11.8383 |  | 7.869 | 6.928
18 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-31 | M/S North Land | Sewerage Diplomatic Ecclave Link Road | 12.08 | 12.025 |  | 0.4553% | 0 | 15.365 | 0 | 15.365 | 0 | 100% | 99.54% | 15.295 |  | 12.298 | 3.067
19 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-29 | M/S Inzi | Sewerage Rider Sewer | 14.706 | 13.724 |  | 6.678% | 0 | 13.629 | 0 | 13.044 | 0 | 100% | 93.32% | 12.7189 |  | 9.965 | 3.664
20 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-28 | M/S Inzi | 72", 66" Dia Pipe Laying | 4.84 | 4.745 |  | 1.963% | 0 | 2.97 | 0 | 2.97 | 0 | 100% | 98.04% | 2.9117 |  | 2.458 | 0.512
21 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-x 7 CA #33,35,37,38,40,48,51 | M/S Land Lad | Sewerage Rider & Drainage | 61.136 | 59.932 |  | 1.969% | 0 | 148.321 | 0 | 126.746 | 0 | 100% | 98.03% | 145.4 |  | 63.37 | 84.951
22 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-30 | M/S Inzi | Sewerage Rider Sewer | 14.706 | 13.724 |  | 6.678% |  |  | 0 |  | 0 | 100% | 93.32% | 0 |  |  | 0
23 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-32 | M/S Inzi | Sewerage Rider Sewer | 14.706 | 13.724 |  | 6.678% |  |  | 0 |  | 0 | 100% | 93.32% | 0 |  |  | 0
24 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-24 | M/S BuildBest Builder | Pedestrain Bridge | 6.353 | 5.561 |  | 12.47% | 0 | 23.547 | 0 | 22.725 | 0 | 100% | 87.53% | 20.6115 |  | 6.117 | 17.43
25 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-39 | M/S Land Lad | Pedestrain Bridge | 6.353 | 5.561 |  | 12.47% | 0 | 13.24 | 0 | 13.24 | 0 | 100% | 87.53% | 11.5894 |  | 5.468 | 7.772
26 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty- | M/S Choudary Sons | De Sitting of Nullah Work Army Area | 16.437 | 14.793 |  | 10% | 0 | 19.721 | 0 | 17.339 | 0 | 100% | 90% | 17.7485 |  | 15.614 | 4.107
27 | 2 x CA Inprogress | M/S Youkon Builder & Developers | Operational Work of Disposal Work | 45.034 | 28.065 |  | 37.68% |  |  |  | 0 | 0 |  |  |  |  | 37.201
28 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-52 | M/S Teepu Engineering Services | Mechinal Disposal Work | 20.699 | 13.826 |  | 33.2% | 6.688 | 39.343 | 6.688 | 11.275 | 0 | 100% | 66.8% | 26.2794 |  | 0 | 39.343
29 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-54,55 | ALDO International | Ancilary Work | 23.162 | 14.268 |  | 38.4% | 0 | 29.283 | 0 | 6.866 | 0 | 100% | 61.6% | 18.0386
30 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-49 | M/S Tuba | Electric Work |  |  |  | 100% | 0 | 11.995 | 0 | 6.128 | 0 | 100% | 100% | 11.995
31 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-66 | The Land Lord Group | Thrust Bore Forceman | 19.614 | 14.907 |  | 24% | 0 | 21.989 | 0 | 13.92 | 0 | 100% | 76% | 16.712
32 | CA No.57,58,61,62,63 | RBC | Asphalt Work | 81.765 | 67.715 |  | 17.18% | 7.678 | 89.57 | 7.678 | 81.892 | 0 | 100% | 82.82% | 74.1788
| Total |  |  | 654.8193 | 545.8098 |  |  | 14.366 | 740.0154 | 14.366 | 610.751 | 0 |  |  | 613.8004 |  |  | 191.5914
[13 empty] | 100% | 100% | 0
2 | Sublet Contract | [10 empty] | 0 | 100% | 100% | 0
1 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I-02 | (M/S Saddaqat Builders) Sewerage | Sewrage Work | 483.187 | 424.505 | 100% | 12.14% | 0 | 149.885 | 0 | 147.309 | 0 | 100% | 87.86% | 131.6818 |  | 118.6 | 31.285
2 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I-03 | (M/S Yukon Builders & Developers) (Conduite & Disposal Satation) | Conduit Works & Disposal station-Sub pkg-4 Part A | 527.4945 | 443.0954 | 100% | 16% | 0 | 511.274 | 0 | 511.274 | 0 | 100% | 84% | 429.4702 |  | 486.393 | 24.881
3 | Inprogress | (M/S Yukon Builders & Developers) | Road works |  |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 0 |  | 0 | 0
4 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I-01 | M/s STC | Conduit Works & Rider Sewerage Work | 336.926 | 283.0178 |  | 16% | 0 | 320.156 | 0 | 320.156 | 0 | 100% | 84% | 268.931 |  | 313.229 | 6.927
5 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I-04 | M/s EDDCO | Conduit Work | 427.5587 | 359.1493 |  | 16% | 0 | 176.25 | 0 | 176.035 | 0 | 100% | 84% | 148.05 |  | 176.035 | 0.215
6 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I- | M/s EDDCO | Fly-over | 1116.3099 | 993.5158 |  | 11% | 0 | 1586.158 | 0 | 1560.52 | 0 | 100% | 89% | 1411.6806 |  | 1485.21 | 100.948
7 |  | M/S Yukon Builders & Developers | Disposal - 01 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 100% | 100% | 0 |  | 0 | 0
8 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I-05 | (M/S North Land | Route 47 / Garrasion | 119.6996 | 107.7296 |  | 10% | 0 | 168.239 | 0 | 161.08 | 0 | 100% | 90% | 151.4151 |  | 186.51 | -18.271
9 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I-06 | (M/S Saddaqat Builders) | ADA Nullah | 277.65 | 249.885 |  | 10% | 0 | 251.5019 | 0 | 234.263 | 0 | 100% | 90% | 226.3517 |  | 217.465 | 34.0369
10 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I-09 | M/s STC | ADA Nullah | 319.9299 | 287.9369 |  | 10% | 0 | 396.8025 | 0 | 396.049 | 0 | 100% | 90% | 357.1223 |  | 388.657 | 8.1455
11 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I-07 | M/s EDDCO | ADA Nullah | 510.0645 | 459.0581 |  | 10% | 0 | 625.852 | 0 | 594.412 | 0 | 100% | 90% | 563.2668 | #REF! | 619.796 | 6.056
12 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I-11 | M/S Yukon Builders & Developers | ADA Nullah | 309.9352 | 278.9417 |  | 10% | 0 | 283.237 | 0 | 279.29 | 0 | 100% | 90% | 254.9133 |  | 265.131 | 18.106
13 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I-19 | (M/S North Land | ADA Nullah | 510.0645 | 459.0581 |  | 10% | 1.798 | 514.928 | 1.798 | 456.38 | 0 | 100% | 90% | 463.4352 |  | 391.56 | 123.368
14 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I-10 | M/S Yukon Builders & Developers | Road works | 342.397 | 287.614 |  | 16% | 0 | 193.953 | 0 | 160.904 | 0 | 100% | 84% | 162.9208 |  | 95.072 | 98.881
15 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I- | (M/S North Land | Road works | 119.699 | 107.729 |  | 10% | 0 | 115.779 | 0 | 105.15 | 0 | 100% | 90% | 104.201 |  | 113.131 | 2.648
16 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I-20 | (M/S INZI | Road works | 166.82 | 140.13 |  | 16% | 0 | 80.1 | 0 | 71.71 | 0 | 100% | 84% | 67.2846
17 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I-14 | (M/S Saddaqat Builders) | Road works | 510.0645 | 428.4546 |  | 16% | 0 | 173.74 | 0 | 165.89 | 0 | 100% | 84% | 145.9417 |  | 104.608 | 69.132
18 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I-08 | M/s STC | Road works | 210.714 | 177 |  | 16% | 0 | 138.875 | 0 | 121.035 | 0 | 100% | 84% | 116.6552 |  | 81.62 | 57.255
19 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I-12 | M/s EDDCO | Road works | 200.839 | 168.705 |  | 16% | 0 | 111.647 | 0 | 97.25 | 0 | 100% | 84% | 93.7836 |  | 89.507 | 22.14
20 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty- 44&45 | M/S Yukon Builders & Developers | Machinacal Work | 35.695 | 27.842 |  | 22% | 0 | 22.589 | 0 | 15.813 | 0 | 100% | 78% | 17.6194 |  | 26.1 | -3.511
21 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty- | M/S Yukon Builders & Developers | Running & Operational Disp 1 | 8.957 | 6.718 |  | 25% | 0 | 13.436 | 0 | 11.943 | 0 | 100% | 75% | 10.0774
22 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-16 | M/S Best Builder | Pedestrain Bridge | 201.621 | 161.87 |  | 19.72% | 0.989 | 132.258 | 0.989 | 90.423 | 0 | 100% | 80.28% | 106.1824 |  | 25.015 | 107.243
23 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-17 | M/S BA Construction | Road works | 75.913 | 63.77 |  | 16% | 0 | 41.423 | 0 | 37.348 | 0 | 100% | 84% | 34.797 |  | 22.711 | 18.712
24 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-15 | M/S Shah Developers | Pedestrain Bridge | 104.7 | 83.76 |  | 20% | 0 | 101.152 | 0 | 50.52 | 0 | 100% | 80% | 80.9216 |  | 28.063 | 73.089
25 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I- 22 | (M/S Land Lord | Mechinal Work |  |  |  | 15% | 20.988 | 70.258 | 20.988 | 35.78 | 0 | 100% | 85% | 59.7193
26 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I- 68 | Ne M Shafi | Electrical & Machinacal Work | 13.836 | 12.037 |  | 13% | 0 | 13.921 | 0 | 13.836 | 0 | 100% | 87% | 12.1109
27 | In process |  | Cobble Stone |  |  |  | 100% | 0 | 40.312 | 0 | 3.186 | 0 | 100% | 85% | 34.2652
Total (Rs in Million) |  |  |  | 6930.0755 | 6014.5225 |  |  | 38.141 | 6973.7418 | 38.141 | 6428.307 | 0 |  |  | 6066.5985 |  | 5234.413 | 972.8778
[9 empty] | 6930.3508 |  | 6428.307 |  |  |  | 5801
[9 empty] | 43.391 | 38.141 | 0 | 0 |  |  | 265.5985
6059.9139
[9 empty] | 2.7427e-12 | 0

## Anx-D
Anx "D"
DETAIL OF EXPENDITURES
Re-Modelling and Up Gradation of ADA Nullah and Walton Road Pkg-I
Ser | Head of A/c | Expenditures (Rs in Million)
|  | During the Month | Upto Date | Year to Date
Work Expenditures
1 | Stores Consumed (Material+Diesel)
| Misc Site Expense | 0 | 0.264 | 0
| Bore at Site | 0 | 2.7 | 0
| Material Consumption NLC | -46.712 | 1610.1822 | -46.712
| Elec connection-Instl (Wapda & Cont) charges | 0 | 7.7836 | 0
2 | Sub Contr Cost |  |  | 0
| Net Payments | 27.1621 | 5297.3861 | 27.1623
| Retention Money | 1.5539 | 302.5899 | 1.5539
| Income Tax | 2.3619 | 459.9379 | 2.3619 |  | -0.0003538
| Contractor Escalation (Detail Att | 0 | 95.1282 | 0
3 | Plants and Machinery |  |  | 0
| Hiring Charges | 0 | 37.462 | 0
| Repair/ Maint | 0.35 | 9.768 | 0.35
| Repair/ Maint (Batching Plant) Insl of BP |  | 3.822 | 0
| Disposal Pump Repair & Maint (Aproxx | 0 | 0 | 0
| POL NLC / Hired Plant & Machinery | 2.34 | 87.123 | 2.34
| POL Hiring veh | 0 | 0 | 0
4 | Direct Labour / Salary |  |  | 0
| Wages/ Muster Roll / Labour Muster Roll | 0 | 0 | 0
| Gen Labor | 1.907 | 39.3459 | 1.907
| Petty General Labour (Salary) | 0 | 6.404 | 0
5 | Any Other |  |  | 0
| Depreciation of Operating Assets as per ERP | 17.6 | 20.536 | 17.6
| Toll Tax Tokken | 1.124 | 1.124 | 1.124
| Office/site Establishment/ dev Exp | 0 | 0 | 0
| Proj Maint Cost Fund | 0.37495 | 97.0579 | 0.37496
| House Rent Charges | 0.21 | 4.873 | 0.21
| Lab Test Fee | 0 | 0.4835 | 0
| Provision for accrued exp |  | 0 | 0
| Cilent Facility - Veh | 0 | 33.476 | 0
| Tn Charges / Loading/ Unloading | 0 | 0 | 0
| Only Deducted income Tax | 0 | 0 | 0
| Cutting of Tree Exp | 0 | 0 | 0
462.1804 | EPC PST 5% | 6.401 | 6.4007 | 6.401
461.9184 | PST (5% ) | 1.7855 | 455.7798 | 1.7855
0.26207 | Total Work Expenditure | 16.4584 | 8579.6277 | 16.4586
1 | Pay & Allowances
| Gen labour |  |  | 0
| Civ Personals/benefits/Salaries/welfare | 0.04 | 2.2107 | 0.04
| NLC Employees Paybill | 8.5 | 155.42 | 8.5
2 | Other Expenditures |  |  | 0
| POL ( bikes petrol ) | 0 | 1.407 | 0
| POL ( Diesel P&M ) | 0 | 0.503 | 0
| Utilities | 0.75 | 11.495 | 0.75
| TADA | 0 | 0.182 | 0
| Gas - LPG for Office Mess | 0 | 0.107 | 0
| Repair & Maint (Vehicles) | 0 | 0.435 | 0
| Repair & Maint (Furniture ) | 0 | 0.0884 | 0
| Repair & Maint (Office Equipment ) | 0 | 0.934 | 0
| Repair & Maint (Cptr, Electric,Building and Genral) / Office Contingency | 0 | 0.76 | 0
| Weight Charges | 0 | 0.152 | 0
| Medical Charges | 0 | 0.067 | 0 |  |  | 0.151
| Entertainment Exp | 0.261 | 3.795 | 0.261
| Printing & Stationery/Photocopies | 0 | 1.965 | 0
| Freight Charges | 0 | 1.847 | 0
| Office Contigencies | 0.247 | 5.2747 | 0.247
| Local Purchase | 0.72 | 11.1531 | 0.72
| Security Exp | 0 | 0.365 | 0
| Hiring Charges / Crane | 0 | 0.254 | 0
| Welfare/ Donation/ Charity/ Cash Award | 0 | 0 | 0
| Site Estab Rs.21.50 M) | 0 | 21.5 | 0 | 60.8459
3 | HQ Expenditures | 0 | 0 | 0
| HQ NLC Expenses | 0 | 0 | 0
| HQ Engrs NLC Expenses | 0 | 0 | 0
| Total Overhead Expenditure | 10.518 | 219.9149 | 10.518
| Grand Total Expenditure (Work + Overhead) | 26.9764 | 8799.5426 | 26.9766
Note : |  |  | 8771.9847 | 4341.728
|  |  | 27.5579 | -4314.7514

## Escalation Cost
Detail of Escalation Cost
Ser | Contractor | Amount
1 | EDDCO | 49104546
2 | STC | 15354401
3 | Yukon | 13133827
4 | Northland | 11201847
5 | Saddaqat | 6333553
Total |  | 95128174

## Anx-E
2025-06-01
Re-Modelling and Up Gradation of ADA Nullah and Walton Road Pkg-I
DETAIL OF PAYMENTS TO SUB CONTRACTORS
Ser | CA No | Contractor | Activity | NLC CA Amount | Sub Contr CA Amount |  | Month |  |  |  |  | UTD |  |  |  |  | YTD
[6 empty] | Cost % | Sub Contr's Vetted Work Done | Retention Money | Income Tax | Material Recovery | Net Payment Due | Sub Contr's Vetted Work Done | Retention Money | Income Tax | Material Recovery | Net Payment Due | Sub Contr's Vetted Work Done | Retention Money | Income Tax | Material Recovery | Net Payment Due
1 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I/Petty-3 | (M/S Saddaqat Builders) Part A | Road Diversion Work | 16.709 | 14.784 | 88.48% | 0 | 0 | 0 | 0 | 0 | 14.8992 | 0.74496 | 1.1323 | 0 | 13.0219 | 0 | 0 | 0 | 0 | 0
2 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I/Petty-4 | (M/S Saddaqat Builders) Part B | Road Diversion Work | 16.702 | 14.777 | 88.47% | 0 | 0 | 0 | 0 | 0 | 14.9027 | 0.74514 | 1.1326 | 0 | 13.025 | 0 | 0 | 0 | 0 | 0
3 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I/Petty-5 | (M/S Saddaqat Builders) Part C | Road Diversion Work | 16.7 | 14.775 | 88.47% | 0 | 0 | 0 | 0 | 0 | 11.8838 | 0.59419 | 0.90317 | 0 | 10.3865 | 0 | 0 | 0 | 0 | 0
4 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I/Petty | (M/S Saddaqat Builders) Part D | Road Diversion Work | 16.7 | 14.775 | 88.47% | 0 | 0 | 0 | 0 | 0 | 9.0703 | 0.45351 | 0.68934 | 0 | 7.9274 | 0 | 0 | 0 | 0 | 0
5 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I/Petty-6 | (M/S Saddaqat Builders) | 72 Pipe Sewrage Work | 12.14 | 10.421 | 85.84% | 0 | 0 | 0 | 0 | 0 | 6.9084 | 0.34542 | 0.52504 | 0 | 6.038 | 0 | 0 | 0 | 0 | 0
6 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I/Petty-11 | (M/S Saddaqat Builders) | 66 Pipe Sewrage Work | 5.967 | 5.894 | 98.78% | 0 | 0 | 0 | 0 | 0 | 3.3791 | 0.16896 | 0.25682 | 0 | 2.9534 | 0 | 0 | 0 | 0 | 0
7 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-1 | (M/S Zashpak Engineering Service) | Diversion Acillary Work | 5.008 | 4.355 | 86.96% | 0 | 0 | 0 | 0 | 0 | 3.521 | 0.17605 | 0.2676 | 0 | 3.0774 | 0 | 0 | 0 | 0 | 0
8 | C/2023/PO468/CBD ADA Nullah/Pkg-1/-2 | (M/S Choudary Son) | Diversion Work | 17.127 | 14.565 | 85.04% | 0 | 0 | 0 | 0 | 0 | 13.9293 | 0.69647 | 1.0586 | 0 | 12.1742 | 0 | 0 | 0 | 0 | 0
9 | Petty-7,8,9,10 | (M/S Sapper & Co) | Disposal - 02 | 67.379 | 55.661 | 82.61% | 0 | 0 | 0 | 0 | 0 | 58.6258 | 2.9313 | 4.4556 | 0 | 51.2389 | 0 | 0 | 0 | 0 | 0
10 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-2 | (M/S Sapper & Co) | Electric Work Part A&B | 18.535 | 5.038 | 27.18% | 0 | 0 | 0 | 0 | 0 | 7.855 | 0.39275 | 0.59698 | 0 | 6.8653 | 0 | 0 | 0 | 0 | 0
10 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-12 | (M/S BA Construction & Co) | ADA Nullah Part-A | 16.4922 | 14.843 | 90% | 0 | 0 | 0 | 0 | 0 | 15.1434 | 0.75717 | 1.1509 | 0 | 13.2353 | 0 | 0 | 0 | 0 | 0
11 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-13 | (M/S BA Construction & Co) | ADA Nullah Part-B | 16.6456 | 14.9811 | 90% | 0 | 0 | 0 | 0 | 0 | 13.8258 | 0.69129 | 1.0508 | 0 | 12.0837 | 0 | 0 | 0 | 0 | 0
12 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-14 | (M/S Reckon Enterprises) | Sewerage & Conduit Work | 13.6807 | 10.9445 | 80% | 0 | 0 | 0 | 0 | 0 | 12.7572 | 0.63786 | 0.96954 | 0 | 11.1498 | 0 | 0 | 0 | 0 | 0
13 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-15 | (M/S Reckon Enterprises) | Sewerage & Conduit Work | 13.6878 | 10.9502 | 80% | 0 | 0 | 0 | 0 | 0 | 14.1552 | 0.70776 | 1.0758 | 0 | 12.3716 | 0 | 0 | 0 | 0 | 0
14 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-34 & 36 | M/S North Land | Sewerage Thrust Bore | 27.587 | 24.74 | 89.68% | 0 | 0 | 0 | 0 | 0 | 22.7258 | 1.1363 | 1.7272 | 0 | 19.8623 | 0 | 0 | 0 | 0 | 0
15 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-26 | (M/S Reckon Enterprises) | Sewerage & Conduit Work | 16.104 | 12.884 | 80% | 0 | 0 | 0 | 0 | 0 | 12.756 | 0.6378 | 0.96946 | 0 | 11.1487 | 0 | 0 | 0 | 0 | 0
16 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-27 | (M/S Reckon Enterprises) | Sewerage & Conduit Work | 16.064 | 12.852 | 80% | 0 | 0 | 0 | 0 | 0 | 11.8383 | 0.59192 | 0.89971 | 0 | 10.3467 | 0 | 0 | 0 | 0 | 0
17 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-31 | M/S North Land | Sewerage Diplomatic Ecclave Link Road | 12.08 | 12.025 | 99.54% | 0 | 0 | 0 | 0 | 0 | 15.295 | 0.76475 | 1.1624 | 0 | 13.3679 | 0 | 0 | 0 | 0 | 0
18 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-29 | M/S Inzi | Sewerage Rider Sewer | 14.706 | 13.724 | 93.32% | 0 | 0 | 0 | 0 | 0 | 12.7189 | 0.63595 | 0.96664 | 0 | 11.1163 | 0 | 0 | 0 | 0 | 0
19 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-28 | M/S Inzi | 72", 66" Dia Pipe Laying | 4.84 | 4.745 | 98.04% | 0 | 0 | 0 | 0 | 0 | 2.9117 | 0.14559 | 0.22129 | 0 | 2.5448 | 0 | 0 | 0 | 0 | 0
20 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-x 7 CA #33,35,37,38,40,48,51 | M/S Land Lad | Sewerage Rider & Drainage | 61.136 | 59.932 | 98.03% | 0 | 0 | 0 | 0 | 0 | 145.4 | 7.27 | 11.0504 | 0 | 127.0796 | 0 | 0 | 0 | 0 | 0
21 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-30 | M/S Inzi | Sewerage Rider Sewer | 14.706 | 13.724 | 93.32% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-32 | M/S Inzi | Sewerage Rider Sewer | 14.706 | 13.724 | 93.32% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-24 | M/S BuildBest Builder | Pedestrain Bridge | 6.353 | 5.561 | 87.53% | 0 | 0 | 0 | 0 | 0 | 20.6115 | 1.0306 | 1.5665 | 0 | 18.0145 | 0 | 0 | 0 | 0 | 0
24 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-39 | M/S Land Lad | Pedestrain Bridge | 6.353 | 5.561 | 87.53% | 0 | 0 | 0 | 0 | 0 | 11.5894 | 0.57947 | 0.8808 | 0 | 10.1292 | 0 | 0 | 0 | 0 | 0
25 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty- | M/S Choudary Sons | De Sitting of Nullah Work Army Area | 16.437 | 14.793 | 90% | 0 | 0 | 0 | 0 | 0 | 17.7485 | 0.88743 | 1.3489 | 0 | 15.5122 | 0 | 0 | 0 | 0 | 0
26 | 2 x CA Inprogress | M/S Youkon Builder & Developers | Operational Work of Disposal Work | 45.034 | 28.065 | 62.32% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-52 | M/S Teepu Engineering Services | Mechinal Disposal Work | 20.699 | 13.826 | 66.8% | 4.4673 | 0.22336 | 0.33951 | 0 | 3.9044 | 26.2794 | 1.314 | 1.9972 | 0 | 22.9682 | 4.4673 | 0.22336 | 0.33951 | 0 | 3.9044
28 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-54,55 | ALDO International | Ancilary Work | 23.162 | 14.268 | 61.6% | 0 | 0 | 0 | 0 | 0 | 18.0386 | 0.90193 | 1.3709 | 0 | 15.7657 | 0 | 0 | 0 | 0 | 0
29 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-49 | M/S Tuba | Electric Work | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 11.995 | 0.59975 | 0.91162 | 0 | 10.4836 | 0 | 0 | 0 | 0 | 0
30 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-66 | The Land Lord Group | Thrust Bore Forceman | 19.614 | 14.907 | 76% | 0 | 0 | 0 | 0 | 0 | 16.712 | 0.8356 | 1.2701 | 0 | 14.6063 | 0 | 0 | 0 | 0 | 0
31 | CA No.57,58,61,62,63 | RBC | Asphalt Work | 81.765 | 67.715 | 82.82% | 6.3587 | 0.31793 | 0.48326 | 0 | 5.5575 | 74.1788 | 3.7089 | 5.6376 | 0 | 64.8323 | 6.3587 | 0.31793 | 0.48326 | 0 | 5.5575
| Total |  |  | 654.8193 | 545.8098 | 100% | 10.8259 | 0.5413 | 0.82277 | 0 | 9.4619 | 621.6554 | 31.0828 | 47.2458 | 0 | 543.3268 | 10.8259 | 0.5413 | 0.82277 | 0 | 9.4619
| Sublet Contract |  |  | 0 | 0 |  | 0 | 0 | 0 | 0
1 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I-02 | (M/S Saddaqat Builders) Sewerage | Sewrage Work | 483.187 | 424.505 | 87.86% | 0 | 0 | 0 | 0 | 0 | 131.6818 | 6.5841 | 10.0078 | 0 | 115.0899 | 0 | 0 | 0 | 0 | 0
2 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I-03 | (M/S Yukon Builders & Developers) (Conduite & Disposal Satation) | Conduit Works 10' x 6' | 527.4945 | 443.0954 | 84% | 0 | 0 | 0 | 0 | 0 | 429.4702 | 21.4735 | 32.6397 | 0 | 375.3569 | 0 | 0 | 0 | 0 | 0
3 |  | (M/S Yukon Builders & Developers) | Road works | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I-01 | M/s STC | Conduit Works & Rider Sewerage Work | 336.926 | 283.0178 | 84% | 0 | 0 | 0 | 0 | 0 | 268.931 | 13.4466 | 20.4388 | 0 | 235.0457 | 0 | 0 | 0 | 0 | 0
5 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I-04 | M/s EDDCO | Conduit Work | 427.5587 | 359.1493 | 84% | 0 | 0 | 0 | 0 | 0 | 148.05 | 7.4025 | 11.2518 | 0 | 129.3957 | 0 | 0 | 0 | 0 | 0
6 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I- | M/s EDDCO | Fly-over | 1116.3099 | 993.5158 | 89% | 0 | 0 | 0 | 0 | 0 | 1411.6806 | 70.584 | 107.2877 | 0 | 1233.8089 | 0 | 0 | 0 | 0 | 0
7 | 0 | (M/S Yukon Builders & Developers) | Disposal - 01 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I-05 | (M/S North Land | Route 47 / Garrasion | 119.6996 | 107.7296 | 90% | 0 | 0 | 0 | 0 | 0 | 151.4151 | 7.5708 | 11.5075 | 0 | 132.3368 | 0 | 0 | 0 | 0 | 0
9 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I-06 | (M/S Saddaqat Builders) | ADA Nullah | 277.65 | 249.885 | 90% | 0 | 0 | 0 | 0 | 0 | 226.3517 | 11.3176 | 17.2027 | 0 | 197.8314 | 0 | 0 | 0 | 0 | 0
10 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I-09 | M/s STC | ADA Nullah | 319.9299 | 287.9369 | 90% | 0 | 0 | 0 | 0 | 0 | 357.1223 | 17.8561 | 27.1413 | 0 | 312.1249 | 0 | 0 | 0 | 0 | 0
11 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I-07 | M/s EDDCO | ADA Nullah | 510.0645 | 459.0581 | 90% | 0 | 0 | 0 | 0 | 0 | 563.2668 | 28.1633 | 42.8083 | 0 | 492.2952 | 0 | 0 | 0 | 0 | 0
12 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I-11 | (M/S Yukon Builders & Developers) | ADA Nullah | 309.9352 | 278.9417 | 90% | 0 | 0 | 0 | 0 | 0 | 254.9133 | 12.7457 | 19.3734 | 0 | 222.7942 | 0 | 0 | 0 | 0 | 0
13 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I-19 | (M/S North Land | ADA Nullah | 510.0645 | 459.0581 | 90% | 1.6182 | 0.08091 | 0.12298 | 0 | 1.4143 | 463.4352 | 23.1718 | 35.2211 | 0 | 405.0424 | 1.6182 | 0.08091 | 0.12298 | 0 | 1.4143
14 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I-10 | M/S Yukon Builders & Developers | Road works | 342.397 | 287.614 | 84% | 0 | 0 | 0 | 0 | 0 | 162.9208 | 8.146 | 12.382 | 0 | 142.3928 | 0 | 0 | 0 | 0 | 0
15 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I- | (M/S North Land | Road works | 119.699 | 107.729 | 90% | 0 | 0 | 0 | 0 | 0 | 104.201 | 5.2101 | 7.9193 | 0 | 91.0717 | 0 | 0 | 0 | 0 | 0
| C/2023/P0468/CBD-ADA-Nallah/Pkg-I-20 | (M/S INZI | Road works | 166.82 | 140.13 | 84% | 0 | 0 | 0 | 0 | 0 | 67.2846 | 3.3642 | 5.1136 | 0 | 58.8067 | 0 | 0 | 0 | 0 | 0
16 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I-14 | (M/S Saddaqat Builders) | Road works | 510.0645 | 428.4546 | 84% | 0 | 0 | 0 | 0 | 0 | 145.9417 | 7.2971 | 11.0916 | 0 | 127.5531 | 0 | 0 | 0 | 0 | 0
17 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I-08 | M/s STC | Road works | 210.714 | 177 | 84% | 0 | 0 | 0 | 0 | 0 | 116.6552 | 5.8328 | 8.8658 | 0 | 101.9566 | 0 | 0 | 0 | 0 | 0
18 | C/2023/P0468/CBD-ADA-Nallah/Pkg-I-12 | M/s EDDCO | Road works | 200.839 | 168.705 | 84% | 0 | 0 | 0 | 0 | 0 | 93.7836 | 4.6892 | 7.1276 | 0 | 81.9669 | 0 | 0 | 0 | 0 | 0
19 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty- 44&45 | M/S Yukon Builders & Developers | Machinacal Work | 35.695 | 27.842 | 78% | 0 | 0 | 0 | 0 | 0 | 17.6194 | 0.88097 | 1.3391 | 0 | 15.3993 | 0 | 0 | 0 | 0 | 0
20 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-16 | M/S Best Builder | Pedestrain Bridge | 201.621 | 161.87 | 80.28% | 0.79401 | 0.039701 | 0.060345 | 0 | 0.69397 | 106.1824 | 5.3091 | 8.0699 | 0 | 92.8034 | 0.79401 | 0.039701 | 0.060345 | 0 | 0.69397
21 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-17 | M/S BA Construction | Road works | 75.913 | 63.77 | 84% | 0 | 0 | 0 | 0 | 0 | 34.797 | 1.7399 | 2.6446 | 0 | 30.4126 | 0 | 0 | 0 | 0 | 0
22 | C/2023/PO468/CBD ADA Nullah/Pkg-1/petty-15 | M/S Shah Developers | Pedestrain Bridge | 104.7 | 83.76 | 80% | 0 | 0 | 0 | 0 | 0 | 80.9216 | 4.0461 | 6.15 | 0 | 70.7255 | 0 | 0 | 0 | 0 | 0
23 | CA in Progress | (M/S Land Lord | Mechinal Work | 0 | 0 | 85% | 17.8398 | 0.89199 | 1.3558 | 0 | 15.592 | 55.2571 | 2.3571 | 3.584 | 0 | 49.316 | 17.84 | 0.892 | 1.3558 | 0 | 15.5922
24 | CA in Progress | Ne M Shafi | Electrical & Machinacal Work | 13.836 | 12.037 | 87% | 0 | 0 | 0 | 0 | 0 | 12.1109 | 0.60555 | 0.92043 | 0 | 10.585 | 0 | 0 | 0 | 0 | 0
| CA in Progress | 0 | Cobble Stone | 0 | 0 | 85% | 0 | 0 | 0 | 0 | 0 | 34.2652 | 1.7133 | 2.6042 | 0 | 29.9478 | 0 | 0 | 0 | 0 | 0
Total Cost (Rs in Million) |  |  |  | 7598.1531 | 5826.8555 |  | 31.078 | 1.5539 | 2.3619 | 0 | 27.1621 | 6059.9139 | 302.5899 | 459.9379 | 0 | 5297.3861 | 31.0782 | 1.5539 | 2.3619 | 0 | 27.1623
[12 empty] | 6028.8358 | 301.036 | 457.5758 | 0 | 5270.2239
[9 empty] | 23.693 |  |  | 31.0782 | 1.5539 | 2.3621 | 0 | 27.1621 | 31.0782 | 1.5539 | 2.3619 | 0 | 27.1623
Ser | CA No | Contractor | Activity | NLC CA Amount | Sub Contr CA Amount |  | Month |  |  |  |  | UTD |  |  |  |  | YTD
[6 empty] | Cost % | Sub Contr's Vetted Work Done | Retention Money | Income Tax | Material Recovery | Net Payment Due | Sub Contr's Vetted Work Done | Retention Money | Income Tax | Material Recovery | Net Payment Due | Sub Contr's Vetted Work Done | Retention Money | Income Tax | Material Recovery | Net Payment Due
37.4955
40.312
6.0468

## Anx-F
Name of Contractor | Work Done | Secure Adv | Total | Recovery |  |  |  |  | NetPayable Before Tax | I Tax | NetPayable After Tax | Paid Amount | Balance
|  |  |  | Material | RM 5% | Performance Guarantee | Other | Total
STC | 21360698 |  | 21360698 | 8109898 | 1068034.9 |  | 0 | 9177932.9 | 12182765.1 | 913707 | 11269058 | 11269058 | 0
STC | 32399413 |  | 32399413 | 9455014 | 1619970.65 |  | 8083120 | 19158104.65 | 13241308.35 | 993098 | 12248210 | 12248210 | 0
STC | 62576602 |  | 62576602 | 29571259 | 3128830.1 |  | 23776931 | 56477020.1 | 6099581.9 | 457469 | 5642113 | 5642113 | 0
STC | 62389264 |  | 62389264 | 22370045 | 3119463.2 |  | 14950149 | 40439657.2 | 21949606.8 | 1646221 | 20303386 | 20303386 | 0
STC | 18420521 |  | 18420521 |  | 921026.05 |  |  | 921026.05 | 17499494.95 | 1312462 | 16187033 | 16187033 | 0
STC | 7894509 |  | 7894509 | - | 394725.45 |  |  | 394725.45 | 7499783.55 | 562484 | 6937300 | 6937300 | 0
STC | 37340472 |  | 37340472 | 16150462 | 1867023.6 |  | - | 18017485.6 | 19322986.4 | 1449224 | 17873762 | 17873762 | 0
STC | 16003059 |  | 16003059 | - | 800152.95 | 14150895 | - | 14951047.95 | 1052011.05 | 78901 | 973110 | 973110 | 0
STC | 2684680 |  | 2684680 |  | 134234 |  | 2010000 | 2144234 | 540446 | 40533 | 499913 | 499913 | 0
STC | 1150578 |  | 1150578 |  | 57528.9 |  |  | 57528.9 | 1093049.1 | 81979 | 1011070 | 1011070 | 0
STC | 625036 |  | 625036 |  | 31251.8 |  |  | 31251.8 | 593784.2 | 44534 | 549250 | 549250 | 0
STC | 267872.72 |  | 267872.72 |  | 13393.636 |  |  | 13393.636 | 254479.084 | 19086 | 235393 | 235393 | 0
STC | 2892367 |  | 2892367 |  | 144618.35 |  | 2703450 | 2848068.35 | 44298.65 | 3322 | 40977 | 40977 | 0
STC | 1239586 |  | 1239586 |  | 61979.3 |  | 1153800 | 1215779.3 | 23806.7 | 1786 | 22021 | 22021 | 0
STC | 1073098 |  | 1073098 |  | 53654.9 | -14150895 | 984900 | -13112340.1 | 14185438.1 | 1063908 | 13121530 | 13121530 | 0
STC | 459900 |  | 459900 |  | 22995 |  | 427485 | 450480 | 9420 | 707 | 8713 |  | 8713
| 268777655.72 | 0 | 268777655.72 | 85656678 | 13438882.786 | 0 | 54089835 | 153185395.786 | 115592259.934 | 8669421 | 106922839 | 106914126 | 8713
STC | 24111717 |  | 24111717 | 6047550 | 1205585.85 |  |  | 7253135.85 | 16858581.15 | 1264394 | 15594187 | 15594187 | 0
STC | 10333593 |  | 10333593 | - | 516679.65 |  |  | 516679.65 | 9816913.35 | 736269 | 9080644 | 9080644 | 0
STC | 196942328 |  | 196942328 | 76289775 | 9847116.4 |  | 43576300 | 129713191.4 | 67229136.6 | 5042185 | 62186952 | 62186952 | 0
STC | 84403855 |  | 84403855 | 23081182 | 4220192.75 | 14396847 | 40508862 | 82207083.75 | 2196771.25 | 164758 | 2032013 | 2032013 | 0
STC | 11843036 |  | 11843036 | 5451996 | 592151.8 |  | 5230100 | 11274247.8 | 568788.2 | 42659 | 526129 | 526129 | 0
STC | 5075586 |  | 5075586 |  | 253779.3 |  | 1015385 | 1269164.3 | 3806421.7 | 285482 | 3520940 | 3520940 | 0
STC | 2934564 |  | 2934564 |  | 146728.2 |  | 0 | 146728.2 | 2787835.8 | 209088 | 2578748 | 2578748 | 0
STC | 1257670 |  | 1257670 |  | 62883.5 |  | 1005000 | 1067883.5 | 189786.5 | 14234 | 175553 | 175553 | 0
STC | 10721942 |  | 10721942 | 4456444 | 536097.1 | -14396847 | 5714300 | -3690005.9 | 14411947.9 | 1080896 | 13331052 | 13331052 | 0
STC | 4595114 |  | 4595114 | 4259150 | 229755.7 |  | 0 | 4488905.7 | 106208.3 | 7966 | 98242 | 0 | 98242
STC | 352219405 | 0 | 352219405 | 119586097 | 17610970.25 | 0 | 97049947 | 234247014.25 | 117972390.75 | 8847931 | 109124460 | 109026218 | 98242
STC | 19211500 |  | 19211500 | 11454539 | 960575 | 5000000 | 1139909 | 18555023 | 656477 | 49236 | 607241 | 607241 | 0
STC | 8233500 |  | 8233500 |  | 411675 |  | 3618000 | 4029675 | 4203825 | 315287 | 3888538 | 3888538 | 0
STC | 18377512 |  | 18377512 | 10003777 | 918875.6 |  | 167018 | 11089670.6 | 7287841.4 | 546588 | 6741253 | 6741253 | 0
STC | 7876077 |  | 7876077 |  | 393803.85 |  | 7100765 | 7494568.85 | 381508.15 | 28613 | 352895 | 352895 | 0
STC | 11138976 |  | 11138976 |  | 556948.8 |  | 10512300 | 11069248.8 | 69727.2 | 5230 | 64497 | 64497 | 0
STC | 5388646 |  | 5388646 |  | 238692.35 |  | 0 | 238692.35 | 5149953.65 | 386247 | 4763707 | 4763707 | 0
STC | 4825145 |  | 4825145 |  | 241257.25 |  |  | 241257.25 | 4583887.75 | 343792 | 4240096 | 4240096 | 0
STC | 12965842 |  | 12965842 | 12107529 | 648292.1 |  | 0 | 12755821.1 | 210020.9 | 15752 | 194269 | 194269 | 0
STC | 88017198 | 0 | 88017198 | 33565845 | 4370119.95 | 5000000 | 22537992 | 65473956.95 | 22543241.05 | 1690745 | 20852496 | 20852496 | 0
Reckon | 10500000 |  | 10500000 |  | 525000 |  |  | 525000 | 9975000 | 798000 | 9177000 | 9177000 | 0
Reckon | 4500000 |  | 4500000 |  | 225000 |  |  | 225000 | 4275000 | 342000 | 3933000 | 3933000 | 0
Reckon | 15000000 | 0 | 15000000 | 0 | 750000 |  | 0 | 750000 | 14250000 | 1140000 | 13110000 | 13110000 | 0
Reckon | 5362190 |  | 5362190 |  | 268109.5 |  |  | 268109.5 | 5094080.5 | 407526 | 4686554.5 | 4686555 | -0.5
Reckon | 2298081 |  | 2298081 |  | 114904.05 |  |  | 114904.05 | 2183176.95 | 174654 | 2008522.95 | 2008522 | 0.95
| 1998918 |  | 1998918 |  | 99945.9 |  |  | 99945.9 | 1898972.1 | 151918 | 1747054.1 | 1747054 | 0.1
Reckon | 9659189 | 0 | 9659189 | 0 | 482959.45 | 0 | 0 | 482959.45 | 9176229.55 | 734098 | 8442131.55 | 8442131 | 0.55
Reckon | 6276463 |  | 6276463 |  | 313823.15 |  | 150000 | 463823.15 | 5812639.85 | 465011 | 5347628.85 | 5347629 | -0.15
Reckon | 2689913 |  | 2689913 |  | 134495.65 |  |  | 134495.65 | 2555417.35 | 204433 | 2350984.35 | 2350984 | 0.35
Reckon | 8966376 | 0 | 8966376 | 0 | 448318.8 |  | 150000 | 598318.8 | 8368057.2 | 669444 | 7698613.2 | 7698613 | 0.2
Reckon | 5088842 |  | 5088842 |  | 254442.1 |  |  | 254442.1 | 4834399.9 | 386752 | 4447647.9 | 4447648 | -0.1
Reckon | 2180932 |  | 2180932 |  | 109046.6 |  |  | 109046.6 | 2071885.4 | 165751 | 1906134.4 | 1906134 | 0.4
Reckon | 4568324 |  | 2180932 |  | 228416.2 |  |  | 228416.2 | 1952515.8 | 156201 | 1796314.8 | 1796315 | -0.2
Reckon | 11838098 | 0 | 9450706 | 0 | 591904.9 | 0 | 0 | 591904.9 | 8858801.1 | 708704 | 8150097.1 | 8150097 | 0.1
Saddaqat | 6240389 | 0 | 6240389 | 0 | 312019.45 |  | 0 | 312019.45 | 5928369.55 | 474270 | 5454100 | 5454099 | 1
Saddaqat | 3039338 | 0 | 3039338 | 0 | 151966.9 |  | 0 | 151966.9 | 2887371.1 | 230990 | 2656381 | 2656381 | 0
Saddaqat | 14161007 |  | 14161007 | 1037354 | 708050.35 |  | 1140313 | 2885717.35 | 11275289.65 | 902023 | 10373267 | 10373267 | 0
Saddaqat | 15923063 |  | 15923063 | 0 | 796153.15 |  | 0 | 796153.15 | 15126909.85 | 1210153 | 13916757 | 13916757 | 0
Saddaqat | 2730091 |  | 2730091 |  | 136504.55 |  | 1734709 | 1871213.55 | 858877.45 | 68710 | 790167 | 790167 | 0
Saddaqat | 26046017 |  | 26046017 |  | 1302300.85 |  | 0 | 1302300.85 | 24743716.15 | 1979497 | 22764219 | 22764219 | 0
Saddaqat | 25481594 |  | 25481594 | 0 | 1274079.7 |  | 247973 | 1522052.7 | 23959541.3 | 1916763 | 22042778 | 22042778 | 0
Saddaqat | 9170838 |  | 9170838 |  | 458541.9 |  | 2205800 | 2664341.9 | 6506496.1 | 520520 | 5985976 | 5985976 | 0
Saddaqat | 3930359 |  | 3930359 |  | 196517.95 |  |  | 196517.95 | 3733841.05 | 298707 | 3435134 | 3435134 | 0
Saddaqat | 2083315 |  | 2083315 |  | 104165.75 |  |  | 104165.75 | 1979149.25 | 158332 | 1820817 | 1820817 | 0
Saddaqat | 892849 |  | 892849 |  | 44642.45 |  | 829400 | 874042.45 | 18806.55 | 1505 | 17302 | 17302 | 0
Saddaqat | 2840581 |  | 2840581 |  | 142029.05 | 1505000 | 1193295 | 2840324.05 | 256.95 | 21 | 236 | 0 | 236
Saddaqat | 1217392 |  | 1217392 |  | 60869.6 | 995000 | 160523 | 1216392.6 | 999.4 | 80 | 919 | 0 | 919
Saddaqat | 3390476 |  | 3390476 |  | 169523.8 |  | 405363 | 574886.8 | 2815589.2 | 225247 | 2590342 | 2590342 | 0
Saddaqat | 1453061 |  | 1453061 |  | 72653.05 |  |  | 72653.05 | 1380407.95 | 110433 | 1269975 | 1269975 | 0
Saddaqat | 2553885 |  | 2553885 |  | 127694.25 |  |  | 127694.25 | 2426190.75 | 194095 | 2232096 | 2232096 | 0
Saddaqat | 1094522 |  | 1094522 |  | 54726.1 |  |  | 54726.1 | 1039795.9 | 83184 | 956612 | 956612 | 0
Saddaqat | 1051837 |  | 1051837 |  | 52591.85 |  |  | 52591.85 | 999245.15 | 79940 | 919305 | 919305 | 0
| 123300614 | 0 | 123300614 | 1037354 | 6165030.7 | 2500000 | 7917376 | 17619760.7 | 105680853.3 | 8454470 | 97226383 | 97225227 | 1156
Saddaqat | 8838957 |  | 8838957 | 0 | 441947.85 |  | 0 | 441947.85 | 8397009.15 | 671761 | 7725248 | 7725248 | 0
Saddaqat | 2667316 | 0 | 2667316 | 0 | 133365.8 |  | 0 | 133365.8 | 2533950.2 | 202716 | 2331234 | 2331234 | 0
Saddaqat | 2349110 | 0 | 2349110 | 0 | 117455.5 |  | 0 | 117455.5 | 2231654.5 | 178532 | 2053123 | 2053123 | 0
Saddaqat | 289087 |  | 289087 |  | 14454.35 |  |  | 14454.35 | 274632.65 | 21971 | 252662 | 252662 | 0
Saddaqat | 14144470 | 0 | 14144470 | 0 | 707223.5 |  | 0 | 707223.5 | 13437246.5 | 1074980 | 12362267 | 12362267 | 0
Saddaqat | 6608962 |  | 6608962 |  | 330448.1 |  | 6221589 | 6552037.1 | 56924.9 | 4554 | 52371 | 52371 | 0
Saddaqat | 1820138 |  | 1820138 |  | 91006.9 |  |  | 91006.9 | 1729131.1 | 138330 | 1590801 | 1590801 | 0
Saddaqat | 4533291 |  | 4533291 | 0 | 226664.55 |  | 0 | 226664.55 | 4306626.45 | 344530 | 3962096 | 3962097 | -1
Saddaqat | 1027046 |  | 1027046 | 0 | 51352.3 |  | 0 | 51352.3 | 975693.7 | 78055 | 897639 | 897639 | 0
Saddaqat | 156811 |  | 156811 | 0 | 7840.55 |  | 0 | 7840.55 | 148970.45 | 11918 | 137052 | 137052 | 0
Saddaqat | 14146248 | 0 | 14146248 | 0 | 707312.4 |  | 6221589 | 6928901.4 | 7217346.6 | 577387 | 6639959 | 6639960 | -1
Saddaqat | 1788361 |  | 1788361 |  | 89418.05 |  |  | 89418.05 | 1698942.95 | 135915 | 1563028 | 1563028 | 0
Saddaqat | 3188729 |  | 3188729 |  | 159436.45 |  |  | 159436.45 | 3029292.55 | 242343 | 2786950 | 2786949 | 1
Saddaqat | 2469892 |  | 2469892 | 0 | 123494.6 |  | 0 | 123494.6 | 2346397.4 | 187712 | 2158685 | 2158686 | -1
Saddaqat | 2048062 |  | 2048062 |  | 102403.1 |  |  | 102403.1 | 1945658.9 | 155653 | 1790006 | 1790006 | 0
Saddaqat | 1428538 |  | 1428538 |  | 71426.9 |  |  | 71426.9 | 1357111.1 | 108569 | 1248542 | 1248542 | 0
Saddaqat | 222494 |  | 222494 |  | 11124.7 |  |  | 11124.7 | 211369.3 | 16910 | 194459 | 194459 | 0
Saddaqat | 601725 |  | 601725 |  | 30086.25 |  |  | 30086.25 | 571638.75 | 45731 | 525908 | 525908 | 0
Saddaqat | 11747801 | 0 | 11747801 | 0 | 587390.05 | 0 | 0 | 587390.05 | 11160410.95 | 892833 | 10267578 | 10267578 | 0
Saddaqat | 1415979 |  | 1415979 |  | 70798.95 |  |  | 70798.95 | 1345180.05 | 107614 | 1237566 | 1237566 | 0
Saddaqat | 851276 |  | 851276 |  | 42563.8 |  |  | 42563.8 | 808712.2 | 64697 | 744015 | 744015 | 0
Saddaqat | 2021302 |  | 2021302 |  | 101065.1 |  |  | 101065.1 | 1920236.9 | 153619 | 1766618 | 1766618 | 0
Saddaqat | 2115093 |  | 2115093 |  | 105754.65 |  |  | 105754.65 | 2009338.35 | 160747 | 1848591 | 1848591 | 0
Saddaqat | 6403650 | 0 | 6403650 | 0 | 320182.5 | 0 | 0 | 320182.5 | 6083467.5 | 486677 | 5596790 | 5596790 | 0
Saddaqat | 18816388 |  | 18816388 | 9859703 | 940819.4 | 6308951 | 0 | 17109473.4 | 1706914.6 | 136553 | 1570362 | 1570362 | 0
Saddaqat | 8064166 |  | 8064166 |  | 403208.3 |  | 1443953 | 1847161.3 | 6217004.7 | 497360 | 5719645 | 5719645 | 0
Saddaqat | 37921823 |  | 37921823 |  | 1896091.15 |  | 0 | 1896091.15 | 36025731.85 | 2882059 | 33143673 | 33143673 | 0
Saddaqat | 16252210 |  | 16252210 | 4851575 | 812610.5 |  | 848339 | 6512524.5 | 9739685.5 | 779175 | 8960511 | 8960511 | 0
Saddaqat | 5459976 |  | 5459976 |  | 272998.8 |  |  | 272998.8 | 5186977.2 | 414958 | 4772019 | 4772019 | 0
Saddaqat | 2339990 |  | 2339990 |  | 116999.5 |  |  | 116999.5 | 2222990.5 | 177839 | 2045152 | 2045152 | 0
Saddaqat | 28381199 |  | 28381199 |  | 1419059.95 | -6308951 |  | -4889891.05 | 33271090.05 | 2661687 | 30609403 | 30609403 | 0
Saddaqat | 12163371 |  | 12163371 |  | 608168.55 |  |  | 608168.55 | 11555202.45 | 924416 | 10630786 | 10630786 | 0
| 129399123 | 0 | 129399123 | 14711278 | 6469956.15 | 0 | 2292292 | 23473526.15 | 105925596.85 | 8474047 | 97451551 | 97451551 | 0
Saddaqat | 27701852 |  | 27701852 | 11466604 | 1385092.6 |  | 9296900 | 22148596.6 | 5553255.4 | 444260 | 5108995 | 5108995 | 0
Saddaqat | 11872222 |  | 11872222 | 7631500 | 593611.1 |  |  | 8225111.1 | 3647110.9 | 291769 | 3355342 | 3355342 | 0
Saddaqat | 72848437 |  | 72848437 | 56847621 | 3642421.85 |  | 11825700 | 72315742.85 | 532694.15 | 42616 | 490078 | 490078 | 0
Saddaqat | 31220759 |  | 31220759 | 28406350 | 1561037.95 |  | 0 | 29967387.95 | 1253371.05 | 100270 | 1153101 | 1153101 | 0
Saddaqat | 25314308 |  | 25314308 | 18228188 | 1265715.4 | 3494233 | 0 | 22988136.4 | 2326171.6 | 186094 | 2140078 | 2140078 | 0
Saddaqat | 10848989 |  | 10848989 |  | 542449.45 | 9000000 |  | 9542449.45 | 1306539.55 | 104523 | 1202017 | 1202017 | 0
Saddaqat | 10410780 |  | 10410780 | 1570750 | 520539 |  | 8154600 | 10245889 | 164891 | 13191 | 151700 | 151700 | 0
Saddaqat | 4461763 |  | 4461763 |  | 223088.15 |  |  | 223088.15 | 4238674.85 | 339094 | 3899581 | 3899581 | 0
Saddaqat | 1860668 |  | 1860668 |  | 93033.4 |  |  | 93033.4 | 1767634.6 | 141411 | 1626224 | 1626224 | 0
Saddaqat | 797430 |  | 797430 |  | 39871.5 |  |  | 39871.5 | 757558.5 | 60605 | 696954 | 696954 | 0
Saddaqat | 8034592 |  | 8034592 |  | 401729.6 | -12494233 |  | -12092503.4 | 20127095.4 | 1610168 | 18516927 | 18516927 | 0
Saddaqat | 3443395 |  | 3443395 |  | 172169.75 |  |  | 172169.75 | 3271225.25 | 261698 | 3009527 |  | 3009527
| 208815195 | 0 | 208815195 | 124151013 | 10440759.75 | 0 | 29277200 | 163868972.75 | 44946222.25 | 3595699 | 41350524 | 38340997 | 3009527
Sapper | 5715285 |  | 5715285 |  | 285764.25 |  |  | 285764.25 | 5429520.75 | 434362 | 4995159 | 4995159 | 0
Sapper | 319668 |  | 319668 |  | 15983.4 |  |  | 15983.4 | 303684.6 | 24295 | 279390 | 279390 | 0
Sapper | 3616029 |  | 3616029 |  | 180801.45 |  | 1206000 | 1386801.45 | 2229227.55 | 178338 | 2050890 | 2050890 | 0
Sapper | 1597069 |  | 1597069 |  | 79853.45 |  | 1336650 | 1416503.45 | 180565.55 | 14445 | 166121 | 166121 | 0
Sapper | 962971 |  | 962971 |  | 48148.55 |  |  | 48148.55 | 914822.45 | 73186 | 841636 | 885933 | -44297
Sapper | 1044288 |  | 1044288 |  | 52214.4 |  |  | 52214.4 | 992073.6 | 79366 | 912708 | 912715 | -7
Sapper | 45625 |  | 45625 |  | 2281.25 |  | 0 | 2281.25 | 43343.75 | 3468 | 39876 | 39876 | 0
Sapper | 834598 |  | 834598 |  | 41729.9 |  | 442200 | 483929.9 | 350668.1 | 28053 | 322615 | 278311 | 44304
Sapper | 261825 |  | 261825 |  | 13091.25 |  | 0 | 13091.25 | 248733.75 | 19899 | 228835 | 228835 | 0
Sapper | 14397358 | 0 | 14397358 | 0 | 719867.9 |  | 2984850 | 3704717.9 | 10692640.1 | 855412 | 9837230 | 9837230 | 0
Sapper | 1660699 |  | 1660699 |  | 83034.95 |  |  | 83034.95 | 1577664.05 | 126213 | 1451451 | 1451451 | 0
Sapper | 3224773 |  | 3224773 |  | 161238.65 |  |  | 161238.65 | 3063534.35 | 245083 | 2818451 | 2818451 | 0
Sapper | 1244104 |  | 1244104 |  | 62205.2 |  |  | 62205.2 | 1181898.8 | 94552 | 1087347 | 1087347 | 0
Sapper | 1484635 |  | 1484635 |  | 74231.75 |  |  | 74231.75 | 1410403.25 | 112832 | 1297571 | 1297571 | 0
Sapper | 1765819 |  | 1765819 |  | 88290.95 |  | 1339200 | 1427490.95 | 338328.05 | 27066 | 311262 | 311262 | 0
Sapper | 1614114 |  | 1614114 |  | 80705.7 |  | 0 | 80705.7 | 1533408.3 | 122673 | 1410735 | 1410735 | 0
Sapper | 3134064 |  | 3134064 | 2869304 | 156703.2 |  | 0 | 3026007.2 | 108056.8 | 8645 | 99412 | 99412 | 0
Sapper | 14128208 | 0 | 14128208 | 2869304 | 706410.4 |  | 1339200 | 4914914.4 | 9213293.6 | 737064 | 8476229 | 8476229 | 0
Sapper | 3699796 |  | 3699796 |  | 184989.8 |  |  | 184989.8 | 3514806.2 | 281184 | 3233622 | 3233622 | 0
Sapper | 872984 |  | 872984 |  | 43649.2 |  |  | 43649.2 | 829334.8 | 66347 | 762988 | 762988 | 0
Sapper | 6872362 |  | 6872362 | 5672978 | 343618.1 |  | 0 | 6016596.1 | 855765.9 | 68461 | 787305 | 787305 | 0
Sapper | 1861204 |  | 1861204 |  | 93060.2 |  | 1386900 | 1479960.2 | 381243.8 | 30500 | 350744 | 350744 | 0
Sapper | 13306346 | 0 | 13306346 | 5672978 | 665317.3 |  | 1386900 | 7725195.3 | 5581150.7 | 446492 | 5134659 | 5134659 | 0
Sapper | 7569125 |  | 7569125 |  | 378456.25 |  | 4051800 | 4430256.25 | 3138868.75 | 251110 | 2887759 | 2927636 | -39877
Sapper | 3247788 |  | 3247788 | 3035756 | 162389.4 |  | 0 | 3198145.4 | 49642.6 | 3971 | 45672 | 5795 | 39877
Sapper | 3173609 |  | 3173609 | 2673684 | 158680.45 |  | 321600 | 3153964.45 | 19644.55 | 1572 | 18073 | 18073 | 0
Sapper | 13990522 | 0 | 13990522 | 5709440 | 699526.1 |  | 4373400 | 10782366.1 | 3208155.9 | 256653 | 2951504 | 2951504 | 0
Sapper | 3684893 |  | 3684893 | 0 | 184244.65 |  | 0 | 184244.65 | 3500648.35 | 280052 | 3220596 | 3220596 | 0
Sapper | 3684893 | 0 | 3684893 | 0 | 184244.65 | 0 | 0 | 184244.65 | 3500648.35 | 280052 | 3220596 | 3220596 | 0
BA | 2726703 |  | 2726703 |  | 136335.15 |  |  | 136335.15 | 2590367.85 | 194278 | 2396090 | 2396090 | 0
BA | 2726703 | 0 | 2726703 | 0 | 136335.15 |  | 0 | 136335.15 | 2590367.85 | 194278 | 2396090 | 2396090 | 0
BA | 8704114 |  | 8704114 |  | 435205.7 |  |  | 435205.7 | 8268908.3 | 661513 | 7607395 | 7607395 | 0
BA | 3730334 |  | 3730334 |  | 186516.7 |  |  | 186516.7 | 3543817.3 | 283505 | 3260312 | 3260312 | 0
BA | 1568607 |  | 1568607 |  | 78430.35 |  |  | 78430.35 | 1490176.65 | 111763 | 1378414 | 1378414 | 0
BA | 672260 |  | 672260 |  | 33613 |  |  | 33613 | 638647 | 51092 | 587555 | 587555 | 0
BA | 14675315 | 0 | 14675315 | 0 | 733765.75 |  | 0 | 733765.75 | 13941549.25 | 1107873 | 12833676 | 12833676 | 0
BA | 788708 |  | 788708 |  | 39435.4 |  |  | 39435.4 | 749272.6 | 59942 | 689331 | 689331 | 0
BA | 338061 |  | 338061 |  | 16903.05 |  |  | 16903.05 | 321157.95 | 25693 | 295465 | 295465 | 0
BA | 9650325 |  | 9650325 |  | 482516.25 |  |  | 482516.25 | 9167808.75 | 733425 | 8434384 | 8434384 | 0
BA | 4135854 |  | 4135854 |  | 206792.7 |  |  | 206792.7 | 3929061.3 | 314325 | 3614736 | 3614736 | 0
BA | 14912948 | 0 | 14912948 | 0 | 745647.4 |  | 0 | 745647.4 | 14167300.6 | 1133385 | 13033916 | 13033916 | 0
BA | 11962276 |  | 11962276 |  | 598113.8 |  |  | 598113.8 | 11364162.2 | 909133 | 10455029 | 10455029 | 0
BA | 5126690 |  | 5126690 |  | 256334.5 |  |  | 256334.5 | 4870355.5 | 389628 | 4480728 | 4480728 | 0
BA | 17088966 | 0 | 17088966 | 0 | 854448.3 |  | 0 | 854448.3 | 16234517.7 | 1298761 | 14935757 | 14935757 | 0
Northland | 54264921 |  | 54264921 |  | 2713246.05 |  | 5792926 | 8506172.05 | 45758748.95 | 3431906 | 42326843 | 42326843 | 0
Northland | 23256395 |  | 23256395 | 20212009 | 1162819.75 |  | - | 21374828.75 | 1881566.25 | 141117 | 1740449 | 1740449 | 0
Northland | 29575045 |  | 29575045 | - | 1478752.25 |  | 21848500 | 23327252.25 | 6247792.75 | 468584 | 5779209 | 5779209 | 0
Northland | 12675019 |  | 12675019 | - | 633750.95 | 5386481 | - | 6020231.95 | 6654787.05 | 499109 | 6155678 | 6155678 | 0
Northland | 16422471 |  | 16422471 |  | 821123.55 |  | 12182300 | 13003423.55 | 3419047.45 | 256429 | 3162618 | 3162618 | 0
Northland | 7038202 |  | 7038202 |  | 351910.1 |  |  | 351910.1 | 6686291.9 | 501472 | 6184820 | 6184820 | 0
| 1218465 |  | 1218465 |  | 60923.25 |  |  | 60923.25 | 1157541.75 | 86816 | 1070726 | 1070726 | 0
Northland | 144450518 | 0 | 144450518 | 20212009 | 7222525.9 | 5386481 | 39823726 | 72644741.9 | 71805776.1 | 5385433 | 66420343 | 66420343 | 0
Northland | 70675451 |  | 70675451 | 54896634 | 3533772.55 |  | - | 58430406.55 | 12245044.45 | 918378 | 11326666 | 11326666 | 0
Northland | 180338923 |  | 180338923 | 17518456 | 9016946.15 |  | 40862300 | 67397702.15 | 112941220.85 | 8470592 | 104470629 | 104470629 | 0
Northland | 77288110 |  | 77288110 | - | 3864405.5 | 16043977 | 32257250 | 52165632.5 | 25122477.5 | 1884186 | 23238292 | 23238292 | 0
Northland | 11139911 |  | 11139911 | 4805225 | 556995.55 |  | 1391754 | 6753974.55 | 4385936.45 | 328945 | 4056991 | 4056991 | 0
Northland | 4774247 |  | 4774247 |  | 238712.35 |  |  | 238712.35 | 4535534.65 | 340165 | 4195370 | 4195370 | 0
Northland | 2212987 |  | 2212987 |  | 110649.35 |  |  | 110649.35 | 2102337.65 | 157675 | 1944663 | 1944663 | 0
Northland | 948423.19 |  | 948423.19 |  | 47421.1595 |  |  | 47421.1595 | 901002.0305 | 67575 | 833427 | 833427 | 0
Northland | 8613961 |  | 8613961 | 1168035 | 430698.05 |  | 2803900 | 4402633.05 | 4211327.95 | 315850 | 3895478 | 3895478 | 0
Northland | 3691698 |  | 3691698 |  | 184584.9 |  |  | 184584.9 | 3507113.1 | 263033 | 3244080 | 3244080 | 0
Northland | 48341904 |  | 48341904 |  | 2417095.2 |  | 25534494 | 27951589.2 | 20390314.8 | 1529274 | 18861041 | 12608870 | 6252171
| 408025615.19 | 0 | 408025615.19 | 78388350 | 20401280.7595 | 16043977 | 102849698 | 217683305.7595 | 190342309.4305 | 14275673 | 176066637 | 169814466 | 6252171
Northland | 27979610 |  | 27979610 | 17441253 | 1398980.5 | 3503234 |  | 22343467.5 | 5636142.5 | 422711 | 5213432 | 5213432 | 0
Northland | 11991261 |  | 11991261 |  | 599563.05 |  |  | 599563.05 | 11391697.95 | 854377 | 10537321 | 10537321 | 0
Northland | 32151391 |  | 32151391 | 7735701 | 1607569.55 |  | 5845713 | 15188983.55 | 16962407.45 | 1272181 | 15690226 | 15690226 | 0
Northland | 13779167 |  | 13779167 | 0 | 688958.35 | -3503234 | 3861382 | 1047106.35 | 12732060.65 | 954905 | 11777156 | 11777156 | 0
Northland | 4040802 |  | 4040802 |  | 202040.1 | 0 | 0 | 202040.1 | 3838761.9 | 287907 | 3550855 | 3550855 | 0
Northland | 1731772 |  | 1731772 |  | 86588.6 |  |  | 86588.6 | 1645183.4 | 123389 | 1521794 |  | 1521794
Northland | 5224304 |  | 5224304 |  | 261215.2 |  |  | 261215.2 | 4963088.8 | 372232 | 4590857 |  | 4590857
| 96898307 | 0 | 96898307 | 25176954 | 4844915.35 | 0 | 9707095 | 39728964.35 | 57169342.65 | 4287702 | 52881641 | 46768990 | 6112651
Northland | 9005163 |  | 9005163 |  | 450258.15 |  |  | 450258.15 | 8554904.85 | 641618 | 7913287 | 7913287 | 0
| 5488474 |  | 5488474 |  | 274423.7 |  |  | 274423.7 | 5214050.3 | 391054 | 4822996 | 0 | 4822996
Northland | 9005163 |  | 9005163 |  | 450258.15 |  |  | 450258.15 | 8554904.85 | 641618 | 7913287 | 7913287 | 0
Northland | 11572004 |  | 11572004 |  | 578600.2 |  |  | 578600.2 | 10993403.8 | 824505 | 10168899 | 10168899 | 0
| 2560514 |  | 2560514 |  | 128025.7 |  |  | 128025.7 | 2432488.3 | 182437 | 2250051 | 0 | 2250051
Northland | 37631318 | 0 | 37631318 | 0 | 1881565.9 | 0 | 0 | 1881565.9 | 35749752.1 | 2681232 | 33068520 | 25995473 | 7073047
Yukon | 56312925 |  | 56312925 | 0 | 2815646.25 |  | 0 | 2815646.25 | 53497278.75 | 4279782 | 49217497 | 49217497 | 0
Yukon | 73854676 |  | 73854676 | 0 | 3692733.8 |  |  | 3692733.8 | 70161942.2 | 5612955 | 64548987 | 64548986 | 1
Yukon | 100179346 |  | 100179346 | 94716616 | 5008967.3 |  | 96830 | 99822413.3 | 356932.7 | 28555 | 328378 | 328378 | 0
Yukon | 56914177 |  | 56914177 | 40024167 | 2845708.85 |  |  | 42869875.85 | 14044301.15 | 1123544 | 12920757 | 12920757 | 0
Yukon | 26164289 |  | 26164289 | 19625252 | 1308214.45 |  |  | 20933466.45 | 5230822.55 | 418466 | 4812357 | 4812357 | 0
Yukon | 11213266 |  | 11213266 | 0 | 560663.3 |  |  | 560663.3 | 10652602.7 | 852208 | 9800395 | 9800395 | 0
Yukon | 31817350 |  | 31817350 | 26386838 | 1590867.5 |  |  | 27977705.5 | 3839644.5 | 307172 | 3532473 | 3532473 | 0
Yukon | 13636008 |  | 13636008 |  | 681800.4 | 12954000 |  | 13635800.4 | 207.6 | 17 | 191 | 0 | 191
Yukon | 20249084 |  | 20249084 | 11946039 | 1012454.2 | 7290000 |  | 20248493.2 | 590.8 | 47 | 544 | 0 | 544
Yukon | 8678178 |  | 8678178 |  | 433908.9 | 7303464 |  | 7737372.9 | 940805.1 | 75264 | 865541 | 865541 | 0
Yukon | 2730982 |  | 2730982 |  | 136549.1 |  |  | 136549.1 | 2594432.9 | 207555 | 2386878 | 2386878 | 0
Yukon | 1170421 |  | 1170421 |  | 58521.05 |  |  | 58521.05 | 1111899.95 | 88952 | 1022948 | 1022948 | 0
Yukon | 14400679 |  | 14400679 | 10921515 | 720033.95 |  |  | 11641548.95 | 2759130.05 | 220730 | 2538400 | 2538400 | 0
Yukon | 6171717 |  | 6171717 |  | 308585.85 |  |  | 308585.85 | 5863131.15 | 469050 | 5394081 | 5394081 | 0
Yukon | 2250805 |  | 2250805 |  | 112540.25 |  |  | 112540.25 | 2138264.75 | 171061 | 1967204 | 1967204 | 0
Yukon | 964631 |  | 964631 |  | 48231.55 |  |  | 48231.55 | 916399.45 | 73312 | 843087 | 843087 | 0
Yukon | 426708534 | 0 | 426708534 | 203620427 | 21335426.7 | 27547464 | 96830 | 252600147.7 | 174108386.3 | 13928670 | 160179718 | 160178982 | 736
Yukon | 108682727 |  | 108682727 | 51241958 | 5434136.35 |  |  | 56676094.35 | 52006632.65 | 4160531 | 47846102 | 47846102 | 0
Yukon | 46578312 |  | 46578312 | 21982268 | 2328915.6 | 13947086 |  | 38258269.6 | 8320042.4 | 665603 | 7654439 | 7654439 | 0
Yukon | 19234743 |  | 19234743 | 17794764 | 961737.15 |  |  | 18756501.15 | 478241.85 | 38259 | 439983 | 439983 | 0
Yukon | 8243461 |  | 8243461 |  | 412173.05 |  |  | 412173.05 | 7831287.95 | 626503 | 7204785 | 7204785 | 0
Yukon | 12572914 |  | 12572914 | 8262145 | 628645.7 |  | 250338 | 9141128.7 | 3431785.3 | 274543 | 3157242 | 3157242 | 0
Yukon | 5388391.82 |  | 5388391.82 | 4546566 | 269419.591 |  | 0 | 4815985.591 | 572406.229 | 45792 | 526614 | 526614 | 0
| 8424214 |  | 8424214 | 5850851 | 421210.7 |  |  | 6272061.7 | 2152152.3 | 172172 | 1979980 | 1979980 | 0
| 3610377 |  | 3610377 |  | 180518.85 |  |  | 180518.85 | 3429858.15 | 274389 | 3155469 | 3155469 | 0
| 22749839 |  | 22749839 |  | 1137491.95 |  |  | 1137491.95 | 21612347.05 | 1728988 | 19883359 | 19883359 | 0
| 3884479 |  | 3884479 | 9373207 | 194223.95 | -13947086 | 0 | -4379655.05 | 8264134.05 | 661131 | 7603003 | 7603003 | 0
| 11414708 |  | 11414708 | 2891703 |  |  | 312939 | 3204642 | 8210066 | 656805 | 7553261 | 7553261 | 0
Yukon | 250784165.82 | 0 | 250784165.82 | 121943462 | 11968472.891 | 0 | 563277 | 134475211.891 | 116308953.929 | 9304716 | 107004237 | 107004237 | 0
Yukon | 26958060 |  | 26958060 | 19708848 | 1347903 | 5901000 |  | 26957751 | 309 | 25 | 284 | 0 | 284
Yukon | 11553455 |  | 11553455 | 7888317 | 577672.75 | 3087000 |  | 11552989.75 | 465.25 | 37 | 428 | 0 | 428
Yukon | 15982025 |  | 15982025 | 14260025 | 799101.25 |  |  | 15059126.25 | 922898.75 | 73832 | 849067 | 849067 | 0
Yukon | 6849440 |  | 6849440 |  | 342472 |  |  | 342472 | 6506968 | 520557 | 5986411 | 5986411 | 0
| 14961941 |  | 14961941 | 10121395 | 748097.05 |  |  | 10869492.05 | 4092448.95 | 327396 | 3765053 | 3765053 | 0
| 6412260 |  | 6412260 |  | 320613 |  |  | 320613 | 6091647 | 487332 | 5604315 | 5604315 | 0
| 15658544 |  | 15658544 |  | 782927.2 |  |  | 782927.2 | 14875616.8 | 1190049 | 13685568 | 13685568 | 0
| 7446552 |  | 7446552 |  | 372327.6 |  |  | 372327.6 | 7074224.4 | 565938 | 6508286 | 6508286 | 0
| 9902185 |  | 9902185 |  | 495109.25 |  |  | 495109.25 | 9407075.75 | 752566 | 8654510 | 8654510 | 0
Yukon | 115724462 | 0 | 115724462 | 51978585 | 5786223.1 | 8988000 | 0 | 66752808.1 | 48971653.9 | 3917732 | 45053922 | 45053210 | 712
Yukon | 11000719 |  | 11000719 | 0 | 550035.95 |  |  | 550035.95 | 10450683.05 | 836055 | 9614628 | 9614628 | 0
| 2515968 |  | 2515968 |  | 125798.4 |  |  | 125798.4 | 2390169.6 | 191214 | 2198956 | 2198956 | 0
Yukon | 13516687 | 0 | 13516687 | 0 | 675834.35 | 0 | 0 | 675834.35 | 12840852.65 | 1027269 | 11813584 | 11813584 | 0
Yukon | 7838177 |  | 7838177 | 0 | 391908.85 |  |  | 391908.85 | 7446268.15 | 595701 | 6850567 | 6850567 | 0
| 0 |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
Yukon | 7838177 | 0 | 7838177 | 0 | 391908.85 | 0 | 0 | 391908.85 | 7446268.15 | 595701 | 6850567 | 6850567 | 0
EDDCO | 89761229 |  | 89761229 | 55912625 | 4488061.45 |  | 0 | 60400686.45 | 29360542.55 | 2202041 | 27158502 | 27158502 | 0
EDDCO | 38469098 |  | 38469098 | 24859668 | 1923454.9 |  |  | 26783122.9 | 11685975.1 | 876448 | 10809527 | 10809527 | 0
EDDCO | 9887251 |  | 9887251 | 3715169 | 494362.55 |  | 0 | 4209531.55 | 5677719.45 | 425829 | 5251890 | 5251890 | 0
EDDCO | 4237393 |  | 4237393 | - | 211869.65 |  |  | 211869.65 | 4025523.35 | 301914 | 3723609 | 3723609 | 0
EDDCO | 2459357 |  | 2459357 | - | 122967.85 |  |  | 122967.85 | 2336389.15 | 175229 | 2161160 | 2161160 | 0
EDDCO | 1054010 |  | 1054010 | - | 52700.5 |  |  | 52700.5 | 1001309.5 | 75098 | 926212 | 926212 | 0
EDDCO | 1365880 |  | 1365880 | - | 68294 |  |  | 68294 | 1297586 | 97319 | 1200267 | 1200267 | 0
EDDCO | 585377 |  | 585377 |  | 29268.85 |  |  | 29268.85 | 556108.15 | 41708 | 514400 | 0 | 514400
| 1564022 |  | 1564022 |  | 78201.1 |  |  | 78201.1 | 1485820.9 | 111437 | 1374384 | 0 | 1374384
| 641264 |  | 641264 |  | 32063.2 |  |  | 32063.2 | 609200.8 | 45690 | 563511 | 0 | 563511
EDDCO | 150024881 | 0 | 150024881 | 84487462 | 7501244.05 | 0 | 0 | 91988706.05 | 58036174.95 | 4352713 | 53683462 | 51231167 | 2452295
EDDCO | 319492782 |  | 319492782 | 123187794 | 15974639.1 |  | 0 | 139162433.1 | 180330348.9 | 13524776 | 166805573 | 166805573 | 0
EDDCO | 131041841 |  | 131041841 | 48005107 | 6552092.05 |  | 17177165 | 71734364.05 | 59307476.95 | 4448061 | 54859416 | 54859416 | 0
EDDCO | 193086266 |  | 193086266 | 31918052 | 9654313.3 |  | 7361642 | 48934007.3 | 144152258.7 | 10811419 | 133340840 | 133340840 | 0
EDDCO | 212595104 |  | 212595104 | 71209699 | 10629755.2 |  | 35637835 | 117477289.2 | 95117814.8 | 7133836 | 87983979 | 87983979 | 0
EDDCO | 91112187 |  | 91112187 | 51781777 | 4555609.35 |  | 15273358 | 71610744.35 | 19501442.65 | 1462608 | 18038835 | 18038835 | 0
EDDCO | 187537799 |  | 187537799 | 91904419 | 9376889.95 |  |  | 101281308.95 | 86256490.05 | 6469237 | 79787253 | 79787253 | 0
EDDCO | 80373342 |  | 80373342 | 48517461 | 4018667.1 |  |  | 52536128.1 | 27837213.9 | 2087791 | 25749423 | 25749423 | 0
EDDCO | 32118343 |  | 32118343 | 28275183 | 1605917.15 |  |  | 29881100.15 | 2237242.85 | 167793 | 2069450 | 2069450 | 0
| 94244250 |  | 94244250 | 39106615 | 4712212.5 |  | 0 | 43818827.5 | 50425422.5 | 3781907 | 46643516 | 13575964 | 33067552
| 40390412 |  | 40390412 |  | 2019520.6 |  | 0 | 2019520.6 | 38370891.4 | 2877817 | 35493074 | 0 | 35493074
EDDCO | 1381992326 | 0 | 1247357664 | 494799492 | 62367883.2 |  | 75450000 | 632617375.2 | 614740288.8 | 46105521 | 568634769 | 568634769 | 0
EDDCO | 180292795 |  | 180292795 | 63874085 | 9014639.75 |  | 0 | 72888724.75 | 107404070.25 | 8055305 | 99348765 | 99348765 | 0
EDDCO | 75582520 |  | 75582520 | 32736665 | 3779126 |  |  | 36515791 | 39066729 | 2930005 | 36136724 | 36136724 | 0
EDDCO | 173962732 |  | 173962732 | 52449950 | 8698136.6 |  |  | 61148086.6 | 112814645.4 | 8461098 | 104353547 | 104353547 | 0
EDDCO | 74555456 |  | 74555456 | 48341629 | 3727772.8 |  |  | 52069401.8 | 22486054.2 | 1686454 | 20799600 | 20799600 | 0
EDDCO | 22443902 |  | 22443902 | 13339033 | 1122195.1 |  | 113529 | 14574757.1 | 7869144.9 | 590186 | 7278959 | 7278959 | 0
EDDCO | 9618816 |  | 9618816 | 5127340 | 480940.8 |  | 623757 | 6232037.8 | 3386778.2 | 254008 | 3132770 | 3132770 | 0
EDDCO | 12947204 |  | 12947204 | 11975032 | 647360.2 |  |  | 12622392.2 | 324811.8 | 24361 | 300451 | 300451 | 0
EDDCO | 5548802 |  | 5548802 | 4883024 | 277440.1 |  | 250308 | 5410772.1 | 138029.9 | 10352 | 127678 | 127678 | 0
| 688239 |  | 688239 | 0 | 34411.95 |  | 0 | 34411.95 | 653827.05 | 49037 | 604790 | 152010 | 452780
| 1982066 |  | 1982066 | 471225 | 99103.3 |  | 0 | 570328.3 | 1411737.7 | 105880 | 1305858 | 0 | 1305858
EDDCO | 557622532 | 0 | 557622532 | 233197983 | 27881126.6 | 0 | 987594 | 262066703.6 | 295555828.4 | 22166686 | 273389142 | 271630504 | 1758638
EDDCO | 48754035 | 0 | 48754035 | 0 | 2437701.75 |  | 0 | 2437701.75 | 46316333.25 | 3473725 | 42842608 | 42842608 | 0
EDDCO | 20894587 |  | 20894587 |  | 1044729.35 |  |  | 1044729.35 | 19849857.65 | 1488739 | 18361119 | 18361119 | 0
EDDCO | 199422 |  | 199422 |  | 9971.1 |  |  | 9971.1 | 189450.9 | 14209 | 175242 | 175242 | 0
EDDCO | 85466 |  | 85466 |  | 4273.3 |  |  | 4273.3 | 81192.7 | 6089 | 75104 | 75104 | 0
| 4817737 |  | 4817737 | 4305400 | 240886.85 |  |  | 4546286.85 | 271450.15 | 20359 | 251091 | 251091 | 0
| 2064745 |  | 2064745 | 1570750 | 103237.25 |  |  | 1673987.25 | 390757.75 | 29307 | 361451 | 361451 | 0
| 4057365 |  | 4057365 |  | 202868.25 |  |  | 202868.25 | 3854496.75 | 289087 | 3565410 | 3565410 | 0
EDDCO | 80873357 | 0 | 80873357 | 5876150 | 4043667.85 | 0 | 0 | 9919817.85 | 70953539.15 | 5321515 | 65632025 | 65632025 | 0
EDDCO | 0 | 75450000 | 75450000 | 0 | 0 |  | 0 | 0 | 75450000 | 5658750 | 69791250 | 69791250 | 0
EDDCO | 0 | 75450000 | 75450000 | 0 | 0 |  | 0 | 0 | 75450000 | 5658750 | 69791250 | 69791250 | 0
EDDCO | 32848430 | 0 | 32848430 | 0 | 1642421.5 |  | 0 | 1642421.5 | 31206008.5 | 2340451 | 28865558 | 0 | 28865558
EDDCO
EDDCO | 32848430 | 0 | 32848430 | 0 | 1642421.5 | 0 | 0 | 1642421.5 | 31206008.5 | 2340451 | 28865558 | 0 | 28865558
Inzi | 1269601 |  | 1269601 |  | 63480.05 |  | 0 | 63480.05 | 1206120.95 | 96490 | 1109631 | 1109631 | 0
| 1403569 |  | 1403569 |  | 70178.45 |  |  | 70178.45 | 1333390.55 | 106671 | 1226720 | 1226720 | 0
Inzi | 2673170 | 0 | 2673170 | 0 | 133658.5 | 0 | 0 | 133658.5 | 2539511.5 | 203161 | 2336351 | 2336351 | 0
Inzi | 9271299 |  | 9271299 |  | 463564.95 |  | 0 | 463564.95 | 8807734.05 | 704619 | 8103115 | 8103115 | 0
| 3172217 |  | 3172217 |  | 158610.85 |  |  | 158610.85 | 3013606.15 | 241088 | 2772518 | 0 | 2772518
Inzi | 12443516 | 0 | 12443516 | 0 | 622175.8 | 0 | 0 | 622175.8 | 11821340.2 | 945707 | 10875633 | 8103115 | 2772518
Inzi | 17451316 | 0 | 17451316 | 9767500 | 872565.8 |  | 0 | 10640065.8 | 6811250.2 | 544900 | 6266350 | 6266350 | 0
Inzi | 7479135 |  | 7479135 |  | 373956.75 |  |  | 373956.75 | 7105178.25 | 568414 | 6536764 | 6536764 | 0
Inzi | 12014298 |  | 12014298 |  | 600714.9 |  |  | 600714.9 | 11413583.1 | 913087 | 10500496 | 10500496 | 0
Inzi | 1663519 |  | 1663519 |  | 83175.95 |  |  | 83175.95 | 1580343.05 | 126427 | 1453916 | 1453916 | 0
Inzi | 5861922 |  | 5861922 |  | 293096.1 |  |  | 293096.1 | 5568825.9 | 445506 | 5123320 | 5123320 | 0
Inzi | 14210032 |  | 14210032 |  | 710501.6 |  |  | 710501.6 | 13499530.4 | 1079962 | 12419568 | 3000000 | 9419568
Inzi | 58680222 | 0 | 58680222 | 9767500 | 2934011.1 | 0 | 0 | 12701511.1 | 45978710.9 | 3678296 | 42300414 | 32880846 | 9419568
Landloard | 9476999 |  | 9476999 |  | 473849.95 |  | 0 | 473849.95 | 9003149.05 | 720252 | 8282897 | 8282898 | -1
Landloard | 4914153 |  | 4914153 |  | 245707.65 |  | 449249 | 694956.65 | 4219196.35 | 337536 | 3881660 | 3881660 | 0
| 423576 |  | 423576 |  | 21178.8 |  | 0 | 21178.8 | 402397.2 | 32192 | 370205 | 370205 | 0
Landloard | 14814728 | 0 | 14814728 | 0 | 740736.4 | 0 | 449249 | 1189985.4 | 13624742.6 | 1089980 | 12534762 | 12534763 | -1
Landloard | 14613393 |  | 14613393 |  | 730669.65 |  | 0 | 730669.65 | 13882723.35 | 1110618 | 12772105 | 12772105 | 0
| 0 |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
Landloard | 14613393 | 0 | 14613393 | 0 | 730669.65 | 0 | 0 | 730669.65 | 13882723.35 | 1110618 | 12772105 | 12772105 | 0
Landloard | 6160162 |  | 6160162 |  | 308008.1 |  |  | 308008.1 | 5852153.9 | 468172 | 5383982 | 5383982 | 0
| 8430433 |  | 8430433 |  | 421521.65 |  |  | 421521.65 | 8008911.35 | 640713 | 7368198 | 7368198 | 0
| 323390 |  | 323390 |  | 16169.5 |  |  | 16169.5 | 307220.5 | 24578 | 282643 | 282643 | 0
Landloard | 14913985 | 0 | 14913985 | 0 | 745699.25 | 0 | 0 | 745699.25 | 14168285.75 | 1133463 | 13034823 | 13034823 | 0
Landloard | 1594166 |  | 1594166 |  | 79708.3 |  | 0 | 79708.3 | 1514457.7 | 121157 | 1393301 | 1393301 | 0
| 3044726 |  | 3044726 |  | 152236.3 |  | 0 | 152236.3 | 2892489.7 | 231399 | 2661091 | 2661091 | 0
| 4890331 |  | 4890331 |  | 244516.55 |  |  | 244516.55 | 4645814.45 | 371665 | 4274149 | 4274149
Landloard | 9529223 | 0 | 9529223 | 0 | 476461.15 | 0 | 0 | 476461.15 | 9052761.85 | 724221 | 8328541 | 8328541 | 0
Landloard | 11810859 |  | 11810859 |  | 590542.95 |  | 427013 | 1017555.95 | 10793303.05 | 863464 | 9929839 | 9929839 | 0
| 1540857 |  | 1540857 |  | 77042.85 |  | 0 | 77042.85 | 1463814.15 | 117105 | 1346709 | 1346709 | 0
| 686019 |  | 686019 |  | 34300.95 |  | 0 | 34300.95 | 651718.05 | 52137 | 599581 | 599581 | 0
Landloard | 14037735 | 0 | 14037735 | 0 | 701886.75 | 0 | 427013 | 1128899.75 | 12908835.25 | 1032706 | 11876129 | 11876129 | 0
Landloard | 10968687 |  | 10968687 | 3980371 | 548434.35 |  | 0 | 4528805.35 | 6439881.65 | 515191 | 5924691 | 5924691 | 0
| 741488 |  | 741488 |  | 37074.4 |  | 0 | 37074.4 | 704413.6 | 56353 | 648061 | 648061 | 0
Landloard | 11710175 | 0 | 11710175 | 3980371 | 585508.75 | 0 | 0 | 4565879.75 | 7144295.25 | 571544 | 6572752 | 6572752 | 0
Landloard | 7389154 |  | 7389154 | 4318712 | 369457.7 |  | 0 | 4688169.7 | 2700984.3 | 216079 | 2484905 | 2484905 | 0
| 7599509 |  | 7599509 | 0 | 379975.45 |  | 0 | 379975.45 | 7219533.55 | 577563 | 6641971 | 6641971
Landloard | 14988663 | 0 | 14988663 | 4318712 | 749433.15 | 0 | 0 | 5068145.15 | 9920517.85 | 793642 | 9126876 | 9126876 | 0
Landloard | 6345858 |  | 6345858 | 4457690 | 317292.9 |  | 0 | 4774982.9 | 1570875.1 | 125670 | 1445205 | 1445205 | 0
| 3216561 |  | 3216561 | 0 | 160828.05 |  | 1937800 | 2098628.05 | 1117932.95 | 89435 | 1028498 | 1028498 | 0
Landloard | 9562419 | 0 | 9562419 | 4457690 | 478120.95 | 0 | 1937800 | 6873610.95 | 2688808.05 | 215105 | 2473703 | 2473703 | 0
| 11428773 |  | 11428773 | 0 | 571438.65 |  | 0 | 571438.65 | 10857334.35 | 868587 | 9988747 | 9988747 | 0
| 3569228 |  | 3569228 | 0 | 178461.4 |  | 0 | 178461.4 | 3390766.6 | 271261 | 3119506 | 3119506 | 0
| 14998001 |  | 14998001 | 0 | 749900.05 | 0 | 0 | 749900.05 | 14248100.95 | 1139848 | 13108253 | 13108253 | 0
| 24124658 |  | 24124658 | 0 | 1206232.9 |  | 0 | 1206232.9 | 22918425.1 | 1833474 | 21084951 | 11746087 | 9338864
| 14299807 |  | 14299807 |  | 714990.35 |  |  | 714990.35 | 13584816.65 | 1086785 | 12498032 |  | 12498032
| 38424465 | 0 | 38424465 | 0 | 1921223.25 | 0 | 0 | 1921223.25 | 36503241.75 | 2920259 | 33582983 | 11746087 | 21836896
| 11035066 |  | 11035066 | 0 | 551753.3 |  | 0 | 551753.3 | 10483312.7 | 838665 | 9644648 | 9644647 | 1
| 11035066 | 0 | 11035066 | 0 | 551753.3 |  | 0 | 551753.3 | 10483312.7 | 838665 | 9644648 | 9644647 | 1
Build Best | 5709767 |  | 5709767 |  | 285488.35 |  | 0 | 285488.35 | 5424278.65 | 433942 | 4990337 | 4990337 | 0
Build Best | 8967987 |  | 8967987 | 5345700 | 448399.35 |  | 3080500 | 8874599.35 | 93387.65 | 7471 | 85917 | 0 | 85917
Build Best | 14677754 | 0 | 14677754 | 5345700 | 733887.7 |  | 3080500 | 9160087.7 | 5517666.3 | 441413 | 5076254 | 4990337 | 85917
Build Best | 18210470 | ERP OK | 18210470 |  | 910523.5 |  | 0 | 910523.5 | 17299946.5 | 1383996 | 15915951 | 15915924 | 27
| 17909076 | ERP OK | 17909076 |  | 895453.8 |  | 0 | 895453.8 | 17013622.2 | 1361090 | 15652532 | 15652532 | 0
| 13495940 | ERP OK | 13495940 | 5345700 | 674797 |  | 6712825 | 12733322 | 762618 | 61009 | 701609 | 701609 | 0
| 21263766 | ERP OK | 21263766 | 11004123 | 1063188.3 |  | 1193100 | 13260411.3 | 8003354.7 | 640268 | 7363087 | 7363104 | -17
0
Build Best | 70879252 | 0 | 70879252 | 16349823 | 3543962.6 | 0 | 7905925 | 27799710.6 | 43079541.4 | 3446363 | 39633179 | 39633169 | 10
Chaudhary | 9670085.43 |  | 9670085.43 |  | 483504.2715 |  | 0 | 483504.2715 | 9186581.1585 | 734926 | 8451655 | 8451654 | 1
Chaudhary | 4144322 |  | 4144322 |  | 207216.1 |  | 0 | 207216.1 | 3937105.9 | 314968 | 3622138 | 3622138 | 0
Chaudhary | 0 |  | 0 |  | -690720 |  | 0 | -690720 | 690720 | 55258 | 635462 | 635462 | 0
Chaudhary | 14053089 |  | 14053089 |  | 702654.45 |  | 0 | 702654.45 | 13350434.55 | 1068035 | 12282400 | 12282400 | 0
| 945667 |  | 945667 |  | 47283.35 |  | 0 | 47283.35 | 898383.65 | 71871 | 826513 | 826513 | 0
| 28813163.43 | 0 | 28813163.43 | 0 | 749938.1715 | 0 | 0 | 749938.1715 | 28063225.2585 | 2245058 | 25818168 | 25818167 | 1
Shah Developers | 19638362 | ERP OK | 19638362 |  | 981918.1 |  | 0 | 981918.1 | 18656443.9 | 1399233 | 17257211 | 17257210 | 1
Shah Developers | 9582244 | ERP OK | 9582244 |  | 479112.2 |  |  | 479112.2 | 9103131.8 | 682735 | 8420397 | 8420396 | 1
| 1441320 | ERP OK | 1441320 |  | 72066 |  | 0 | 72066 | 1369254 | 102694 | 1266560 | 1266560 | 0
| 8389797 | ERP OK | 8389797 |  | 419489.85 |  | 0 | 419489.85 | 7970307.15 | 597773 | 7372534 | 7372534 | 0
| 4750602 | ERP OK | 4750602 |  | 237530.1 |  |  | 237530.1 | 4513071.9 | 338480 | 4174592 | 3000000 | 1174592
Shah Developers | 43802325 | 0 | 43802325 | 0 | 2190116.25 | 0 | 0 | 2190116.25 | 41612208.75 | 3120915 | 38491294 | 37316700 | 1174594 | 0
Zashpak | 2471420 |  | 2471420 |  | 123571 | 0 |  | 123571 | 2347849 | 187828 | 2160021 | 2160021 | 0
Zashpak | 1059180 |  | 1059180 |  | 52959 | 0 |  | 52959 | 1006221 | 80498 | 925723 | 925723 | 0
Zashpak | 0 |  | 0 |  | -176530 | 0 |  | -176530 | 176530 | 14122 | 162408 | 162408 | 0
Zashpak | 3530600 | 0 | 3530600 | 0 | 0 | 0 | 0 | 0 | 3530600 | 282448 | 3248152 | 3248152 | 0
Teepu Engineering | 7488477 |  | 7488477 |  | 374423.85 |  |  | 374423.85 | 7114053.15 | 569124 | 6544929 | 6544929 | 0
| 3209347 |  | 3209347 |  | 160467.35 | 0 |  | 160467.35 | 3048879.65 | 243910 | 2804970 | 2804970 | 0
| 4380110 |  | 4380110 |  | 219005.5 | 0 |  | 219005.5 | 4161104.5 | 332888 | 3828217 | 3828216 | 1
[5 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 15077934 | 0 | 15077934 | 0 | 753896.7 | 0 | 0 | 753896.7 | 14324037.3 | 1145922 | 13178116 | 13178115 | 1
Tuba | 5717309 |  | 5717309 |  | 285865.45 | 0 |  | 285865.45 | 5431443.55 | 434515 | 4996929 | 4996928 | 1
| 2776482 |  | 2776482 |  | 138824.1 | 0 | 237658 | 376482.1 | 2399999.9 | 192000 | 2208000 | 2208003 | -3
| 3156754 |  | 3156754 |  | 157837.7 | 0 |  | 157837.7 | 2998916.3 | 239913 | 2759003 | 2759003 | 0
| 11650545 | 0 | 11650545 | 0 | 582527.25 | 0 | 237658 | 820185.25 | 10830359.75 | 866428 | 9963932 | 9963934 | -2
Under Process RARs | 564295064 |  | 564295064 |  | 28214753.2 |  |  | 28214753.2 | 536080310.8 | 42886425 | 493193886 | 0 | 493193886
| 6059913920.16 | 75841908.85 | 5998341866.16 | 1756860657 | 295187146.408 | 72912190.15 | 473732647 | 2597109329.558 | 3414933670.602 | 263632604 | 3144450511.85 | 2560333677 | 584116834.85
6059913920.3729
0.21293

## Anx-G
Anx "G"
[23 empty] | 4265.3 | 2025-06-01
DETAIL OF CONST MATERIAL
Re-Modelling and Up Gradation of ADA Nullah and Walton Road Pkg-I
Rs in Million
Ser | Item | Unit | Total Qty Req (approx) | Purchases | [7 empty] | Consumed / Recovered | [7 empty] | Issued to contractor/ Concrete Production |  | Balance |  | Remarks
|  |  |  | During the Month |  |  | Upto Date |  |  | Year to Date |  | During the Month |  |  | Upto Date |  |  | Year to Date |  |  |  | Upto date
|  |  |  | Qty | Rate | Cost | Qty | Rate | Cost | Qty | Cost | Qty | Rate | Cost | Qty | Rate | Cost | Qty | Cost | Qty | Cost | Qty | Cost
JMF
1 | Cement (Bulk) | Ton | 26014 | 0 |  | 0 | 23061.48 |  | 620982522 | [5 empty] | 0 |  |  |  |  | 23057.984 | 620888330.2438 | 3.496 | 94191.7562 | 26927.2623 | 620888384.2908 | 620888384.2908 | 26942.722 | 26927.2623 | 620888384.2908
2 | Crush (All type) | Cft | 2032805 | 0 |  | 0 | 789825 |  | 109265210 |  |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 789825.385 | 109265210 | -0.385 | 0 | 138.341 | 109265263.2613 | 109265263.2613 | 195108685.1619
3 | Sand (lawarencepur) | Cft | 1588399 | 0 |  | 0 | 512025 |  | 85887344.1 |  |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 493813.82 | 85887344 | 18211.18 | 0.1 | 167.7405 | 503911.82 | 82832591.1424 | -195014493.4058
4 | Admixture | Kg | 252167 | 0 | 0 | 0 | 102900 | 119 | 12245100 | [10 empty] | 102900 | 12245100 | 0 | 0 | #DIV/0! | 127778.61 | #DIV/0! | 306.59
5 | Steel | [20 empty] | 0 | 0 |  |  |  | 8093976
6 | Steel G-60 No.3 | Ton | 582.32 |  |  |  | 240.9 | 262748.1 | 63296017.29 | [10 empty] | 5010.575 | 1316519060.8155 | 0 | 0 |  |  |  | -7999784.2438
7 | Steel G-60 No 4 | Ton | 1048.17 | 0 |  | 0 | 1705.835 | 262748.0998 | 448204904.8215
8 | Steel G-60 No 5 | Ton | 2154.58 |  |  |  | 1668.08 | 262748.1 | 438284850.648
9 | Steel G-60 No 6 | Ton | 1746.95 |  |  |  | 673.675 | 262748.1 | 177006826.2675
10 | Steel G-60 No 8 | Ton | 291.16 |  |  |  | 218.19 | 262748.1 | 57329007.939
11 | Steel G-60 No 10 | Ton | 291.16 |  |  |  | 186.685 | 262748.1 | 49051129.0485
12 | Steel G-60 No11 | Ton | 291.16 |  |  |  | 317.21 | 262748.1 | 83346324.801
13 | Concrete | [20 empty] | 0 | 0
14 | 1500 Psi | Cu.m | 0 | 0 |  | 0 | 3697.5 | 14200 | 52476100 |  |  | 0 |  | 0 | 62 |  | 880400 |  |  | 3635.5 | 51595700 | 0 | 0 | 3697.5 | 3697.5 | 0
15 | 2000 Psi | Cu.m | 0 | 0 |  | 0 | 96 | 15300 | 1468800 | [10 empty] | 96 | 1468800 | 0 | 0 | 96 | 96 | 0
16 | 3000 Psi | Cu.m | 0 | 0 |  | 0 | 2073.5 | 17400 | 35739600 |  |  | 0 |  | 0 | 187 |  | 3253800 |  |  | 1886.5 | 32485800 | 0 | 0 | 2073.5 | 2073.5 | 0
17 | 3500 Psi | Cu.m |  | 0 |  | 0 | 1133 |  | 22911908 |  |  | 0 |  | 0 | 1133 |  | 22911908 |  |  | 0 | 0 | 0 | 0 | 1133 | 1133 | 0
17 | 4000 Psi | Cu.m | 0 | 0 |  | 0 | 20723 | 20100 | 416512200 |  |  | 0 |  | 0 | 249.5 |  | 5014950 |  |  | 20473.5 | 411497250 | 0 | 0 | 20723 | 20723 | 0
18 | 5000 Psi | Cu.m |  |  |  |  | 12 | 23000 | 276000 |  |  | 0 | [7 empty] | 12 | 276000 | 0 | 0 | 12 | 12 | 0
19 | Pipe 66" Dia | Nos | 325 |  |  |  | 337 | 196903 | 66356311 |  |  | 0 | 0 | 0 | 337 | 196903 | 66356311 |  |  |  |  | 0 | 0
20 | Pipe 72" Dia | Nos | 379 |  |  |  | 472 | 238989 | 112802808 |  |  | 0 | 0 | 0 | 383.43 | 238989 | 91635552.3 |  |  | 88.6 | 21167255.7 | -0.03 | 0
21 | Pipe 27" Dia | Nos | 165 |  |  |  | 0 |  |  |  |  | 0 | [9 empty] | 0 | 0
22 | Pipe 30" Dia | Nos | 164 |  |  |  | 0 |  | 0 | [12 empty] | 0 | 0
23 | Pipe 36" Dia | Nos | 240 |  |  |  | 0 |  | 0 | [12 empty] | 0 | 0
24 | Pipe 42" Dia | Nos | 163 |  |  |  | 0 |  | 0 | [12 empty] | 0 | 0
25 | Pipe 48" Dia | Nos | 177 |  |  |  | 0 |  | 0 |  |  |  | 124182.8813 | [8 empty] | 0 | 0
26 | Pipe 54" Dia | Nos | 45 |  |  |  | 0 |  | 0 | [12 empty] | 0 | 0
27 | Submersiable Pump | Nos | 8 |  |  |  | 8 |  | 131000000 |  |  | 0 |  | 0 | 8 |  | 131000000 |  |  |  |  | 0 | 0
28 | HDP Pipes 1200mm | Rft |  | 422.19 |  | 14692000 | 3957.23 |  | 137711409.04 | 422.19 | 14692000 | 422 |  | 14692000 | 3957.2 |  | 137711409 | 422 | 14692000 | 0 | 0 | 0.03 | 0.04 |  | 34792.7073 | 4175124.8702 | 600
29 | HDP Pipes 1200mm - Alpha | Rft |  | 0 |  | 0 | 1414.17 |  | 50372735.4 |  |  | 0 |  | 0 | 96.27 |  | 3429137 |  |  | 1317.9 | 46943598 | 0 | 0.4 |  | 0
30 | HDP Pipes 1200mm - Plascoo | Rft |  | 0 |  | 0 | 350 |  | 12250000 |  |  | 0 |  | 0 | 350 |  | 12250000 |  |  |  |  | 0 | 0
31 | HDP Pipes 900mm | mtr |  | 0 |  |  | 45.75 |  | 3435000 |  |  | 0 |  | 0 | 45.75 |  | 3435000 |  |  |  |  | 0 | 0
32 | HDP Pipes 630mm | mtr |  | 0 |  | 0 | 3843 |  | 82530000 |  |  | 8.38 |  | 179963.9358 | 2421 |  | 51991730.92 | 8.4 | 179963.94 | 1127.0954 | 24204599.0911 | 294.9046 | 6333669.9889 |  | 152.3926 | 37
33 | HDP Pipes 450mm | Rft |  | 0 |  | 0 | 255 |  | 1389622.5 |  |  | 0 |  | 0 | 255 |  | 1389623 |  |  |  |  | 0 | -0.5
33 | HDP Pipes 250mm | mtr |  | 0 |  |  | 671 |  | 2331865.91 |  |  | 11.455 |  | 39808.5305 | 347 |  | 1205741.9 | 11.5 | 39809 | 0 | 0 | 324 | 1126124.01
34 | HDP Pipes 160mm | Rft |  | 0 |  |  | 1600 |  | 1040000 |  |  | 0 |  | 0 | 1600 |  | 1040000 |  |  |  |  | 0 | 0
35 | HDP Pipes 125mm | Rft |  | 0 |  | 0 | 120 |  | 60000 |  |  | 0 |  | 0 | 120 |  | 60000 |  |  |  |  | 0 | 0
36 | Asphalt Base Course | Ton |  | -3702.9 | 13000 | -46297358.7 | 50252 |  | 628308789.11 | -3702.9 | -46297358.7 | -3702.9 |  | -46297358.7 | 50252.18 |  | 628308789.11 | -3702.9 | -46297358.7 |  |  | -0.18 | 0 | 12503.1151 | 75018690.4262
37 | AWC | Ton |  | -1413.92 | 13200.024 | -18663744 | 23171 |  | 305857755 | -1413.92 | -18663744 | -1413.92 |  | -18663744 | 23170.8 |  | 305857755 | -1413.92 | -18663744 |  |  | 0.2 | 0 | 13200.1379 | 39600413.6672 |  | 7920000
38 | Manhole Covers - RPC | Nos |  | 0 |  | 0 | 500 |  | 7150000 |  |  | 0 |  | 0 | 169 |  | 2416700 |  |  |  |  | 331 | 4733300
37 | Ductile Iron Cover & Frame | Nos |  | 0 |  | 0 | 252 |  | 17773520 |  |  | 0 |  | 0 | 152 |  | 10720534 |  |  | 0 | 0 | 100 | 7052986 |  | 3526490
38 | 4" UPVC Pipe Class-D | rft |  | 0 |  | 0 | 5600 |  | 2268000 | [5 empty] | 5600 |  | 2268000 |  |  | 0 | 0 | 0 | 0
39 | 6" UPVC Pipe Class-D | rft |  | 0 |  | 0 | 2550 |  | 2282250 |  |  | 0 |  | 0 | 2550 |  | 2282250 |  |  | 0 | 0 | 0 | 0
40 | 6" UPVC Pipe Class-B | Rft |  | 0 |  | 0 | 390 |  | 202858.5 |  |  | 0 |  | 0 | 390 |  | 202858.5 |  |  |  |  | 0 | 0
40 | 8" UPVC Pipe Class-D | rft |  | 0 |  | 0 | 2332 |  | 5270720 |  |  | 130 |  | 293100 | 2332.31 |  | 5270720 | 130 | 293100 | 0 | 0 | -0.31 | 0
41 | 4" UPVC Pipe Class-B | Rm |  | 0 |  | 0 | 15331 |  | 10808355 |  |  | 0 |  | 0 | 12175.4 |  | 8583368.1 |  |  |  |  | 3155.6 | 2224986.9 |  | 416655 | 0
42 | 4" UPVC Pipe Class-D 100 MM Dia | mtr |  | 0 |  | 0 | 1912 |  | 2351760 |  |  | 0 |  | 0 | 1912 |  | 2351760 |  |  |  |  | 0 | 0 |  |  | 2083698
43 | 2" UPVC Pipe Class-B | Rm |  | 0 |  | 0 | 5736 |  | 1778160 |  |  | 0 |  | 0 | 0 |  | 0 |  |  |  |  | 5736 | 1778160
44 | HDPE Bend 90 Dia 1200mm | Nos |  | 0 |  | 0 | 4 |  | 3600000 |  |  | 0 |  | 0 | 4 |  | 3600000 |  |  |  |  | 0 | 0
45 | 90",45" Bend 900 mm |  |  | 0 |  | 0 | 3 |  | 2655000 |  |  | 0 |  | 0 | 3 |  | 2655000 |  |  |  |  | 0 | 0
46 | HDP Fitting Butt Fusion Stub End | Nos |  | 0 |  | 0 | 1 |  | 236000 |  |  | 0 |  | 0 | 1 |  | 236000 |  |  |  |  | 0 | 0
47 | 45 DEG Elbow Dia 4" | Nos |  | 0 |  | 0 | 200 |  | 59620 |  |  | 0 |  | 0 | 200 |  | 59620 |  |  |  |  | 0 | 0
48 | 630 KVA Transformer | Nos |  | 0 |  | 0 | 1 |  | 4240000 |  |  | 0 |  | 0 | 1 |  | 4240000 |  |  |  |  | 0 | 0
49 | 400KVA Transformer | Nos |  | 0 |  | 0 | 1 |  | 3250000 |  |  | 0 |  | 0 | 1 |  | 3250000 |  |  |  |  | 0 | 0
50 | 50KVA Transformer | Nos |  | 0 |  | 0 | 4 |  | 3400000 |  |  | 0 |  | 0 | 4 |  | 3400000 |  |  |  |  | 0 | 0
51 | Road Light 120W | Nos |  | 0 |  |  | 210 |  | 6693521.1 |  |  | 0 |  | 0 | 210 |  | 6693521 |  |  |  |  | 0 | 0.1
52 | Road Light 150W | Nos |  | 0 |  | 0 | 38 |  | 1254718.96 |  |  | 0 |  | 0 | 38 |  | 1254719 |  |  |  |  | 0 | -0.04
53 | Road Light 180W | Nos |  | 0 |  | 0 | 132 |  | 4878218.4 |  |  | 0 |  | 0 | 132 |  | 4878218.4 |  |  |  |  | 0 | 0
54 | 4 Core 35mm | Mtr |  | 0 |  |  | 750 |  | 494325.6 |  |  | 0 | 659.1008 | 0 | 750 |  | 494325.48 |  |  |  |  | 0 | 0.12
55 | 4 Core 25mm | Mtr |  | 0 |  |  | 16500 |  | 8489893.544 |  |  | 1874 | 514.539 | 964379.14 | 14838.8 |  | 7635030.6552 | 1874 | 964379.1 |  |  | 1661.2 | 854862.8888 | 514.6056
56 | 4 Core 50mm | Mtr |  | 0 |  | 0 | 2000 |  | 3452400 |  |  | 0 | [9 empty] | 2000 | 3452400
57 | 4 Core 16mm | Mtr |  | 0 |  | 0 | 90 |  | 181244 |  |  | 90 |  | 181244 | 90 |  | 181244 | 90 | 181244 |  |  | 0 | 0
58 | Single Core 16mm | Mtr |  | 0 |  | 0 | 17500 |  | 1614210.48 |  |  | 1340 | 92.2406 | 123548 | 14839 |  | 1368457.864 | 1340 | 123548 |  |  | 2661 | 245752.616
59 | Single Core 2.5mm | Mtr |  | 0 |  | 0 | 25270 |  | 2048836 |  |  | 3240 | 81.0778 | 272049 | 25270 |  | 2048836 | 3240 | 272049 |  |  | 0 | 0
60 | Single Core 300mm | Mtr |  | 0 |  | 0 | 1000 |  | 9127677.6 |  |  | 0 | 9127.6776 | 0 | 572 |  | 5221022 |  |  |  |  | 428 | 3906655.6
61 | Single Core 120mm | Mtr |  | 0 |  |  | 375 |  | 1335022.5 |  |  | 0 | 3560.06 | 0 | 375 |  | 1335022.5 |  |  |  |  | 0 | 0
62 | Single Core 150mm | Mtr |  | 0 |  |  | 160 |  | 717815.712 |  |  | 0 | 4486.3482 | 0 | 160 |  | 717815.6696 |  |  |  |  | 0 | 0.0424
63 | Single Core 70mm | Mtr |  | 0 |  |  | 280 |  | 561825.376 |  |  | 0 | 2006.5192 | 0 | 280 |  | 561825.4008 |  |  |  |  | 0 | -0.0248
64 | 1x1.15mm 450/750 , Red/Black. Green | Coil |  | 0 |  | 0 | 18 |  | 81846 |  |  | 0 |  | 0 | 18 |  | 81846 |  |  |  |  | 0 | 0
65 | 1x6mm 450/750 , Red/Black. Green | Coil |  | 0 |  | 0 | 9 |  | 140382 |  |  | 0 |  | 0 | 9 |  | 140382 |  |  |  |  | 0 | 0
66 | 1x4mm 450/750 , Red/Black. Green | Coil |  | 0 |  | 0 | 9 |  | 95175 |  |  | 0 |  | 0 | 9 |  | 95175 |  |  |  |  | 0 | 0
67 | 12 mtr Electric Pole Double Arm | Nos |  | 0 |  | 0 | 148 |  | 17316000 |  |  | 7 |  | 819000 | 115 |  | 13455000 | 7 | 819000 | 12 | 1404000 | 21 | 2457000 | 117000
68 | 10 Mtr Single Arm | Nos |  | 0 |  |  | 13 |  | 1313000 |  |  | 0 |  | 0 | 0 |  | 0 |  |  | 13 | 1313000 | 0 | 0
69 | 10 Mtr Double Arm | Nos |  | 0 |  |  | 4 |  | 418000 |  |  | 0 |  | 0 | 0 |  | 0 |  |  | 4 | 418000 | 0 | 0
70 | 12 mtr Electric Pole Single Arm | Nos |  | 0 |  | 0 | 270 |  | 30780000 |  |  | 6 |  | 684000 | 220 |  | 25080000 | 6 | 684000 | 10 | 1140000 | 40 | 4560000
71 | Light Control Pannel | Nos |  |  |  |  | 4 |  | 2006000 |  |  | 0 |  | 0 | 4 |  | 2006000 |  |  |  |  | 0 | 0
72 | ATB Box | Nos |  | 0 |  | 0 | 12 |  | 1038080 |  |  | 0 |  | 0 | 8 |  | 692053.6 |  |  |  |  | 4 | 346026.4 | 86506.6
73 | Barrier | Nos |  | 0 |  | 0 | 1100 |  | 16972800 |  |  | 0 |  | 0 | 1100 |  | 16972800 |  |  |  |  | 0 | 0
74 | Tuff Apver Gray 60mm | Nos |  | 0 |  | 0 | 72845 |  | 11072440 | [10 empty] | 72845 | 11072440 | 0 | 0
75 | Kerb Stone 6"x12"x14" | Nos |  | 0 |  | 0 | 6368 |  | 1974080 | [10 empty] | 6368 | 1974080 | 0 | 0
76 | Grating as per Drawing 2'x7" | Nos |  | 0 |  | 0 | 140 |  | 975800 | [10 empty] | 140 | 975800 | 0 | 0
77 | Gen Set 400KVA Diesel | Nos |  | 0
G.Total | [5 empty] | -50269102.7 |  | 2365247.6998 | 4402089696.6475 |  | -50269102.7 |  |  | -46712010.0936 |  |  | 1610182212.3996 | 0 | -46712009.66 |  | 2752741367.8505 |  | 39166116.3974
G.Total | [7 empty] | 2365247.6998 | 4452358799.6475 |  | 1706846906.488 | [5 empty] | 1656894222.3596 | 0 | 1269742045.8756 |  | 2725884571.7096 |  | 99359126.9883
[9 empty] | -50269103 |  | -1757116009.188 | [5 empty] | -46712009.96 |  | -1316454055.5356 | 0 | 26856796.1408 | 0 | -60193010.5908
-1269742045.4419
12503.1599
50252
678402000
-50093210.89

## JMF
Re Modelling and Upgradation of ADA Nullah and Walton Road Package -1
SUPPLY OF 3000 & 4000 PSI CONCRETE UPTO Jun 2025
Sublet Contractor: M/S Saddaqat Builders
Sr No. | Item Description | Unit | Qty | Material Qty
|  |  |  | Cement (bags) | Sand (Cft) | Crush (Cft) |  |  |  | Conc Admixture
[6 empty] | 5-10 | 10-19 | 19-25 | Total
1 | 1500 PSI Conc. | CM | 3697.5 | 12645.45 | 74837.4 | 25327.875 | 76020.6 | 25327.875 | 126676.35 | 7616.85
2 | 2000 PSI Conc. | CM | 96 | 426.24 | 1604.16 | 642.24 | 1924.8 | 642.24 | 3209.28 | 255.36
3 | 3000 PSI Conc. | CM | 2073.5 | 13145.99 | 34565.245 | 13187.46 | 39562.38 | 13187.46 | 65937.3 | 7879.3
4 | 3500 PSI Conc. | CM | 1133 | 9064 | 26432.89 | 1450.24 | 18014.7 | 3772.89 | 23237.83 | 4192.1
5 | 4000 PSI Conc. | CM | 20723 | 178217.8 | 365139.26 | 117499.41 | 351669.31 | 117499.41 | 586668.13 | 107759.6
6 | 5000 PSI Conc. | CM | 12 | 122.4 | 211.44 | 68.04 | 203.64 | 68.04 | 339.72 | 62.4
7 | 6000 PSI Conc. | CM | 2.5 | 25.5 | 44.05 | 14.175 | 42.425 | 14.175 | 70.775 | 13
8 | NERO | CM | 110.5 | 884 | 1077.375
|  |  |  | 214531.38 | 503911.82 | 158189.44 | 487437.855 | 160512.09 | 806139.385 | 127778.61
|  |  |  | 10726.569 | 512025 | 806139.385
[5 empty] | -8113.18 |  |  | 789825
16314.385
|  |  |  | 23057.984 | 493813.82 |  |  | 789825.385 |  | 102900

## Anx-H
Anx "H"
DETAIL OF EQPTS, PLANTS, MACHINERY
Re-Modelling and Up Gradation of ADA Nullah and Walton Road Pkg-I
Ser | Description |  |  | During the Month | [5 empty] | Upto Date | [5 empty] | Year to Date
|  | Regn No | Hiring Date | Hours/Kms | Amount of hiring* (Rs) | Qty of POL Issued | Amount of Fuel Issued (Rs) | Repair/ Maint (Rs) | Total Amount (Rs) | Hours/Kms | Amount of hiring* (Rs) | Qty of POL Issued | Amount of Fuel Issued (Rs) | Repair/ Maint (Rs) | Total Amount (Rs) | Hours/Kms | Amount of hiring* (Rs) | Qty of POL Issued | Amount of Fuel Issued (Rs) | Repair/ Maint (Rs) | Total Amount (Rs)
1 | Plant & Machinery (Hired) |  |  |  | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
2
3
4
5
6
7
8
9
10
[9 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
| NLC Own Vehicle | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0
1
2
3
4
5
6
7
8
9
10
Total Amounts (M) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Anx-J
STATUS OF INTERIM PAYMENT CERTIFICATES
Re-Modelling and Up Gradation of ADA Nullah and Walton Road Pkg-I
[8 empty] | Additions |  |  | Deductions
Sr # | Description | Date of Submission | Date of Vetting | Work Done | Vetted Work Done | Escl | Vetted Escl | Mob Adv | S. Adv | With Held | With Held | Mob Adv | Sec Adv | Retension Money | PRA 5% | PRA PSID | IT Tax | Total Deductions | Net Receivable | Received | Vetted Receivables
1 | IPC # 01 Mob Adv |  |  |  |  | 0 |  | 240121355 | [9 empty] | 0 | 240121355 | 240121355 | 0
3 | IPC # 03 Mob Adv |  |  | 0 |  | 0 |  | 500000000 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 500000000 | 500000000 | 0
10 | IPC # 10 |  |  | 0 |  | 0 |  | 695967594 | 0 |  |  |  | 0 | 0 | 0 |  |  | 0 | 695967594 | 695967594 | 0
[19 empty] | 0 |  | 0
2 |  | 2023-12-24 | 2023-12-26 | 95951053.8 | 95951053.8 | 0 |  | 0 | 76654847 |  |  | 0 |  | 5047553 | 4569097.8 |  | 0 | 9616650.8 | 162989250 | 162989250 | 0
4 | IPC # 04 | 2024-01-20 | 2024-01-31 | 349372175.25 | 349372175.25 | 0 |  |  | 0 |  |  | 0 | 15560790 | 17718609 | 16636770.25 |  |  | 49916169.25 | 299456006 | 299456006 | 0
5 | IPC # 05 | 2024-03-01 | 2024-03-04 | 289816144.8 | 289816144.8 | 0 |  | 0 | 75450000 |  |  | 0 | 0 | 14740807 | 13800768.8 |  |  | 28541575.8 | 336724569 | 336724569 | 0
6 | IPC # 06 | 2024-03-04 | 2024-03-12 | 698704235.25 | 698704235.25 | 0 |  | 0 | 0 |  |  | 174676059 | 36004285 | 35185211 | 33271630.25 |  |  | 279137185.25 | 419567050 | 419567050 | 0
7 | IPC # 07 | 2024-03-27 | 2024-04-01 | 645422988 | 645422988 | 0 |  | 0 | 0 |  |  | 161355747 | 4559779 | 32521149 | 30734428 |  |  | 229171103 | 416251885 | 416251885 | 0
8 | IPC # 08 | 2024-04-01 | 2024-04-02 | 248654835.45 | 248654835.45 | 0 |  | 0 | 0 |  |  | 62163709 | 0 | 12682742 | 11840706.45 |  |  | 86687157.45 | 161967678 | 161967678 | 0
9 | IPC # 09 | 2024-05-08 | 2024-05-14 | 220850563.5 | 220850563.5 | 0 |  | 0 | 0 |  |  | 55212641 | 24538808 | 11292528 | 10516693.5 | 100 | 0 | 101560770.5 | 119289793 | 119289793 | 0
11 | IPC # 11 | 2024-05-10 | 2024-06-01 | 1547888250.3 | 1547888250.3 |  | 0 |  | 0 | 0 | 846712823 | 175293857.075 | 0 | 25881471 | 33389306 | 100 | 47235501.5169 | 1128513058.5919 | 419375191.7081 | 419375192 | -0.29188
12 | IPC # 11-Balance |  |  | 0 | 0 |  |  |  |  | 0 | -846712822 | 211678205.5 | 2107717 | 51762942 | 40319658 | 100 | 43587296.8125 | -497256902.6875 | 497256902.6875 | 497256903 | -0.3125
13 | IPC # 12 | 2024-06-06 | 2024-06-10 | 358919541.75 | 358919541.75 |  |  |  | 0 |  |  | 89729885.5 | 50911193 | 18195977 | 17091406.75 | 100 | 15006186.4688 | 190934748.7188 | 167984793.0312 | 167984793 | 0.03125
14 | IPC # 13 | 2024-06-13 | 2024-07-27 | 756910372.05 | 756910372.05 |  |  |  | 0 |  |  | 189227593 | 18422281 | 38095519 | 36043351.05 | 100 | 38337373.4287 | 320126217.4787 | 436784154.5712 | 436784155 | -0.42875
15 | IPC # 14 | 2024-07-30 | 2024-08-06 | 318517559.85 | 318517559.85 | 38753765.4 | 38753765.4 |  | 0 |  |  | 89317831 | 0 | 18113566 | 17012920.25 | 100 | 18737994.6187 | 143182411.8688 | 214088913.3812 | 214088913 | 0.38125
16 | IPC # 15 |  |  | 771626988.3 | 771626988.3 | 0 | 0 |  |  |  |  | 192906747 |  | 38831349 | 36744142.3 | 100 | 40491766.9225 | 308974105.2225 | 462652883.0775 | 462652883 | 0.0775
17 | IPC # 16 |  | 2024-10-17 | 201897761.1 | 201897761.1 | 0 | 0 | 0 |  |  |  | 34526673 |  | 10344888 | 9614179.1 | 100 | 11776965.0075 | 66262805.1075 | 135634955.9925 | 135634956 | -0.0075
18 | IPC # 17 | 2024-11-11 | 2024-12-03 | 611180292 | 611180292 | 0 | 0 |  |  |  | 14466910 |  |  | 30085669 | 28414923 | 100 | 42497078 | 115464680 | 495715612 | 495715611 | 1
19 | EPC - 1 |  |  | 0 | 0 | 95660134.5 | 95660134.5 | [7 empty] | 4555244.5 |  | 7174510.0875 | 11729754.5875 | 83930379.9125 | 83930380 | -0.0875
20 | IPC # 18 | 2025-01-10 |  | 288906781.8 | 288906781.8 | 0 | 0 |  |  |  | 10000000 |  |  | 14695339 | 13757466 | 200 | 20565858.21 | 59018863.21 | 229887918.59 | 229887919 | -0.41
21 | IPC # 19 | 2025-02-24 |  | 160179279.75 | 160179279.75 | 0 | 0 | [6 empty] | 8258964 | 7627585 | 200 | 11394023.6813 | 27280772.6812 | 132898507.0687 | 132898507 | 0.06875
22 | IPC # 20 | 2025-03-04 | 2025-03-31 | 825936605.55 | 825936605.55 | 0 | 0 |  |  |  | 35803516 |  |  | 41546831 | 39330315 | 200 | 51345279 | 168026141 | 657910464.55 | 657910265 | 199.55
| IPC # 21 |  |  | 169000000 | 169000000 | 0 | 0 | [6 empty] | 0 | 8047619.0476 | 100 | 5070000 | 13117719.0476 | 155882280.9524 | 155882281 | -0.047619
| IPC # 21 Balance |  |  | 64535111.6 | 64535111.6 | [8 empty] | 11120720 | 3073100.5524 |  | 0 | 14193820.5524 | 50341291.0476 | 0 | 50341291.0476
| IPC # 22 |  |  | 490549000 | 0 | [8 empty] | 24527450 | 23096283 |  | 0 | 47623733 | 442925267 | 0 | 0
| UP |  |  | 456556200 | [9 empty] | 22827810 | 22430771 |  | 0 | 45258581 | 411297619 | 0 | 0
|  |  |  | 9571375740.1 | 8624270540.1 | 134413899.9 | 134413899.9 | 1436088949 | 152104847 | 0 | 60270427 | 1436088948.075 | 152104853 | 483477094 | 461918365.6 | 1600 | 353219833.7544 | 2947081121.4294 | 8346902314.5706 | 7442337938 | 50341490.5706
|  |  |  | Work Done |  | Vetted Work
|  | Anx J |  | 9571.3757 |  | 8624.2705 | [8 empty] | 0.26207
|  | Anx A |  | 9571.3756 |  | 8624.2706
|  |  |  | 0.0001648 |  | -9.9e-06

## Anx-K
STATE OF CLAIMS / VARIATION ORDERS
Re-Modelling and Up Gradation of ADA Nullah and Walton Road Pkg-I
Ser | Type of Claim | Revenue Claimed |  |  | Vetted Cost by Client |  | Remarks
|  | During Month | Update | YTD | Update | YTD
| EPC-1 | 0 | 91.12 | 0 | 91.12 | 0 |  | 91.12 | 86.781
| EPC-2 IPC # 14 |  | 36.893 | 0 | 36.893 | 0 |  | 36.893 | 35.1362
| Under Process | 0
|  |  | 0 |  | 0 | 0
Total |  | 0 | 128.013 | 0 | 128.013 | 0
PST 5% |  | 0 | 6.4007 | 0 | 6.4007 | 0
Total EPCs |  | 0 | 134.4137 | 0 | 134.4137 | 0

## Anx-L
LIST OF ASSETS
Re-Modelling and Up Gradation of ADA Nullah and Walton Road Pkg-I
Ser |  | Category of Asset | Purchase Cost (Rs) | Opening Dep of Assets | Monthly Depreciation | Depreciation Year to Date | Depreciation up to Date | Accum Dep of Assets from other Proj not booked to ADA Nullah | Asset's Value | Remarks
1 | Cement Mixers | Pd Cen P0421 Transit Mixer (Ma | 32280480 | 10300783.58 | 155884.3642 | 155884.3642 | 1870612.37 | 12171395.95 | 20109084.05
2 | Single cabins | Toyota Single Cabin LEG-17-2891 | 3374500 | 2502753.48 | 28120.825 | 28120.825 | 337449.9 | 2840203.38 | 534296.62
3 | Printers | Printers-HP IJ 125 SR # L9 X 8 | 20500 | 14520.18 | 170.825 | 170.825 | 2049.9 | 16570.08 | 3929.92
4 | Printers | Printer | 13000 | 7041.18 | 108.325 | 108.325 | 1299.9 | 8341.08 | 4658.92
5 | Printers | PRINTER | 18730 | 9988.86 | 156.075 | 156.075 | 1872.9 | 11861.76 | 6868.24
6 | Bikes | MOTOR BIKE | 63500 | 63499 | 0 | 0 | 0 | 63499 | 1 |  | 4120
7 | Bikes | Motor Bike Honda 70- | 68405 | 68404 | 0 | 0 | 0 | 68404 | 1
8 | Motor Pump | Motor Pump | 290000 | 234415.87 | 2416.6583 | 2416.6583 | 28999.9 | 263415.77 | 26584.23
9 | Printers | PRINTER BLACK LBP-2900B FOR SITE OFFICE | 16700 | 10993.52 | 139.1583 | 139.1583 | 1669.9 | 12663.42 | 4036.58
10 | Printers | PRINTER | 12500 | 6874.47 | 104.1583 | 104.1583 | 1249.9 | 8124.37 | 4375.63
11 | Printers | PRINTER | 12500 | 6874.47 | 104.1583 | 104.1583 | 1249.9 | 8124.37 | 4375.63
12 | Generators | GENERATOR | 1 | 0 | 0 | 0 | 0 | 0 | 1
13 | Testing and Lab Equipment | Tools & Equipment | 373500 | 308136.65 | 3112.4917 | 3112.4917 | 37349.9 | 345486.55 | 28013.45
14 | Fork Lifters | 45 Pole Lifter Machine | 211997 | 155463.69 | 1766.6333 | 1766.6333 | 21199.6 | 176663.29 | 35333.71
15 | Testing and Lab Equipment | TOTAL STATION -Nikon DTM-322+ (Sr # D330727) | 497350 | 356433.51 | 4144.575 | 4144.575 | 49734.9 | 406168.41 | 91181.59
16 | Generators | Pd C P0414 Gen Set 45 Kva | 106600 | 29482.52 | 430.8183 | 430.8183 | 5169.82 | 34652.34 | 71947.66
17 | Generators | Pd C P0400 Gen Set 60 Kva | 31342 | 31341 | 0 | 0 | 0 | 31341 | 1
18 | Motor graders | Pd Cen P0415 Motor Grader Mits | 264074.81 | 95726.76 | 1039.1792 | 1039.1792 | 12470.15 | 108196.91 | 155877.9
19 | Road Rollers - PTR | Pd Cen P0415 Road Roller Vib 1 | 1670835 | 1670834 | 0 | 0 | 0 | 1670834 | 1
20 | Tractors | Pd C P0400 Millat Tractor 4x4 | 2967387 | 1437372.88 | 10132.5367 | 10132.5367 | 121590.44 | 1558963.32 | 1408423.68
21 | Trolleys | Hyd Pripping Trolley with Pintle Hook | 471145 | 190041.21 | 3959.1925 | 3959.1925 | 47510.31 | 237551.52 | 233593.48
22 | Generators | Pd Cen P0341 Gen Set 100 Kva D | 1166666 | 475031.62 | 4295.8592 | 4295.8592 | 51550.31 | 526581.93 | 640084.07
23 | Cement Mixers | Pd Cen P0415 Transit Mixer (As | 10851172.66 | 5403094.03 | 38098.445 | 38098.445 | 457181.34 | 5860275.37 | 4990897.29
24 | Cranes | Pdc P0341 Crane Kato Sr 250 Ri | 25497570 | 9648908.87 | 96052.4858 | 96052.4858 | 1152629.83 | 10801538.7 | 14696031.3
25 | Excavators | Pdc P0411 Excavator Wheel Hita | 8419088 | 8419087 | 0 | 0 | 0 | 8419087 | 1
26 | Dump Trucks | Pdc P0341 Dump Trk Man Tgs Ww | 16382811 | 11405624.33 | 41825.0892 | 41825.0892 | 501901.07 | 11907525.4 | 4475285.6
27 | Cement Mixers | Transit Mixture 7619 | 16140240 | 6510348.48 | 135632.26 | 135632.26 | 1627587.12 | 8137935.6 | 8002304.4
28 | Generators | Gen Set 45 Kva Boos | 1545000 | 889318.43 | 4785.9892 | 4785.9892 | 57431.87 | 946750.3 | 598249.7
29 | Generators | Generator 3000 Watt | 56995 | 56994 | 0 | 0 | 0 | 56994 | 1
30 | Generators | Generator | 25300 | 25299 | 0 | 0 | 0 | 25299 | 1
31 | Generators | Generator | 67000 | 66999 | 0 | 0 | 0 | 66999 | 1
32 | Double cabins | Double Cabin - Hilux | 1036797 | 1036796 | 0 | 0 | 0 | 1036796 | 1
33 | Single cabins | Toyota Hilux 4x4 | 942603 | 942602 | 0 | 0 | 0 | 942602 | 1
34 | Bikes | 20x M/Cycle | 36500 | 36499 | 0 | 0 | 0 | 36499 | 1
35 | Printers | payment against purchase of printer | 12565 | 7120.16 | 209.4167 | 209.4167 | 2513 | 9633.16 | 2931.84
36 | Printers | payment against purchase of printer | 12565 | 7120.16 | 209.4167 | 209.4167 | 2513 | 9633.16 | 2931.84
37 | Batching Plants | Batching Plant 60 Cum | 16380000 | 1911000 | 68250 | 68250 | 819000 | 2730000 | 13650000
38 | Batching Plants | 70% Payment Batching Plant (HQ PD Sindh) IFO "Global Technologies | 17150000 | 4001666.68 | 142916.6667 | 142916.6667 | 1715000 | 5716666.68 | 11433333.32
39 | Batching Plants | 30% BALANCE PAYMENT OF 1 X BATCHING PLANT, 2 X CEMENT SILO, 1 X CEMENT SCREW AND | 19370000 | 4196833.38 | 161416.6667 | 161416.6667 | 1937000 | 6133833.38 | 13236166.62
40 | Trailors | PAYMENT AGAINST PURCHASE OF 1 X ISUZU TRUCK FOR PERI URBAN FSD SARGODHA PROJ PD | 3730000 | 854791.66 | 25902.7775 | 25902.7775 | 310833.33 | 1165624.99 | 2564375.01
41 | Porta Cabins | PORTA CABIN 8'X20' | 445026 | 114965.05 | 3708.55 | 3708.55 | 44502.6 | 159467.65 | 285558.35
42 | Porta Cabins | PORTA CABIN 8'X20' | 445026 | 114965.05 | 3708.55 | 3708.55 | 44502.6 | 159467.65 | 285558.35
43 | Tractors | Remaining payment against Supply of 14 x tractors along with attachments for PD | 2818720 | 203574.22 | 7829.7775 | 7829.7775 | 93957.33 | 297531.55 | 2521188.45
44 | Laptops | HP Pro Book 450 G8/ Intel Core i-5 /11th Gen/8 GB/512GB SSD PCIENVME/15.6 | 169785 | 79232.53 | 1414.865 | 1414.865 | 16978.38 | 96210.91 | 73574.09
45 | Tankers / Bowsers | Water Bowser 8000 L | 752688 | 144265.2 | 6272.4 | 6272.4 | 75268.8 | 219534 | 533154
46 | Motor Water Pump | Dewatering Pump (MT-6) with 50 HP Engine | 2775750 | 520777.49 | 23489.2967 | 23489.2967 | 281871.56 | 802649.05 | 1973100.95
47 | Motor Water Pump | Dewatering Pump (MT-6) with 50 HP Engine | 2350000 | 470000 | 19583.3333 | 19583.3333 | 235000 | 705000 | 1645000
48 | Motor Water Pump | Dewatering Pump (MT-6) with 50 HP Engine | 2350000 | 470000 | 19583.3333 | 19583.3333 | 235000 | 705000 | 1645000
49 | Motor Water Pump | Dewatering Pump (MT-6) with 50 HP Engine | 2350000 | 470000 | 19583.3333 | 19583.3333 | 235000 | 705000 | 1645000
| Motor Water Pump | Dewatering Pump (MT-6) with 50 HP Engine | 2350000 | 470000 | 19583.3333 | 19583.3333 | 235000 | 705000 | 1645000
| Motor Water Pump | Dewatering Pump (MT-10) with 75 HP Engine | 4750000 | 950000 | 39583.3333 | 39583.3333 | 475000 | 1425000 | 3325000
| Single cabins | Toyota Single cabin (8x proc) | 7505404 | 1375990.7 | 62545.0333 | 62545.0333 | 750540.4 | 2126531.1 | 5378872.9
| Printers | HP 4345 MFP Printer | 82600 | 11013.33 | 1376.6667 | 1376.6667 | 16520 | 27533.33 | 55066.67
| PCs | PC Dell Ci5 6th Generation 8GB RAM, 250 GB HD, 24 LED (All Accessories) | 66198 | 3861.55 | 551.65 | 551.65 | 6619.8 | 10481.35 | 55716.65
| PCs | PC Dell Ci5 6th Generation 8GB RAM, 250 GB HD, 24 LED (All Accessories) | 66198 | 3861.55 | 551.65 | 551.65 | 6619.8 | 10481.35 | 55716.65
| PCs | PC Dell Ci5 6th Generation 8GB RAM, 250 GB HD, 24 LED (All Accessories) | 55000 | 3208.33 | 458.3333 | 458.3333 | 5500 | 8708.33 | 46291.67
| PCs | PC Dell Ci5 6th Generation 8GB RAM, 250 GB HD, 24 LED (All Accessories) | 55000 | 3208.33 | 458.3333 | 458.3333 | 5500 | 8708.33 | 46291.67
| PCs | PC Dell Ci5 6th Generation 8GB RAM, 250 GB HD, 24 LED (All Accessories) | 55000 | 3208.33 | 458.3333 | 458.3333 | 5500 | 8708.33 | 46291.67
| Racks & Armoire | Steel Cabinet | 32000 | 1866.66 | 266.6667 | 266.6667 | 3200 | 5066.66 | 26933.34
| Racks & Armoire | Steel Cabinet | 32000 | 1866.66 | 266.6667 | 266.6667 | 3200 | 5066.66 | 26933.34
| Porta Cabins | Porta Cabin 10'x20'-P0468 | 1051408 | 61332.13 | 8761.7333 | 8761.7333 | 105140.8 | 166472.93 | 884935.07
| Porta Cabins | PORTA CABIN 10'X40'-P0468 | 1942144 | 113291.73 | 16184.5333 | 16184.5333 | 194214.4 | 307506.13 | 1634637.87
| Porta Cabins | Porta Cabin 10'x20'-P0468 | 1051407 | 61332.07 | 8761.725 | 8761.725 | 105140.7 | 166472.77 | 884934.23
| Deep-Freezer | Deep Freezer 70-155 | 117764 | 6869.56 | 981.3667 | 981.3667 | 11776.4 | 18645.96 | 99118.04
| Laptops | Laptop Normal/HP Pro Book 450 G9/ Intel Core i-5 /12th Gen/8 GB/512 SSD/15.6" FH | 268275 | 40241.07 | 4471.2333 | 4471.2333 | 53654.8 | 93895.87 | 174379.13
| Photocopy Machine | Photocopier Ricoh MP 301 | 67924 | 3962.23 | 566.0333 | 566.0333 | 6792.4 | 10754.63 | 57169.37
| PCs | Dell 7050 Tower ,Ci-7th Gen 7700 | 134375 | 7838.54 | 1119.7917 | 1119.7917 | 13437.5 | 21276.04 | 113098.96
| Air Conditioner | AC 1.5 Ton (CHIQ) | 179901 | 10494.22 | 1499.175 | 1499.175 | 17990.1 | 28484.32 | 151416.68
| Air Conditioner | AC 1 Ton (Haier) | 152201 | 8878.39 | 1268.3417 | 1268.3417 | 15220.1 | 24098.49 | 128102.51
| Air Conditioner | AC 1.5 Ton (CHIQ) | 179901 | 10494.22 | 1499.175 | 1499.175 | 17990.1 | 28484.32 | 151416.68
| PCs | PC Dell Ci5 6th Generation 8GB RAM, 250 GB HD, 24 LED (All Accessories) | 55000 | 3208.33 | 458.3333 | 458.3333 | 5500 | 8708.33 | 46291.67
| PCs | PC Dell Ci5 6th Generation 8GB RAM, 250 GB HD, 24 LED (All Accessories) | 55000 | 3208.33 | 458.3333 | 458.3333 | 5500 | 8708.33 | 46291.67
| PCs | PC Dell Ci5 6th Generation 8GB RAM, 250 GB HD, 24 LED (All Accessories) | 55000 | 3208.33 | 458.3333 | 458.3333 | 5500 | 8708.33 | 46291.67
| PCs | PC Dell Ci5 6th Generation 8GB RAM, 250 GB HD, 24 LED (All Accessories) | 55000 | 3208.33 | 458.3333 | 458.3333 | 5500 | 8708.33 | 46291.67
| PCs | PC Dell Ci5 6th Generation 8GB RAM, 250 GB HD, 24 LED (All Accessories) | 55000 | 3208.33 | 458.3333 | 458.3333 | 5500 | 8708.33 | 46291.67
| PCs | PC Dell Ci5 6th Generation 8GB RAM, 250 GB HD, 24 LED (All Accessories) | 55000 | 3208.33 | 458.3333 | 458.3333 | 5500 | 8708.33 | 46291.67
| PCs | PC Dell Ci5 6th Generation 8GB RAM, 250 GB HD, 24 LED (All Accessories) | 55000 | 3208.33 | 458.3333 | 458.3333 | 5500 | 8708.33 | 46291.67
| Printers | HP 4345 MFP Printer | 29639 | 3457.88 | 493.9833 | 493.9833 | 5927.8 | 9385.68 | 20253.32
| Printers | HP 4345 MFP Printer | 29639 | 3457.88 | 493.9833 | 493.9833 | 5927.8 | 9385.68 | 20253.32
| PCs | PC-HP Pavilion 10th Gen Ram 8 GB , HD 256 GB ,I3 Processor with All Accessories | 127968.75 | 6398.43 | 1066.4058 | 1066.4058 | 12796.87 | 19195.3 | 108773.45
| PCs | PC-HP Pavilion 10th Gen Ram 8 GB , HD 256 GB ,I3 Processor with All Accessories | 127968.75 | 6398.43 | 1066.4058 | 1066.4058 | 12796.87 | 19195.3 | 108773.45
[5 empty] | 499500 | 499500 | 5994000
|  |  |  | 79.1789 | 1.7136 | 1.7136 | 20.5632 | 93.7481 | 123.1917

## Anx-M
Anx "M"
MONTH - MAR, 2024
DETAILS OF LIABILITIES
Re-Modelling and Up Gradation of ADA Nullah and Walton Road Pkg-I
1 | Against Contractor/Supplier |  |  |  | Amount (M)
|  | a. | Payable to contrs ( VWD) | - | 584.1168
|  | a. | Payable against Un Vetted Work Done | 0
|  | b. | Vetted Laib contr | 0
|  | b. | Rentention Money Payable | 0 | 295.1871
|  | c. | Performance Guarantee | 0 | 72.9122
|  | d. | Const Mat | 0
|  | e. | Utilities | 0
f.
|  |  | Sub Total | 0 | 952.2162
2 | Other Payables
|  | a. | Payable against Mob Adv received from Client | 0 | #REF! | #REF!
|  | b. | Payable against Sec Adv received from Client | 0 | #REF! | #REF!
|  | c. | Payable against Hiring Charges | 0
|  |  | Sub Total | 0 | #REF!
|  |  | Grand Total | 0 | #REF!

## Anx-N
Anx "N"
MONTH - MAR, 2024
BUDGETING OF PROJECT
Re-Modelling and Up Gradation of ADA Nullah and Walton Road Pkg-I
Total Expenditure as per Exec Plan |  | 322.1435 | Million
Already Expended Amount Uptodate |  | 2243.6945 | Million
Work Done Uptodate |  | 2353.6485 | Million
Bal Amount to be Expended |  | -1921.551 | Million
Bal Work Done to be Done |  | 7220.2775 | Million |  |  | Rs. In Million
Ser | Description | Exp as per Exec Plan | Already Expended |  | Exp on Bal Work
|  |  | Amount In Million | %age | Amount In Million | %age
Work Expenditures
1 | Stores
| Const Mat & EQPT |  | 0 | #DIV/0! | 0 | #DIV/0!
| Engr Facility |  |  | #DIV/0! | 0 | #DIV/0!
2 | Sub Contr Cost | 5696.77 | 1956.841 | 34.35% | 3739.929 | 65.65%
3 | Plants and Machinery |  |  | #DIV/0! | 0 | #DIV/0!
| a. Hiring Charges / POL |  |  | #DIV/0! | 0 | #DIV/0!
| b. Repair/ Maint |  |  | #DIV/0! | 0 | #DIV/0!
| Lab test |  |  | #DIV/0! | 0 | #DIV/0!
4 | Direct Labour |  |  | #DIV/0! | 0 | #DIV/0!
| Self Execution | 2455.83 | 0 | 0% | 2455.83 | 100%
| b. Salaries Civilian Personals |  |  | #DIV/0! | 0 | #DIV/0!
| d. PC Bills |  |  | #DIV/0! | 0 | #DIV/0!
5 | Any Other |  |  | #DIV/0! | 0 | #DIV/0!
| a. Depreciation against FA | 0 | 2.3491 | #DIV/0! | -2.3491 | #DIV/0!
| b. Expense against rent |  |  | #DIV/0! | 0 | #DIV/0!
| c. Proj Maint cost | 95.7393 | 23.7388 | 24.8% | 72.0005 | 75.2%
| Total Work Expenditure | 8248.3393 | 1982.9288
Overhead Expenditures
a. | Salary | 116.3104 | 35.978 | 30.93% | 80.3324 | 69.07%
b. | POL | 56.3306 | 0.859 | 1.525% | 55.4716 | 98.48%
c. | Utilities - Electricity | 18.3904 | 0 | 0% | 18.3904 | 100%
d. | Utilities - Water | 0.15465 | 0 | 0% | 0.15465 | 100%
e. | Utilities - Telephone/ Mob | 1.0219 | 0 | 0% | 1.0219 | 100%
f. | Utilities - Internet | 0.5775 | 0 | 0% | 0.5775 | 100%
g. | Utilities - Gas/LPG | 0.79826 | 0.107 | 13.4% | 0.69126 | 86.6%
h. | Postage & Courier | 0.30334 | 0 | 0% | 0.30334 | 100%
i. | Entertainment | 3.9913 | 0.877 | 21.97% | 3.1143 | 78.03%
j. | Printing & Stationery | 4.6299 | 0.924 | 19.96% | 3.7059 | 80.04%
k. | Carriage & Freight Charges | 2.3948 | 1.665 | 69.53% | 0.72979 | 30.47%
l. | Legal Expenses | 0 | 0 | #DIV/0! | 0 | #DIV/0!
m. | Office Contingencies | 7.9826 | 8.7718 | 109.9% | -0.78916 | -9.886%
n. | Spare | 0.77326 | 0 | 0% | 0.77326 | 100%
o. | Office Eqpts | 3.672 | 0 | 0% | 3.672 | 100%
p. | Furniture & Fixture | 4.9958 | 0 | 0% | 4.9958 | 100%
q. | Medicine | 0.31931 | 0.004 | 1.253% | 0.31531 | 98.75%
r. | Repair - Vehs | 9.7128 | 0.385 | 3.964% | 9.3278 | 96.04%
s. | Repair - Furniture | 3.8663 | 0.0884 | 2.286% | 3.7779 | 97.71%
t. | Repair - Computer & Eqpt | 2.5655 | 0.934 | 36.41% | 1.6315 | 63.59%
u. | Repair - Other | 6.6987 | 0.76 | 11.35% | 5.9387 | 88.65%
v. | Gifts/ Souvenirs | 0 | 0 | #DIV/0! | 0 | #DIV/0!
w. | Lab Estab/ Testing Equipment | 6.9575 | 0 | 0% | 6.9575 | 100%
x. | Insurance 0.25% of Project Cost | 4.7872 | 0 | 0% | 4.7872 | 100%
y. | Sports/ CSR | 0 | 0 | #DIV/0! | 0 | #DIV/0!
z. | Welfare/ Charity Donations | 0.30334 | 0 | 0% | 0.30334 | 100%
aa. | Funeral Charges | 0 |  | #DIV/0! | 0 | #DIV/0!
bb. | Cash awards - NLC Staff | 0.643 | 0 | 0% | 0.643 | 100%
cc. | TA/ DA Expenditure | 0.25 | 0 | 0% | 0.25 | 100%
dd. | Toll Taxes - Parking Tickets | 0.35 | 0 | 0% | 0.35 | 100%
ee. | Newpapers & Periodicals | 0.030931 | 0 | 0% | 0.030931 | 100%
ff. | Fin Charges | 0.047896 | 0 | 0% | 0.047896 | 100%
gg. | Hiring of Site Accomodations | 12.7 | 0 | 0% | 12.7 | 100%
hh. | Batching Plant - Running Exp | 23.5842 |  | 0% | 23.5842 | 100%
jj. | Water Facility - Camp Site | 4 | 0.2192 | 5.48% | 3.7808 | 94.52%
kk. | Site Establishment Charges | 23 | 0.2192 | 0.953% | 22.7808 | 99.05%
| Total | 322.1435 | 51.7916
| Total Expected Revenue Incl Claims / VOs |  | 9573.93
| Total Expected Expenditure on Completion |  | 7769.6428
| PST |  | 478.696
| OH Expense |  | 322.1435
| Other Income |  | 0
| Total Exp |  | 8570.4823
| Net Profit / (Loss) |  | 1003.4477
| Net Profit %age |  | 10.48%

## Anx-O
DETAIL OF RECOVERIES FROM SUBCONTRACTORS
#REF!
Ser | Activity | Amount in Rs
|  | During the Month | Total up to Date | Running Total YTD | Chq Nos | Chq Amount
1 | Bank Profit Received | 0 | 0.077946 | 0
2 | Handling Charges recoverd from Contr at Mat | 0 | 50.1392 | 0
3 | Hiring Recovery | 0 | 8.4569 | 0
4 | POL Recovery | -4.966 | 31.535 | -4.966
5 | Lab Test | 0 | 0.58098 | 0
6 | Misc Recovery | 0 | 1.183 | 0
7 | Safty | 0 | 0.981 | 0
8 | Other | 0 | 10.871 | 0
9 | RBC Receovery of Machinery/Lying of Asphalt | -4.5 | 0 | -4.5
| Total (Rs in Million) | -9.466 | 103.8249 | -9.466 |  | 0
113.2909
-9.466

## Anx-Q
Anx "Q"
MONTH - MAR, 2024
DETAIL OF ASPHALT EXECUTED AT SITE
Re-Modelling and Up Gradation of ADA Nullah and Walton Road Pkg-I
FROM NIL TO NIL
Ser | Date | Location | Side | Rd |  | Asphalt Qty (Ton) | Remarks
|  |  |  | From | to
- | - | - | - | - | - | - | -
- | - | - | - | - | - | - | -
- | - | - | - | - | - | - | -
- | - | - | - | - | - | - | -
Total | [5 empty] | 0
Cost
| Rate as per Asphalt Plt Bill (Avg Rate) |  |  |  | Rs. | 0
| Total Cost |  |  |  | Rs. | 0
| Actual Cost to be booked |  |  |  | Rs. | 0
| Bill received from PM Asphalt Plt & already booked as Cost |  |  |  | Rs. | 0
[5 empty] | Rs. | 0
Revenue
| Client Rate incl 10% Preminum (Avg Rate) |  |  |  | Rs. | 0
| Total Cost |  |  |  | Rs. | 0
| Reversal of own WD ABC & AWC |  |  |  | Rs. | 0
| Revenue booked 2 |  |  |  | Rs. | 0
| Net Value of Revenue |  |  |  | Rs. | 0

## Anx-R
Anx "R"
MONTH - MAR, 2024
PROJ CON LHR ENGRS NLC
DETAIL OF ASPHALT WORKS
S. No | Site / Pkg | BQ Qty (to be converted in Tons) |  | Demand Placed to PM Asphalt (Tons) |  | Qty Received (Tons) |  | Claimed in IPC (Tons) |  | Paid by Client (Tons) |  | *With held by Client against Claimed Qty (Tons) |  | Qty pending due to core test (Tons) |  | Esclation Claimed (M) |  | Esclation to be claimed (M) |  | Payment made to PM Asphalt by PM Proj (M) | Bal Payment based on Asphalt provided by PM Asphalt (M)
|  | ABC | AWC | ABC | AWC | ABC | AWC | ABC | AWC | ABC | AWC | ABC | AWC | ABC | AWC | ABC | AWC | ABC | AWC
1 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
2 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -

## Appendix
Appx I to Anx "A"
Re-Modelling and Up Gradation of ADA Nullah and Walton Road Pkg-I
CA Amount (As per Ltr of Award) |  | 9573.926 |  | Revised CA Amount Addl Work
Re-revise Approx Co,pletion Cost : 10395.1 |  | 9900
Start Date (As per Ltr of Award) |  | 2023-10-16 |  | Completion Date (As per Ltr of Award) |  | 2025-04-08
Month | During the Month |  | Progressive (Upto Date) |  | Upto Date Progress %
| Planned | Achieved | Planned | Achieved | Planned | Achieved
2023-10-01 | 11.511 | 11.511 | 11.511 | 11.511 | 0.1202% | 0.1202%
2023-11-01 | 56.435 | 56.435 | 67.946 | 67.946 | 0.7097% | 0.7097%
2023-12-01 | 55.058 | 55.058 | 123.004 | 123.004 | 1.285% | 1.285%
2024-01-01 | 312.707 | 312.707 | 435.711 | 455.015 | 4.551% | 4.753%
2024-02-01 | 1132.258 | 1132.258 | 1567.969 | 1587.273 | 16.38% | 16.58%
2024-03-01 | 766.38 | 766.376 | 2334.349 | 2353.649 | 24.38% | 24.58%
2024-04-01 | 464.48 | 464.484 | 2798.829 | 2818.133 | 29.23% | 29.44%
2024-05-01 | 1278.54 | 1278.538 | 4077.369 | 4096.671 | 42.59% | 42.79%
2024-06-01 | 566.75 | 566.751 | 4644.119 | 4663.422 | 48.51% | 48.71%
2024-07-01 | 820.07 | 820.071 | 5464.189 | 5483.493 | 57.07% | 57.28%
2024-08-01 | 408.55 | 408.55 | 5872.739 | 5892.043 | 61.34% | 61.54%
2024-09-01 | 449.82 | 449.82 | 6322.559 | 6341.863 | 66.04% | 66.24%
2024-10-01 | 308.39 | 308.393 | 6630.949 | 6650.256 | 69.26% | 69.46%
2024-11-01 | 260.65 | 260.649 | 6891.599 | 6911.4076 | 71.98% | 72.19% | 37.4955 | 9571.3756
2024-12-01 | 205.01 | 209.7428 | 7096.609 | 7120.1148 | 74.12% | 74.37% |  | 9533.8803
2025-01-01 | 350.95 | 350.9478 | 7447.559 | 7471.5652 | 77.79% | 78.04% |  | 37.4953
2025-02-01 | 535.59 | 535.5945 | 7983.149 | 8007.6623 | 83.38% | 80.89% |  | -0.0002247
2025-03-01 | 387.8 | 387.8 | 8370.949 | 8395.4623 | 84.56% | 84.8% | 9900
2025-04-01 | 583.2 | 583.2 | 8954.149 | 8978.6623 | 90.45% | 90.69% | 0.001
2025-05-01 | 265.56 | 265.563 | 9219.709 | 9244.2253 | 93.13% | 93.38%
2025-06-01 | 289.66 | 289.655 | 9509.369 | 9533.8803 | 96.05% | 96.3%
2025-07-01 | 390.63 | 37.4955 | 9899.999 | 9571.3758 | 100% | 96.68%
9900
0.001

## S Curve
PROJ HIGHLIGHTS AS ON JUL-25
Re-Modelling and Up Gradation of ADA Nullah and Walton Road Pkg-I | [20 empty] | 37.4955 | Month
S CURVE | [20 empty] | 9571.3756 | UTD
MONTHLY
Description | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01
Planned | 0 | 16.652 | 95 | 262 | 350 | 400 | 430 | 450 | 550 | 600 | 630 | 650 | 750 | 750 | 750 | 850 | 650 | 750 | 350 | 290.27 | 265.56 | 289.66 | 390.63
Achived | 0 | 11.511 | 56.435 | 55.058 | 373.652 | 1132.26 | 766.376 | 464.484 | 1278.538 | 566.751 | 820.071 | 408.55 | 449.82 | 308.393 | 260.649 | 209.7428 | 350.9478 | 535.595 | 387.8 | 583.2 | 265.563 | 289.655 | 37.4955
UTD PROGRESS
Description | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01
Planned | 0 | 16.652 | 111.652 | 373.652 | 723.652 | 1123.652 | 1553.652 | 2003.652 | 2553.652 | 3153.652 | 3783.652 | 4433.652 | 5183.652 | 5933.652 | 6683.652 | 7533.652 | 8183.652 | 8933.652 | 8370.949 | 8954.149 | 9219.709 | 9509.369 | 9899.999
Achived | 0 | 11.511 | 67.946 | 123.004 | 455.015 | 1587.273 | 2353.649 | 2818.133 | 4096.671 | 4663.422 | 5483.493 | 5892.044 | 6341.863 | 6650.256 | 6911.4076 | 7120.1148 | 7471.5652 | 8007.6623 | 8395.4623 | 8978.6623 | 9244.2253 | 9533.8803 | 9899.999
S