## Anx E (3) (hidden)
Detail of Payments to Sub-Contractors
Project Control:- Mandra Chakwal Road Project
Project:- Dualization and improvement of Mandra - Chakwal Road Project
SNo | CA No | Contractor | NLC CA Amount | Sub Cont CA Amount | Upto Date
[5 empty] | Sub Contractor's Work Done | 30% retained amount | Retention Money | Payments | Payments against Secured advance & Mob Adv
1 |  | #REF! | 550.343 | 498.595 | 227.5104 | 27.4786 | 10.0016 | 211.2141 | 17.2362 |  | #REF! | 200.0318 | 10.0016 | 15.0024 | 175.0278 | 36.1862
2 |  | #REF! | 227.453 | 205.477 | 70.745 | 5.0018 | 3.2872 | 56.8505 | 2.7251 |  | #REF! | 65.7433 | 3.2872 | 4.9307 | 57.5254 | -0.67487
3 |  | M/s Ajj Engineers | 113.73 | 102.74 | 79.1648 | 9.2817 | 3.4942 | 91.2487 | 23.6578 |  | #REF! | 69.8832 | 3.4942 | 5.2412 | 61.1478 | 30.1009
4 |  | M/s Valley Homes | 553.79 | 468.1 | 16.996 | 0.29047 | 0.83528 | 11.1112 | 43.2992 |  | #REF! | 16.7056 | 0.83528 | 1.2529 | 14.6174 | -3.5062
5 |  | M/s Shahid Builders | 113.73 | 102.74 | 21.5992 | 0.093653 | 1.0753 | 19.8629 | 1.7045 |  | #REF! | 21.5055 | 1.0753 | 1.6129 | 18.8173 | 1.0455
6 |  | M/s Karim Baksh ((MCRP/12/2015/PDN/NLC) | 4.833 | 3.585 | 3.701 |  | 0.18505 | 3.2 |  | closed | -0.11598 | -3.701
7 |  | M/s Hammad Bros (MCRP/13/2015/PDN/NLC) | 12.985 | 9.783 | 1.3936 |  | 0.069679 | 1.03 |  |  | #REF!
8 |  | M/s Hammad Bros (MCRP/24/2015/PDN/NLC) | 1.9045 | 1.9045 | 2.2396 |  | 0.11198 | 1.82 |  | closed | #REF!
9 |  | M/s Mehmood Khan-Culvert (MCRP/19/2015/PD) | 16.883 | 12.966 | 2.0665 |  | 0.10332 | 1.8082 |  |  | #REF!
10 |  | M/s Mehmood Khan-Earthwork (MCRP/18/2015/PD) | 10.5964 | 8.7654 | 9.2474 |  | 0.46237 | 7.94 |  |  | #REF!
11 |  | M/s Muhammad Zada(MCRP/14/2015/PD) | 17.209 | 12.966 | 0.9669 |  | 0.048345 | 0.7 |  |  | #REF!
12 |  | M/s Karim Baksh & Sons(MCRP/38/2015/PD) | 24.6148 | 24.6148 | 7.6907 |  | 0.38454 | 6.5647 |  |  | #REF!
13 |  | M/s Mehmood Khan & Co (CA-25/2015) | 18.2086 | 14.9109 | 0.64858 |  | 0.032429 | 0.56751 |  |  | #REF!
14 |  | M/s Hammad Brothers (CA-23/2015) | 2.3638 | 1.8069 | 0.30189 |  | 0.015094 | 0.2 |  |  | #REF!
15 |  | M/S Karim Bukhsh Son(CA-29(A)/2015) | 2.835 | 2.835 | 3.24 |  | 0.162 | 2.79 |  |  | #REF!
16 |  | M/s Muhammad Roz & Sons(CA-36/2015) | 12.8222 | 9.6327 | 2.0012 |  | 0.10006 | 1.7 |  |  | #REF!
17 |  | M/s Mehmood Khan & Co (CA-42/2015) | 20.9552 | 17.4409 | 4.9848 |  | 0.24924 | 2.5 |  |  | #REF!
18 |  | M/s Mehmood Khan & Co (CA-43/2015) | 21.0853 | 19.6093 | 0 |  | 0 | 0 |  |  | #REF!
19 |  | M/s Mehmood Khan & Co (CA-46/2015) | 4.4426 | 4.4426 | 0.24754 |  | 0.012377 | 0.21659 |  |  | #REF!
|  |  | 1730.7842 | 1522.9149 | 454.7451 | 42.1462 | 20.6299 | 421.3243 | 88.6229 |  | 391.969 | 412.599 | 102.1%
[10 empty] | 412.599 |  | 391.969 | 107.5%
1.0211
0
0
|  |  | 13 | 0 | #REF! |  | #REF!
[5 empty] | #REF! |  | #REF!
0
|  |  | 18 | 0 | #REF! |  | #REF!
#REF!
|  |  | 20 | 0 | #REF! |  | #REF!
#REF!
0
|  |  | 9 |  |  |  | #REF!
#REF!
#REF!
|  |  |  | 0 | #REF!
43 | FHA/TMPR/40/11/PD(N)NLC
[5 empty] | #REF! |  | #REF!
|  |  |  | 0 | #REF! |  | #REF!

## Anx E (2) (hidden)
Detail of Payments to Sub-Contractors (Provisional)
Project Control:- Mandra Chakwal Road Project
Project:- Dualization and improvement of Mandra - Chakwal Road Project
SNo | CA No | Contractor | NLC CA Amount | Sub Cont CA Amount | Upto Date
[5 empty] | Sub Contractor's Work Done | Retention Money | Payments against Work done | Payments against Secured advance & Mob Adv
1 |  | #REF! | 550.343 | 498.595 | 259.8876 | 12.9944 | 193.98 | 17.2362 |  | #REF!
2 |  | #REF! | 227.453 | 205.477 | 75.3357 | 3.7668 | 54.1254 | 2.7251 |  | #REF!
3 |  | M/s Ajj Engineers | 113.73 | 102.74 | 79.1648 | 3.9582 | 67.5909 | 23.6578 |  | #REF!
4 |  | M/s Valley Homes | 553.79 | 468.1 | 50.3902 | 2.5195 | 11.1112 | 43.2992 |  | #REF!
5 |  | M/s Shahid Builders | 113.73 | 102.74 | 37.9628 | 1.8981 | 18.1583 | 1.7045 |  | #REF!
6 |  | M/s Karim Baksh ((MCRP/12/2015/PDN/NLC) | 4.833 | 3.585 | 3.817 | 0.19085 | 3.2 |  | closed | -0.11598 | -3.817
7 |  | M/s Hammad Bros (MCRP/13/2015/PDN/NLC) | 12.985 | 9.783 | 3.2217 | 0.16109 | 1.03 |  |  | #REF!
8 |  | M/s Hammad Bros (MCRP/24/2015/PDN/NLC) | 1.9045 | 1.9045 | 2.2396 | 0.11198 | 1.82 |  | closed | #REF!
9 |  | M/s Mehmood Khan-Culvert (MCRP/19/2015/PD) | 16.883 | 12.966 | 2.462 | 0.1231 | 1.8082 |  |  | #REF!
10 |  | M/s Mehmood Khan-Earthwork (MCRP/18/2015/PD) | 10.5964 | 8.7654 | 9.2474 | 0.46237 | 7.94 |  |  | #REF!
11 |  | M/s Muhammad Zada(MCRP/14/2015/PD) | 17.209 | 12.966 | 1.7088 | 0.085439 | 0.7 |  |  | #REF!
12 |  | M/s Karim Baksh & Sons(MCRP/38/2015/PD) | 24.6148 | 24.6148 | 7.6907 | 0.38454 | 6.5647 |  |  | #REF!
13 |  | M/s Mehmood Khan & Co (CA-25/2015) | 18.2086 | 14.9109 | 0.64858 | 0.032429 | 0.56751 |  |  | #REF!
14 |  | M/s Hammad Brothers (CA-23/2015) | 2.3638 | 1.8069 | 0.30189 | 0.015094 | 0.2 |  |  | #REF!
15 |  | M/S Karim Bukhsh Son(CA-29(A)/2015) | 2.835 | 2.835 | 3.24 | 0.162 | 2.79 |  |  | #REF!
16 |  | M/s Muhammad Roz & Sons(CA-36/2015) | 12.8222 | 9.6327 | 3.3766 | 0.16883 | 1.7 |  |  | #REF!
17 |  | M/s Mehmood Khan & Co (CA-42/2015) | 20.9552 | 17.4409 | 4.9848 | 0.24924 | 2.5 |  |  | #REF!
18 |  | M/s Mehmood Khan & Co (CA-43/2015) | 21.0853 | 19.6093 | 0 | 0 |  |  |  | #REF!
19 |  | M/s Mehmood Khan & Co (CA-46/2015) | 4.4426 | 4.4426 | 0.34171 | 0.017086 | 0.21659 |  |  | #REF!
|  |  | 1730.7842 | 1522.9149 | 546.0218 | 27.3011 | 376.0028 | 88.6229
0
0
|  |  | 13 | 0 | #REF! | #REF!
[5 empty] | #REF! | #REF!
0
|  |  | 18 | 0 | #REF! | #REF!
#REF!
|  |  | 20 | 0 | #REF! | #REF!
#REF!
0
|  |  | 9 |  |  | #REF!
#REF!
#REF!
|  |  |  | 0 | #REF!
43 | FHA/TMPR/40/11/PD(N)NLC
[5 empty] | #REF! | #REF!
|  |  |  | 0 | #REF! | #REF!

## Anx A
Anx "A"
Project Highlight as on 31st Jul 2025
Project Control Unit:- Dev of C-15 Islamabad
1 | Schedule of Project
| a. | Date of Commencement |  |  |  |  | 2022-10-03
| b. | Date of Completion |  |  |  |  | 2024-04-03
| c. | 1st EOT |  |  |  |  | 2024-12-15
2 | Salient Features of Proj
| a. | Dev of infrastructure and earthwork
3 | Client/Consultant |  |  |  |  | Capital Development Authority
4 | Progress
| Work Done |  |  | Rs (Million) |  |  | %age
|  | (1) Achieved as per cost |  |  |  |  | 18.3%
5 | Financial State | [5 empty] | Rs (Million)
| a. | Original CA Amount |  |  |  |  | 1587.04 | [5 empty] | 1587040000
| b. | Total Funds Received from PL-1 account against Cash Reqn |  |  |  |  | 1.58
6 | Expenditure Statement
|  |  | Work Done |  |  | Vetted |  | #REF!
|  |  | During The Month | Year to Date | Up to Date | Up to Date | Year to Date | 536.2118 | #REF!
|  | Revenue | 0 | 0 | 333.556 | 333.56 | 0 | 0 |  |  |  |  | 333556000
|  | Escalation |  | 0 | 0 | 0 | 0 | 3.4083 | 0 | 359033 | 0.35903 | 0
|  | De Escalation | 0 | 0 | 0 | 0 | 0 | 1099.3895
|  | Total Revenue | 0 | 0 | 333.556 | 333.56 | 0
|  | Direct Cost | 0.535 | 0.54 | 293.307 | 293.307 | 0.54
|  | Gross Profit/(Loss) | -0.535 | -0.54 | 40.249 | 40.253 | -0.54 | -3.892
|  | Gen & Adm Exp | 0 | 0 | 0 | 0 | 0
|  | Operating Profit/(Loss) | -0.535 | -0.54 | 40.249 | 40.253 | -0.54
|  | Financial Charges | 0 | 0 | 0 | 0 | 0
|  | Other Income | 0 | 0 | 0 | 0 | 0
|  | Net Profit/(Loss) (Million) | -0.535 | -0.54 | 40.249 | 40.253 | -0.54
|  | Net Profit/(Loss) % Age |  |  | 12.07% | 12.07%
7 | Remarks of SPM

## Anx B
Anx "B"
Detail of Work Self Exec Done By NLC /Hired Labour
Project Control Unit:- Dev of C-15 Islamabad
Bill # | Activity | Amount Rs in Million
|  | CA Amount | Work Done During the Month | Workdone up to Date | Workdone Year to Date | Vetted Workdone up to Date | Vetted Workdone Year to Date
1 | - | 0 | 0 | 0 | 0 | 0 | 0
| Grand Total Amount | 0 | 0 | 0 | 0 | 0 | 0

## Anx C
Detail of Work Done By Sub Contractors | [9 empty] | Anx "C"
Project Control Unit:- Dev of C-15 Islamabad
Ser | Contractor | Amount Rs in Million | [7 empty] | Remarks
|  | NLC's CA Amount | Sub Cont CA Amount | Profit % | Work Done During the Month | Runing Total Upto Date | Running Total YTD | Vetted Work Done up to Date | Vetted Work Done Year to Date
1 | M/S Karsaz (CA No. C-15/68/2023/PDN/NLC) | 633.05 | 497.06 | 21.48 | 0 | 333.556 | 0 | 0 | 0
| Total | 633.05 | 497.06 |  | 0 | 333.556 | 0 | 0

## Anx D (2) (hidden)
Detail of Expenditures
Project Control:- Mandra Chakwal Road Project
Project:- Dualization and improvement of Mandra - Chakwal Road Project
Ser | Head of A/c
Year to Date
Work Expenditures | [6 empty] | Expenses | For the month | Upto Date
| a. Salaries | 17.78 | 0.064063 | 1.778e-05 | #REF! | 17780000 |  |  |  | #REF!
| b.Bore expense | 1 |  |  |  | 1000000 |  |  |  | #REF!
5 | Non productive | 0 | 0 | 0 | #REF! | 0
| a. Depreciation against FA Ref Anx L | #REF! | 0 | #REF! | #REF! | #REF!
| b. Innaguration expenses | 4.7 |  | 4.7e-06 |  | 4700000 |  |  |  | #REF!
| c. Sign boards | 0.44397 |  |  |  | 443973 | 0.44397 | 0 |  | #REF! | 11890
| d. Repair & maintainance | 3.8392 | 1.7439 |  | #REF! | 3839154 | 3.8392 | 0
| Total Expenditure | #REF!

## Anx D
Anex"D"
Detail of Expenditures
Project Control Unit:- Dev of C-15 Islamabad
Ser | Head of A/c | EXPENDITURE |  |  | Remarks
|  | During Month | Upto Date | Year to date
Work Expenditures
1 | Stores Consumed / purchased | 0 | 0 | 0
2 | Sub Contractor Cost | 0 | 261.908 | 0 |  | 272.987
3 | Hiring of Plt / Eqpt / Mach |  |  |  |  | 272987000
POL
Hiring charges
4 | Salary and Benefits
| Salary Civs / Army persons | 0.51 | 12.516 | 0.51 |  | 20.32
5 | Any Other |  |  |  |  | 20320000
| a. Insurance | 0 | 7.804 | 0
| b. Client Exp | 0.025 | 11.079 | 0.03
| Total Expenditure | 0.535 | 293.307 | 0.54
293307000

## Anx E
Anx "E"
Detail of Payments to Sub-Contractors
Project Control Unit:- Dev of C-15 Islamabad
SNo | CA No | Contractor | NLC CA Amount | Sub Cont CA Amount | During the Month |  |  |  |  | Upto Date |  |  |  | Year to Date |  |  |  | Remarks
[5 empty] | Sub Contractor's Work Done | Stores Issued (if any) | Retention Money | Incom Tax 7.5% | Net Payment Due | Sub Contractor's Work Done | Retention Money | Income Tax | Net Payment Due before recovery | Sub Contractor's Work Done | Retention Money | Income Tax 7.5% | Net Payment Due
1 |  | M/S Karsaz (CA No. C-15/68/2023/PDN/NLC) | 633.05 | 497.06 | 0 | 0 | 0 | 0 | 0 | 261.908 | 0 | 0 | 261.908 | 0 | 0 | 0 | 0
|  | G. Total |  |  | 0 | 0 | 0 | 0 | 0 | 261.908 | 0 | 0 | 261.908 | 0 | 0 | 0 | 0 |  | 221775361
#REF!
0
0
|  |  | 13 | 0 | 120258 |  | 12026 |  |  | 108232 | #REF!
[5 empty] | 120258 |  | 12026 |  |  | 108232 | #REF!
0
|  |  | 18 | 0 | 0 |  | 0 | 0 | 0 | 0 | #REF! | 1693981 | PV 32, 29-08-11
#REF!
|  |  | 20 | 0 | 0 |  | 0 | 0 | 0 | 0 | #REF! | 1693980 | PV 31,29-08-11
#REF!
0
PV 20, 18-08-11
|  |  | 9 |  | 0 |  | 0 | 0 | 0 |  | #REF! | 1693982 | PV-33,29-08-11
#REF!
[10 empty] | 0 |  |  | PV 18, 18-08-11
|  |  |  | 0 | [5 empty] | 0
43 | FHA/TMPR/40/11/PD(N)NLC
[5 empty] | 2030560 |  | 203056 |  |  | 1827504 | #REF! | 1693977 | PV 23, 22-08-11
|  |  |  | 0 | 2030560 |  | 203056 |  |  | 1827504 | #REF!

## Anx F
Anx "F"
Detail of Payments to Sub-Contractors | [11 empty] | Anx-"F"
Project Control Unit:- Dev of C-15 Islamabad
SNo | Contractor | RAR No | Work Done | R.Money | Misc Recovery / POL | Store Issued | Gross Payable | I.Tax | Paid | Less / (Over) Paid | Chq. # | Date
1 | M/s Karsaz Engr Pvt Ltd (C-15/68/2023/PDN/NLC) | RAR # 1(1) | 89904398 | 4495220 | 793358 | 449522 | 84166298 | 5594594.6 | 20000000 | 58571703.4 | 00744218 | 2023-07-27 | Audited | 5594594.6 | 100%
|  | RAR # 1(2) | 0 | 0 | 0 | 0 | 0 | 0 | 14000000 | 44571703.4 | 00744220 | 2023-08-02
|  | RAR # 1(3) | 0 | 0 | 0 | 0 | 0 | 0 | 15000000 | 29571703.4 | 00745880 | 2023-08-18
|  | RAR # 1(4) | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 19571703.4 | 00776742 | 2023-12-04
|  | RAR # 1(5) | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 9571703.4 | 00777869 | 2023-12-27
|  | RAR # 2(1) | 98348762 | 4917438 | 28527303 | 491744 | 64412277 | 5043478 | 35000000 | 24368799 | 00781895 | 2024-01-11
|  | RAR # 2(2) | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 21368799 | 00782003 | 2024-01-17
|  | RAR # 2(3) | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 11368799 | 00860500 | 2025-01-20
|  | RAR # 2(4) | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 1368799 | 00860724 | 2025-01-30
|  | RAR # 3(1) | 48308781.02 | 2415439 | 15149640 | 241544 | 30502158.02 | 0 | 0 | 0
During the month |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | RAR WD | 10 % WH | Diff
Year to date |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF!
Up to date |  |  | 236561941.02 | 11828097 | 44470301 | 1182810 | 179080733.02 | 10638072.6 | 127000000 | 41442660.42 | 0
During the month (Total) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | RAR WD | 10 % WH | Diff
Year to date (Total) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
Up to date (Total) |  | 0 | 236561941.02 | 11828097 | 44470301 | 1182810 | 179080733.02 | 10638072.6 | 127000000 | 0 | 0

## Anx F. (2) (hidden)
ANNEX "F"
Payment Information of Sub Contractors
Project Control:- Mandra Chakwal Road Project
Project:- Dualization and improvement of Mandra - Chakwal Road Project
SNo | CA No | Contractor | Upto Date in Rupees | [11 empty] | Total payment |  | Checque No | Date | Total payment to Contractors
|  |  | RAR No | Sub Contractor's Work Done | Stores Issued (if any) | Retention Money | Store Recovered / Idle Charges/ Provisional Payments | Income Tax 7.5% | Net Payble | Paid Amount against work done | Less/ (Over) Paid | Secure Advance against material | I.Tax on advance | Paid against secure advance |  | Payment Voucher No
1 |  | M/s Al-Syed Enterprises |  | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  |  | 1 | 26939769 |  | 2693976.9 | 0 | 2020482.675 | 22225309.425 | 21944957.675 | 0 | 5243289 | 393246.675 | 4850042.325 | 26795000 | PV-1 | RP-51427944 | 01-Oct-14 | 26795000
|  |  | 2 | 24060231 |  | 2406023.1 | 0 | 1804517.325 | 19849690.575 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
|  |  | 3 | 6500000 |  | 650000 | 0 | 487500 | 5362500 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
|  |  | 4 | 29200020 |  | 2920002 | 0 | 2190001.5 | 24090016.5 | 5161130 | 0 | 5631211 | 422340.825 | 5208870.175 | 10370000.175 | PV-35 | 53895353 | 2014-12-05 | 10370000.175
| Total :- |  |  | 86700020 | 0 | 8670002 | 0 | 6502501.5 | 71527516.5 | 27106087.675 | 0 | 10874500 | 815587.5 | 10058912.5 | 37165000.175 |  | 0 | 0 | 37165000.175
[9 empty] | 0 |  | 0
2 |  | M/s Muhammad Saleman Mandokhail |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 1 | 948457 |  | 94845.7 | 0 | 71134.275 | 782477.025 | 751150.4 | 31326.625 | 1674432 | 125582.4 | 1548849.6 | 2300000 | PV-45 | RP-53895322 | 2014-10-02 | 2300000
|  |  | 2 | 2500000 | 0 | 250000 | 0 | 187500 | 2062500 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
|  |  | 3 | 1800000 |  | 180000 | 0 | 135000 | 1485000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
|  |  | 4 | 10700000 |  | 1070000 | 0 | 802500 | 8827500 | 3500000 | 0 | 0 | 0 | 0 | 3500000 | PV-45 | RP-53895364 | 2014-12-08 | 3500000
| Total :- |  |  | 15948457 | 0 | 1594845.7 | 0 | 1196134.275 | 13157477.025 | 4251150.4 | 31326.625 | 1674432 | 125582.4 | 1548849.6 | 5800000 |  | 0 | 0 | 5800000
3 |  | #REF!
|  |  | 1 | 6800000 |  | 680000 | 0 | 510000 | 5610000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
|  |  | 2 | 9300000 |  | 930000 | 0 | 697500 | 7672500 | 2095744 |  | 21939382 | 1645453.65 | 20293928.35 | 20293928.35 | PV-51 | 53895371/53895381 | 2014-12-16 | 22389672.35
| Total :- |  |  | 16100000 | 0 | 1610000 | 0 | 1207500 | 13282500 | 2095744 | 0 | 21939382 | 1645453.65 | 20293928.35 | 20293928.35 |  | 0 | 0 | 22389672.35
4 |  | #REF!
|  |  | 1 | 8700000 |  | 870000 | 0 | 652500 | 7177500 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
|  |  | 2 | 13500000 |  | 1350000 | 0 | 1012500 | 11137500
| Total :- |  |  | 22200000 | 0 | 2220000 | 0 | 1665000 | 18315000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
5 |  | #REF!
|  |  | 1 | 5000000 |  | 500000 | 0 | 375000 | 4125000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
|  |  | 2 | 9560000 |  | 956000 |  | 717000 | 7887000
| Total :- |  |  | 14560000 | 0 | 1456000 | 0 | 1092000 | 12012000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
|  | Grand Total |  | 155508477 |  | 15550847.7 | 0 | 11663135.775 | 128294493.525 | 33452982.075 | 31326.625 | 34488314 | 2586623.55 | 31901690.45 | 63258928.525 |  | 0 | 0 | 65354672.525
Final Bill Payment
R Money (Dr)
Payable (Dr)
Lab Income (Cr)
Bank Payment (Cr)

## Anx F (hidden)
ANNEX "F"
Payment Information of Sub Contractors
Project Control:- Mandra Chakwal Road Project
Project:- Dualization and improvement of Mandra - Chakwal Road Project
SNo | CA No | Contractor | [5 empty] | Deductions | [6 empty] | Amount Due |  |  | Total payment | Under/ (Over) Paid | Checque No | Date
|  |  | RAR No | Sub Contractor's Work Done | Stores Issued (if any) | Secure Advance against material | Mobalization Advance | Retention Money | Store Recovered / Idle Charges/ Provisional Payments | Income Tax 7.5% | Net Payble | Less/ (Over) Paid | Secure Advance against material/Mob Advance | I.Tax on advance |  | Paid Amount against work done | Paid against secure advance/ Mob Advance
1 |  | M/s Al-Syed Enterprises |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 1 | 26939769 |  | 5243289 | 0 | 1346988.45 | 0 | 2020482.675 | 23572297.875 | 0 | 5243289 | 393246.675 | 28422340.2 | 21944957.675 | 4850042.325 | 26795000 | 1627340.2 | 51427944 | 2014-10-01
|  |  | 2 | 6145718 |  | 5631211 | 0 | 307285.9 | 0 | 460928.85 | 5377503.25 | 0 | 5631211 | 422340.825 | 10586373.425 | 5161129.825 | 5208870.175 | 10370000 | 216373.425 | 53895353 | 2014-12-05
|  |  | 3 | 0 |  | 7759250 | 0 | 0 | 0 | 0 | 0 | 0 | 7759250 | 581943.75 | 7177306.25 | 0 | 7177306.25 | 7177306.25 | 0 | 53895403 | 2015-01-05
|  |  | 4 | 3895028 |  | 0 | 0 | 194751.4 | 0 | 292127.1 | 3408149.5 | 0 | 0 | 0 | 3408149.5 | 5251863.05 | 0 | 5251863.05 | -1843713.55 | 60596488 | 2015-01-28
|  |  | 5 | 2724609 |  | 0 | 0 | 136230.45 |  | 204345.675 |  |  |  | 0 | 2384032.875 | 2384033.075 | 0 | 2384033.075 | -0.2 | 605966564 | 2015-03-06
|  |  | 6 | 39933946 |  | 0 | 0 | 1996697.3 |  | 2995045.95 |  |  |  | 0 | 34942202.75 | 15000000 | 0 | 15000000 | 19942202.75 | 64199947 | 2015-03-20
|  |  | 7 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 10000000 | 0 | 10000000 | -10000000 | 64199953 | 2015-03-26
|  |  | 8 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 9942202.75 | 0 | 9942202.75 | -9942202.75 | 64199971 | 2015-04-07
|  |  | 9 | 48268222 |  | 0 | 0 | 2413411.1 | 2000000 | 3620116.65 |  |  |  | 0 | 40234694.25 | 20000000 | 0 | 20000000 | 20234694.25 | 66942543 | 2015-05-05
|  |  | 10 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 10000000 | 0 | 10000000 | -10000000 | 66942593 | 2015-05-21
|  |  | 11 | 0 |  | 0 | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 10234695 | 0 | 10234695 | -10234695 | 69695108 | 2015-06-15
|  |  | 12 | 23535361 |  | 0 | 0 | 1176768.05 |  | 1765152.075 |  |  |  | 0 | 20593440.875 | 20593441 | 0 | 20593441 | -0.125 | 69695149 | 2015-06-30
|  |  | 13 | 34546155 |  | 0 | 0 | 1727307.75 |  | 2590961.625 |  |  |  | 0 | 30227885.625 | 30227886 | 0 | 30227886 | -0.375 | 71820676 | 2015-07-13
|  |  | 14 | 14042998 |  |  |  | 702149.9 | 2050000 | 1053224.85 |  |  |  |  | 10237623.25 | 10237623.25 |  | 10237623.25 | 0 | 74557156 | 2015-09-04
|  |  | 15 | 28433331 |  |  |  | 1421666.55 | 1879165 | 2132499.825 |  |  |  |  | 22999999.625 | 8000000 |  | 8000000 | 14999999.625 | 74557158 | 2015-09-08
[16 empty] | 15000000 |  | 15000000 | -15000000 | 74557214 | 2015-09-23
|  |  | 15-A | 25698513 |  |  |  | 2569851 | -899586 | 1927388.475 |  |  |  |  | 20301687.525 | 20000000 |  | 20000000 | 301687.525 | 74557236 | 2015-10-13
|  |  | 16 | 10786809 |  |  |  | 1078681 | 295024 | 413104 |  |  |  |  | 9000000 | 9000000 |  | 9000000 | 0 | 76574375 | 2015-11-07
|  |  | 17 | 31393939 |  |  |  | 3139394 |  | 2354545 |  |  |  |  | 25900000 | 13000000 |  | 13000000 | 12900000 |  | 2015-12-10
[15 empty] | 0 | 12900000 |  | 12900000 | -12900000 |  | 2015-12-18
|  |  | 18 | 18181818 |  |  |  | 1818182 |  | 1363636 |  |  |  |  | 15000000 | 15000000 |  | 15000000 | 0 | 79109963 | 2016-01-06
|  |  | 19 | 21818182 |  | -8000000 |  | 2181818 |  | 1636364 |  |  |  |  | 10000000 | 10000000 |  | 10000000 | 0 | 81511431 | 2016-02-02
|  |  | 20 | 13939394 |  | -2000000 |  | 1393939 |  | 1045455 |  |  |  |  | 9500000 | 5000000 |  | 5000000 | 4500000 | 81511463 | 2016-02-15
[15 empty] | 0 | 4500000 |  | 4500000 | -4500000 | 83424306 | 2016-02-19
|  |  | 21 | 6060606 |  | -1000000 |  | 606061 |  | 454545 |  |  |  |  | 4000000 | 4000000 |  | 4000000 | 0 | 00210769 | 2016-03-01
|  |  | 22 | 7272728 |  | -1000000 |  | 545455 |  | 727273 |  |  |  |  | 5000000 | 5000000 |  | 5000000 | 0 | 00210798 | 2016-03-15
|  |  | 23 | 20606061 |  | -4000000 |  | 2060606 |  | 1545455 |  |  |  |  | 13000000 | 13000000 |  | 13000000 | 0 | 00220318 | 2016-04-20
|  |  | 24 | 12571428 |  |  |  | 628571 |  | 942857 |  |  |  |  | 11000000 | 11000000 |  | 11000000 | 0 | 00220335 | 2016-04-26 | 20000000 | 113400000
| Total :- |  |  | 396794615 | 0 | 2633750 | 0 | 27445814.85 | 5324603 | 29545507.75 | 32357950.625 | 0 | 18633750 | 1397531.25 | 333915736.15 | 316377831.625 | 17236218.75 | 333614050.375 | 301685.775 | 0 | 0 |  | 87500000
[11 empty] | 0 | 0
2 |  | M/s Muhammad Saleman Mandokhail |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
|  |  | 1 | 948457 |  | 1674432 | 0 | 47422.85 | 0 | 71134.275 | 829899.875 | 78749.875 | 1674432 | 125582.4 | 2378749.475 | 751150 | 1548849.9975 | 2299999.9975 | 78749.4775 | 53895322 | 2014-10-02
|  |  | 2 | 5834105 | 5834105 | 0 | 0 | 291705.25 | 0 | 437557.875 | 5104841.875 | 0 | 0 | 0 | 5104841.875 | 3500000 | 0 | 3500000 | 1604841.875 | 53895364 | 2014-12-12
|  |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1344463 | 0 | 1344463 | -1344463 | 53895398 | 2015-01-02
|  |  | 4 | 1367553 | 1367553 | 0 | 0 | 68377.65 | 0 | 102566.475 | 1196608.875 |  |  | 0 | 1196608.875 | 1100000 | 0 | 1100000 | 96608.875 | 53895417 | 2015-01-15
|  |  | 5 | 0 | 0 | 1271658 | 0 | 0 |  | 0 |  |  |  | 95374.35 | 1176283.65 | 0 | 1176283.65 | 1176283.65 | 0 | 60596500 | 2015-02-06
|  |  | 6 | 1421717 | 1421717 | 0 | 0 | 71085.85 |  | 106628.775 |  |  |  | 0 | 1244002.375 | 1679739 | 0 | 1679739 | -435736.625 | 60596501 | 2015-02-06
|  |  | 7 | 1463333 | 1463333 | 0 | 0 | 73166.65 |  | 109749.975 |  |  |  | 0 | 1280416.375 | 1280418 | 0 | 1280418 | -1.625 | 60596546 | 2015-02-26
|  |  | 8 | 2593867 | 2593867 | 0 | 0 | 129693.35 |  | 194540.025 |  |  |  | 0 | 2269633.625 | 2269633 | 0 | 2269633 | 0.625 | 60596566 | 2015-03-06
|  |  | 9 | 1411728 | 1411728 | 0 | 0 | 70586.4 |  | 105879.6 |  |  |  | 0 | 1235262 | 1235262 | 0 | 1235262 | 0 | 64199973 | 2015-04-07
|  |  | 10 | 2398316 | 2398316 | 0 | 0 | 119915.8 |  | 179873.7 |  |  |  | 0 | 2098526.5 | 2000000 | 0 | 2000000 | 98526.5 | 64200015 | 2015-04-27
|  |  | 11 | 3736945 | 3736945 | 0 | 0 | 186847.25 |  | 280270.875 |  |  |  | 0 | 3269826.875 | 3368354 | 0 | 3368354 | -98527.125 | 66942550 | 2015-05-06
|  |  | 12 | 10511148 | 10511148 | 0 | 0 | 525557.4 | 100000 | 788336.1 |  |  |  | 0 | 9097254.5 | 3500000 | 0 | 3500000 | 5597254.5 | 66942578 | 2015-05-18
|  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 5000000 | 0 | 5000000 | -5000000 | 66942604 | 2015-06-01
|  |  | 13 | 8503574 | 8503574 | 0 | 0 | 425178.7 | -900000 | 637768.05 |  |  |  | 0 | 6540627.25 | 5000000 | 0 | 5000000 | 1540627.25 | 69695109 | 2015-06-15
|  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 2137882 | 0 | 2137882 | -2137882 | 69695150 | 2015-06-30
|  |  | 14 | 9753137 | 0 | 0 | 0 | 487656.85 |  | 731485.275 |  |  |  | 0 | 8533994.875 | 8533994 |  | 8533994 | 0.875 | 71820675 | 2015-07-13
|  |  | 17 | 9596024 |  |  |  | 479801.2 | 1400000 | 719701.8 |  |  |  |  | 6996521 | 6996521 |  | 6996521 | 0 | 71820760 | 2015-09-01
|  |  | 18 | 6203365 |  |  |  | 310168.25 | 1000000 | 465252.375 |  |  |  |  | 4427944.375 | 4427944.375 |  | 4427944.375 | 0 | 74557211 | 2015-09-22
|  |  | 19 | 6196734 |  |  |  | 619673.4 | 823319 | 464755.05 |  |  |  |  | 4288986.55 | 4288987 |  | 4288987 | -0.45 | 76574391 | 2015-11-13
|  |  | 20 | 1555416 |  |  |  | 155541.6 |  | 116656.2 |  |  |  |  | 1283218.2 | 1000000 |  | 1000000 | 283218.2
|  |  | 21 | 14800000 |  |  |  | 1480000 |  | 1110000 |  |  |  |  | 12210000 | 8000000 |  | 8000000 | 4210000 | 79109908 | 2015-12-10
[15 empty] | 0 | 4210000 |  | 4210000 | -4210000 | 79109935 | 2015-12-18
|  |  | 22 | 6060606 |  |  |  | 606061 |  | 454545 |  |  |  |  | 5000000 | 5000000 |  | 5000000 | 0 | 79109964 | 2016-01-06
|  |  | 23 | 2242424 |  |  |  | 224242 |  | 168182 |  |  |  |  | 1850000 | 1850000 |  | 1850000 | 0 | 81511396 | 2016-01-22
|  |  | 24 | 7757576 |  | -1400000 |  | 775758 |  | 581818 |  |  |  |  | 5000000 | 5000000 |  | 5000000 | 0 | 81511433 | 2016-02-02
|  |  | 25 | 6060606 |  |  |  | 606061 |  | 454545 |  |  |  |  | 5000000 | 5000000 |  | 5000000 | 0 | 81511462 | 2016-02-15
|  |  | 26 | 3636363 |  |  |  | 363636 |  | 272727 |  |  |  |  | 3000000 | 3000000 |  | 3000000 | 0 | 210768 | 2016-03-01
|  |  | 27 | 12121212 |  |  |  | 909091 |  | 1212121 |  |  |  |  | 10000000 | 10000000 |  | 10000000 | 0 | 210784 | 2016-03-07
[8 empty] | 0 |  | 0 |  |  |  |  | 0 | 283218 |  | 283218 | -283218 | 220298 | 2016-04-13
|  |  | 28 | 4242424 |  |  |  | 424242 |  | 318182 |  |  |  |  | 3500000 | 3500000 |  | 3500000 | 0 | 220303 | 2016-04-14
|  |  | 29 | 24242424 |  |  |  | 2424242 |  | 1818182 |  |  |  |  | 20000000 | 20000000 |  | 20000000 | 0 | 220336 | 2016-04-26
| Total :- |  |  | 154659054 | 5834105 | 1546090 | 0 | 11875711.45 | 2423319 | 11902458.425 | 7131350.625 | 78749.875 | 1674432 | 220956.75 | 127982698.375 | 125257565.375 | 2725133.6475 | 127982699.0225 | -0.6475 | 0 | 0
3 |  | M/s Ajj Engineers
|  |  | 1 | 2544308 | 2544308 | 0 | 0 | 127215.4 | 0 | 190823.1 | 2226269.5 | 0 | 21939382 | 0 | 2226269.5 | 2095744 | 0 | 2095744 | 130525.5 | 53895371 | 2014-12-16
|  |  | 2 | 0 | 0 | 21939382.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1645453.6875 | 20293928.8125 | 0 | 20293928.8125 | 20293928.8125 | 0 | 53895381 | 2014-12-26
|  |  | 3 | 1851075.8 | 1851075.8 | 0 | 0 | 92553.79 |  | 138830.685 |  |  |  | 0 | 1619691.325 | 1750218 | 0 | 1750218 | -130526.675 | 60596498 | 2015-02-03
|  |  | 4 | 0 | 0 | 3636648.75 | 0 | 0 |  | 0 |  |  |  | 272748.6562 | 3363900.0938 | 0 | 3363900.0938 | 3363900.0938 | 0 | 60596569 | 2015-03-09
|  |  | 5 | 2729741 | 2729741 | 0 | 0 | 136487.05 |  | 204730.575 |  |  |  | 0 | 2388523.375 | 2388523 | 0 | 2388523 | 0.375 | 64199965 | 2015-04-01
|  |  | 6 | 3261519.1 | 3261519.1 | 0 | 0 | 163075.955 |  | 244613.9325 |  |  |  | 0 | 2853829.2125 | 2853829 | 0 | 2853829 | 0.2125 | 64200016 | 2015-04-28
|  |  | 7 | 3815688 | 3815688 | 0 | 0 | 190784.4 | 150000 | 286176.6 |  |  |  | 0 | 3188727 | 3338727 | 0 | 3338727 | -150000 | 66942544 | 2015-05-06
|  |  | 8 | 7603530 | 7603530 | 0 | 0 | 380176.5 |  | 570264.75 |  |  |  | 0 | 6653088.75 | 6500000 | 0 | 6500000 | 153088.75 | 66942594 | 2015-05-21
|  |  | 9 | 9422036 | 0 | 0 | 0 | 471101.8 | -206895 | 706652.7 |  |  |  | 0 | 8037386.5 | 7000000 | 0 | 7000000 | 1037386.5 | 69695129 | 2015-06-18
|  |  | 10 | 21680852 | 0 | 0 | 0 | 1084042.6 |  | 1626063.9 |  |  |  | 0 | 18970745.5 | 20000000 | 0 | 20000000 | -1029254.5 | 69695186 | 2015-07-09
|  |  | 11 | 16974401 |  |  |  | 848720.05 | -1200000 | 1273080.075 |  |  |  |  | 13652600.875 | 5000000 |  | 5000000 | 8652600.875 | 74557157, | 2015-09-08
[16 empty] | 3500000 |  | 3500000 | -3500000 | 74557212 | 2015-09-22
[16 empty] | 5163822 |  | 5163822 | -5163822 | 74557213 | 2015-09-23
|  |  | 12 | 11637357 |  |  |  | 909671 | 0 | 872801.775 |  |  |  |  | 9854884.225 | 8000000 |  | 8000000 | 1854884.225 | 74557223 | 2015-10-06
[15 empty] | 0 | 1854885 |  | 1854885 | -1854885 | 76574386 | 2015-11-12
|  |  | 13 | 19060606 |  |  |  | 1906061 |  | 1429545 |  |  |  |  | 15725000 | 8000000 |  | 8000000 | 7725000 | 79109906 | 2015-12-10
[15 empty] | 0 | 7725000 |  | 7725000 | -7725000 | 79109930 | 2015-12-18
|  |  | 14 | 15757576 |  |  |  | 1575758 |  | 1181818 |  |  |  |  | 13000000 | 13000000 |  | 13000000 | 0
|  |  | 15 | 18181818 |  | -10000000 |  | 1818182 | 1256895 | 1363636 |  |  |  |  | 5000000 | 5000000 |  | 5000000 | 0 | 83424303 | 2016-02-19
|  |  | 16 | 7272727 |  | -1000000 |  | 727272 |  | 545455 |  |  |  |  | 5000000 | 5000000 |  | 5000000 | 0 | 210766 | 2016-03-01
|  |  | 17 | 17575758 |  | -2500000 |  | 1757576 |  | 1318182 |  |  |  |  | 12000000 | 12000000 |  | 12000000 | 0 | 210802 | 2016-03-21
|  |  | 18 | 8000000 |  | -2500000 |  | 400000 |  | 600000 |  |  |  |  | 4500000 | 4500000 |  | 4500000 | 0 | 220304 | 2016-04-14
|  |  | 19 | 9090909 |  | -2500000 |  | 909091 |  | 681818 |  |  |  |  | 5000000 | 5000000 |  | 5000000 | 0 | 220337 | 2016-04-26
| Total :- |  |  | 176459901.9 | 2544308 | 7076031.25 | 0 | 13497768.545 | 0 | 13234492.0925 | 2226269.5 | 0 | 21939382 | 1918202.3438 | 153328575.1687 | 129670748 | 23657828.9062 | 153328576.9062 | -1.7375 | 0 | 0
4 |  | M/s Valley Homes
|  |  | 1 | 0 |  | 0 | 23404952 | 0 | 0 | 0 | 0 | 0 | 0 | 1755371.4 | 21649580.6 | 0 | 21649580.6 | 21649580.6 | 0 | 53895408 | 2015-01-13
|  |  | 2 |  |  |  | 23404951 | [6 empty] | 1755371.325 | 21649579.675 |  | 21649579 | 21649579 | 0.675 | 60596497 | 2015-02-02
|  |  | 3 | 16705582 |  |  | -9361980.6 | 835279.1 | 400000 | 1252918.65 |  |  |  |  | 4855403.65 | 4800000 |  | 4800000 | 55403.65 | 69695103 | 2015-06-08
|  |  | 4 |  |  | 2273749 |  |  | 2162789 |  |  |  |  | 170531.175 | 2103217.825 |  | 2158622 | 2158622 | -55404.175 | 69695147 | 2015-06-30
|  |  | 5 |  |  | 4613989 | [7 empty] | 461398.9 | 4152590.1 |  | 4152590.1 | 4152590.1 | 0 | 71820746 | 2015-08-24
|  |  | 6 | 21668103 |  | -4560434 | -9361981 | 2166810 | -2562789 | 2166810 |  |  |  |  | 849279 | 849279 |  | 849279 | 0 | 81511377 | 2016-01-18
| Total :- |  |  | 38373685 | 0 | 2327304 | 28085941.4 | 3002089.1 | 0 | 3419728.65 | 0 | 0 | 0 | 4142672.8 | 55259650.85 | 5649279 | 49610371.7 | 55259650.7 | 0.15
5 |  | M/s Shahid Builders
|  |  | 1 | 3560066 |  | 0 | 0 | 178003.3 | 0 | 267004.95 | 3115057.75 | 0 | 0 | 0 | 3115057.75 | 2900000 | 0 | 2900000 | 215057.75 | 53895416 | 2015-01-15
|  |  | 2 |  |  | 1842750 |  | 0 |  | 0 |  |  |  | 138206.25 | 1704543.75 | 0 | 1704543.75 | 1704543.75 | 0 | 64199932 | 2015-03-13
|  |  | 3 | 3598813 |  |  |  | 179940.65 |  | 251916.91 |  |  |  |  | 3166955.44 | 3166955 |  | 3166955 | 0.44 | 64199933 | 2015-03-13
|  |  | 4 | 5600438 |  |  |  | 280021.9 |  | 365017.66 |  |  |  |  | 4955398.44 | 5170457 |  | 5170457 | -215058.56 | 69695148 | 2015-06-30
|  |  | 5 | 3689228 |  |  |  | 184461.4 |  | 285260.96 |  |  |  |  | 3219505.64 | 3000000 |  | 3000000 | 219505.64 | 71820688 | 2015-07-14
|  |  | 6 | 5056989 |  |  |  | 252849.45 | 748727 | 353989.23 |  |  |  |  | 3701423.32 | 3920929 |  | 3920929 | -219505.68 | 74557198 | 2015-09-21
|  |  | 7 | 5696592 |  |  |  | 569659 |  | 398761 |  |  |  |  | 4728172 | 3835054 |  | 3835054 | 893118 | 79109912 | 2015-12-11
|  |  | 8 | 2799564 |  | -365647 |  | 279956 |  | 195969 |  |  |  |  | 1957992 | 1957992 |  | 1957992 | 0 | 81511420 | 2016-02-01
|  |  | 9 | 2865056 |  | -583985 |  | 286506 | -159750 | 200554 |  |  |  |  | 1634261 | 1634261 |  | 1634261 | 0
|  |  | 10 | 4323974 |  |  |  | 432398 |  | 302678 |  |  |  |  | 3588898 | 3588898 |  | 3588898 | 0 | 220301 | 2016-04-14
| Total :- |  |  | 37190720 | 0 | 893118 | 0 | 2643795.7 | 588977 | 2621151.71 | 3115057.75 | 0 | 0 | 138206.25 | 31772207.34 | 29174546 | 1704543.75 | 30879089.75 | 893117.59
6 |  | M/s Karim Baksh ((MCRP/12/2015/PDN/NLC)
|  |  | 1 | 914286 |  | 0 | 0 | 45714.3 | 0 | 68571.45 | 800000.25 | 0 | 0 | 0 | 800000.25 | 800000 | 0 | 800000 | 0.25 | RP-64199950 | ,25-Mar-15
|  |  | 2 | 1146698 |  | 0 |  | 57334.9 |  | 86002.35 |  |  |  | 0 | 1003360.75 | 1000000 | 0 | 1000000 | 3360.75 | RP-64199986 | ,10-Apr-15
|  |  | 3 | 1640000 |  |  |  | 82000 |  | 123000 |  |  |  |  | 1435000 | 1400000 |  | 1400000 | 35000 | RP-66942540 | ,5-May-15
[16 empty] | 38361 |  | 38361 | -38361 | RP-81511455 | ,15-Feb-16
| Total :- |  |  | 3700984 | 0 | 0 | 0 | 185049.2 | 0 | 277573.8 | 800000.25 | 0 | 0 | 0 | 3238361 | 3238361 | 0 | 3238361 | 0 | 0 | 0
7 |  | M/s Hammad Bros (MCRP/13/2015/PDN/NLC)
|  |  | 1 | 913522 |  | 0 | 0 | 45676.1 | 0 | 68514.15 | 799331.75 | 0 | 0 | 0 | 799331.75 | 780000 | 0 | 780000 | 19331.75 | 64199988 | 2015-04-03
|  |  | 2 | 108181 |  |  |  | 5409.05 |  | 8113.575 |  |  |  |  | 94658.375 | 50000 |  | 50000 | 44658.375 | 71820698 | 2015-07-15
|  |  | 3 | 371878 |  |  |  | 18593.9 |  | 27890.85 |  |  |  |  | 325393.25 | 200000 |  | 200000 | 125393.25 | 74557197 | 2015-09-21
| Total :- |  |  | 1393581 | 0 | 0 | 0 | 69679.05 | 0 | 104518.575 | 799331.75 | 0 | 0 | 0 | 1219383.375 | 1030000 | 0 | 1030000 | 189383.375
8 |  | M/s Hammad Bros (MCRP/24/2015/PDN/NLC)
|  |  | 1 | 1262559 |  | 0 | 0 | 63127.95 | 0 | 94691.925 | 1104739.125 | 0 | 0 | 0 | 1104739.125 | 455351 | 0 | 455351 | 649388.125 | 66942541 | 2015-05-05
|  |  | 2 |  |  |  |  | 0 |  | 0 |  |  |  |  | 0 | 600000 |  | 600000 | -600000 | 66942592 | 2015-05-21
|  |  | 3 | 528499 |  |  |  | 26424.95 |  | 39637.425 |  |  |  |  | 462436.625 | 465429 |  | 465429 | -2992.375 | 69695140 | 2015-06-30
|  |  | 4 | 448500 |  |  |  | 22425 |  | 33637.5 |  |  |  |  | 392437.5 | 300000 |  | 300000 | 92437.5 | 71820699 | 2015-07-15
| Total :- |  |  | 2239558 | 0 | 0 | 0 | 111977.9 | 0 | 167966.85 | 1104739.125 | 0 | 0 | 0 | 1959613.25 | 1820780 | 0 | 1820780 | 138833.25
9 |  | M/s Mehmood Khan-Culvert (MCRP/19/2015/PD)
|  |  | 1 | 751861 |  | 0 | 0 | 37593.05 | 0 | 56389.575 | 657878.375 | 0 | 0 | 0 | 657878.375 | 550000 | 0 | 550000 | 107878.375 | 66942560 | 2015-05-11
|  |  | 2 | 600329 |  |  |  | 30016.45 |  | 45024.675 |  |  |  |  | 525287.875 | 633166 |  | 633166 | -107878.125 | 69695138 | 2015-06-30
|  |  | 3 | 714298 |  |  |  | 35714.9 |  | 53572.35 |  |  |  |  | 625010.75 | 625011 |  | 625011 | -0.25 | 71820678 | 2015-07-14
|  |  | 4 | 395466 |  |  |  | 19773.3 |  | 29659.95 |  |  |  |  | 346032.75 | 346032 |  | 346032 | 0.75 | 74557229 | 2015-10-09
|  |  | 5 | 7539394 |  |  |  | 753939 |  | 565455 |  |  |  |  | 6220000 | 2000000 |  | 2000000 | 4220000
[15 empty] | 0 | 3000000 |  | 3000000 | -3000000 | 79109921 | 2015-12-17
[15 empty] | 0 | 1220000 |  | 1220000 | -1220000 | 79109933 | 2015-12-18
|  |  | 6 | 2285715 |  |  |  | 114286 |  | 171429 |  |  |  |  | 2000000 | 2000000 |  | 2000000 | 0 | 79109979 | 2016-01-07
| Total :- |  |  | 12287063 | 0 | 0 | 0 | 991322.7 | 0 | 921530.55 | 657878.375 | 0 | 0 | 0 | 10374209.75 | 10374209 | 0 | 10374209 | 0.75
10 |  | M/s Karim Baksh & Sons(MCRP/38/2015/PD)
|  |  | 1 | 6586454 |  | 0 | 0 | 329322.7 | 0 | 658645.4 | 5598485.9 | 0 | 0 | 0 | 5598485.9 | 5000000 | 0 | 5000000 | 598485.9 | 69695167 | 2015-07-03
|  |  | 2 | 1104246 |  |  |  | 55212.3 |  | 82818.45 |  |  |  |  | 966215.25 | 1564702 |  | 1564702 | -598486.75 | 71820751 | 2015-08-26
|  |  | 3 | 1318285 |  |  |  | 65914.25 |  | 98871.375 |  |  |  |  | 1153499.375 | 1100000 |  | 1100000 | 53499.375 | 76574339 | 2015-10-27
[15 empty] | 0 | 53499 |  | 53499 | -53499 | 81511456 | 2016-02-15
| Total :- |  |  | 9008985 | 0 | 0 | 0 | 450449.25 | 0 | 840335.225 | 5598485.9 | 0 | 0 | 0 | 7718200.525 | 7718201 | 0 | 7718201 | -0.475 | 0 | 0
11 |  | M/s Hammad Brothers (CA-23/2015)
|  |  | 1 | 301889 |  | 0 | 0 | 15094.45 | 0 | 22642 | 264152.55 | 0 | 0 | 0 | 264152.55 | 200000 | 0 | 200000 | 64152.55 | 71820697 | 2015-07-15
| Total :- |  |  | 301889 | 0 | 0 | 0 | 15094.45 | 0 | 22642 | 5598485.9 | 0 | 0 | 0 | 264152.55 | 200000 | 0 | 200000 | 64152.55 | 0 | 0
12 |  | M/s Mehmood Khan-Earthwork (MCRP/18/2015/PD)
|  |  | 1 | 2287332 |  | 0 | 0 | 114366.6 | 0 | 171549.9 | 2001415.5 | 0 | 0 | 0 | 2001415.5 | 2001415 | 0 | 2001415 | 0.5 | 69695144 | 2015-06-30
|  |  | 2 | 4595143 |  |  |  | 229757.15 |  | 344635.725 |  |  |  |  | 4020750.125 | 4020750 |  | 4020750 | 0.125 | 71820673 | 2015-07-13
|  |  | 3 | 1586255 |  |  |  | 79312.75 |  | 273504 |  |  |  |  | 1233438.25 | 1233439 |  | 1233439 | -0.75 | 74557153 | 2015-09-03
|  |  | 4 | 778694 |  |  |  | 38934.7 |  | 58402.05 |  |  |  |  | 681357.25 | 681358 |  | 681358 | -0.75 | 74557205 | 2015-09-22
|  |  | 5 | 1210596 |  |  |  | 60529.8 |  | 90794.7 |  |  |  |  | 1059271.5 | 1000000 |  | 1000000 | 59271.5 | 76574370 | 2015-11-05
|  |  | 6 | 2114285 |  |  |  | 105714 |  | 158571 |  |  |  |  | 1850000 | 1850000 |  | 1850000 | 0 | 81511395 | 2016-01-22
|  |  | 7 | 3636363 |  |  |  | 363636 |  | 272727 |  |  |  |  | 3000000 | 3000000 |  | 3000000 | 0 | 81511432 | 2016-02-02
| Total :- |  |  | 16208668 | 0 | 0 | 0 | 992251 | 0 | 1370184.375 | 2001415.5 | 0 | 0 | 0 | 13846232.625 | 13786962 | 0 | 13786962 | 59270.625 | 0 | 0
13 |  | M/s Mehmood Khan & Co (CA-25/2015)
|  |  | 1 | 437332 |  | 0 | 0 | 21866.6 | 0 | 32799.9 | 382665.5 | 0 | 0 | 0 | 382665.5 | 382665 | 0 | 382665 | 0.5 | 71820684 | 2015-07-14
|  |  | 2 | 211253 |  |  |  | 10562.65 |  | 15843.975 |  |  |  |  | 184846.375 | 184847 |  | 184847 | -0.625 | 74557201 | 2015-09-22
|  |  | 3 | 2424242 |  |  |  | 242424 |  | 181818 |  |  |  |  | 2000000 | 2000000 |  | 2000000 | 0 | 81511461 | 2016-02-15
|  |  | 4 | 1212121 |  |  |  | 121212 |  | 90909.075 |  |  |  |  | 999999.925 | 999999.925 |  | 999999.925 | 0
|  |  | 5 | 8000000 |  |  |  | 400000 |  | 600000 |  |  |  |  | 7000000 | 7000000 |  | 7000000 | 0 | 00220340 | 2016-04-27
| Total :- |  |  | 12284948 | 0 | 0 | 0 | 796065.25 | 0 | 921370.95 | 382665.5 | 0 | 0 | 0 | 10567511.8 | 10567511.925 | 0 | 10567511.925 | -0.125 | 0 | 0
14 |  | M/s Muhammad Zada(MCRP/14/2015/PD)
|  |  | 1 | 966897 |  | 0 | 0 | 48344.85 | 0 | 72517.275 | 846034.875 | 0 | 0 | 0 | 846034.875 | 700000 | 0 | 700000 | 146034.875 | 69695139 | 2015-06-30
| Total :- |  |  | 966897 | 0 | 0 | 0 | 48344.85 | 0 | 72517.275 | 382665.5 | 0 | 0 | 0 | 846034.875 | 700000 | 0 | 700000 | 146034.875 | 0 | 0
15 |  | M/s Mehmood Khan & Co (CA-46/2015)
|  |  | 1 | 247536 |  | 0 | 0 | 12376.8 | 0 | 18565.2 | 216594 | 0 | 0 | 0 | 216594 | 216594 | 0 | 216594 | 0 | 74557168 | 2015-09-11
|  |  | 2 | 94178 |  |  |  | 4708.9 | 0 | 7063.35 | 82405.75 | 0 | 0 | 0 | 82405.75 | 82405 | 0 | 82405 | 0.75 | 74557230 | 2015-10-09
|  |  | 3 | 57960 |  |  |  | 2898 |  | 4347 |  |  |  |  | 50715 | 50715 |  | 50715 | 0 | 76574416 | 2015-12-02
|  |  | 4 | 57960 |  |  |  | 2898 |  | 4347 |  |  |  |  | 50715 | 50715 |  | 50715 | 0 | 79109916 | 2015-12-14
|  |  | 5 | 217943 |  |  |  | 10897 |  | 16345 |  |  |  |  | 190701 | 190701 |  | 190701 | 0 | 79109961 | 2016-01-05
|  |  | 6 | 3428572 |  |  |  | 171429 |  | 257143 |  |  |  |  | 3000000 | 3000000 |  | 3000000 | 0 | 79109991 | 2016-01-13
|  |  | 7 | 220579 |  |  |  | 11029 |  | 16544 |  |  |  |  | 193006 | 193006 |  | 193006 | 0 | 81511428 | 2016-02-02
|  |  | 8 | 134985 |  |  |  | 6749 |  | 10124 |  |  |  |  | 118112 | 118112 |  | 118112 | 0 | 83424309 | 2016-02-23
|  |  | 9 | 82266 |  |  |  | 4113 |  | 6170 |  |  |  |  | 71983 | 71983 |  | 71983 | 0 | 00220299 | 2016-04-14
| Total :- |  |  | 4541979 | 0 | 0 | 0 | 227098.7 | 0 | 340648.55 | 298999.75 | 0 | 0 | 0 | 3974231.75 | 3974231 | 0 | 3974231 | 0.75 | 0 | 0
16 |  | M/S Karim Bukhsh Son(CA-29(A)/2015)
|  |  | 1 | 2430000 |  | 0 | 0 | 121500 | 0 | 229500 | 2079000 | 0 | 0 | 0 | 2079000 | 2000000 | 0 | 2000000 | 79000
|  |  | 2 | 810000 |  |  |  | 40500 |  | 60750 |  |  |  |  | 708750 | 787750 | 0 | 787750 | -79000 | 74557170 | 2015-09-11
| Total :- |  |  | 3240000 | 0 | 0 | 0 | 162000 | 0 | 290250 | 2079000 | 0 | 0 | 0 | 2787750 | 2787750 | 0 | 2787750 | 0 | 0 | 0
17 |  | M/s Muhammad Roz & Sons(CA-36/2015)
|  |  | 1 | 2001160 |  | 0 | 0 | 100058 | 0 | 200116 | 1700986 | 0 | 0 | 0 | 1700986 | 1700000 | 0 | 1700000 | 986 | 74557174 | 2015-09-15
|  |  | 2 | 1917905 |  |  |  | 95895 | -334750 | 143843 |  |  |  |  | 1343417 | 1344403 |  | 1344403 | -986 | 76574401 | 2015-11-26
|  |  | 3 | 1203521 |  |  |  | 60176 |  | 90264 |  |  |  |  | 1053081 | 1053081 |  | 1053081 | 0 | 81511435 | 2016-02-03
| Total :- |  |  | 5122586 | 0 | 0 | 0 | 256129 | -334750 | 434223 | 1700986 | 0 | 0 | 0 | 4097484 | 4097484 | 0 | 4097484 | 0 | 0 | 0
18 |  | M/s Mehmood Khan & Co (CA-42/2015)
|  |  | 1 | 4984832 |  | 0 | 0 | 249241.6 | 0 | 373862.4 | 4361728 | 0 | 0 | 0 | 4361728 | 2500000 | 0 | 2500000 | 1861728 | 74557204 | 2015-09-22
[16 empty] | 1500000 |  | 1500000 | -1500000 | 74557204 | 2015-10-09
[16 empty] | 361728 |  | 361728 | -361728
|  |  | 2 | 1357808 |  |  |  | 67890.4 | 0 | 101835.6 | 1188082 | 0 | 0 | 0 | 1188082 | 1100000 |  | 1100000 | 88082 | 76574369 | 2015-11-05
|  |  | 3 | 3465464 |  |  |  | 173273.2 | 0 | 259909.8 | 3032281 | 0 | 0 | 0 | 3032281 | 2000000 |  | 2000000 | 1032281 |  | 2015-11-23
[15 empty] | 0 | 1070363 |  | 1070363 | -1070363 | 79109897 | 2015-12-03
|  |  | 4 | 3030303 |  |  |  | 303030 |  | 227273 |  |  |  |  | 2500000 | 2500000 |  | 2500000 | 0 | 83424305 | 2016-02-19
[15 empty] | 0 | 50000 |  | 50000 | -50000 | 00210754 | 2016-02-26
|  |  | 5 | 1142857 |  |  |  | 57143 |  | 85714 |  |  |  |  | 1000000 | 1000000 |  | 1000000 | 0 | 00220320 | 2016-04-20
|  |  | 6 | 3428572 |  |  |  | 171429 |  | 257143 |  |  |  |  | 3000000 | 3000000 |  | 3000000 | 0 | 00220332 | 2016-04-25
| Total :- |  |  | 17409836 | 0 | 0 | 0 | 1022007.2 | 0 | 1305737.8 | 8582091 | 0 | 0 | 0 | 15082091 | 15082091 | 0 | 15082091 | 0 | 0 | 0
19 |  | M/s Base Trading Co (CA-59/2015)
|  |  | 1 | 4571428 |  | 0 | 0 | 228571.4 | 0 | 342857.1 | 3999999.5 | 0 | 0 | 0 | 3999999.5 | 4000000 | 0 | 4000000 | -0.5 | 74557238 | 2015-10-14
|  |  | 2 | 4484849 |  |  |  | 448485 |  | 336364 |  |  |  |  | 3700000 | 2000000 |  | 2000000 | 1700000 | 79109909 | 2015-12-10
[15 empty] | 0 | 1700000 |  | 1700000 | -1700000 | 79109937 | 2015-12-18
|  |  | 3 | 4228572 |  |  |  | 211429 |  | 317143 |  |  |  |  | 3700000 | 3700000 |  | 3700000 | 0 | 79109987 | 2016-01-13
|  |  | 4 | 1585715 |  |  |  | 79286 |  | 118929 |  |  |  |  | 1387500 | 1387500 |  | 1387500 | 0 | 81511394 | 2016-01-22
|  |  | 5 | 1212121 |  |  |  | 121212 |  | 90909 |  |  |  |  | 1000000 | 1000000 |  | 1000000 | 0 | 83424304 | 2016-02-19
| Total :- |  |  | 16082685 | 0 | 0 | 0 | 1088983.4 | 0 | 1206202.1 | 3999999.5 | 0 | 0 | 0 | 13787499.5 | 13787500 | 0 | 13787500 | -0.5 | 0 | 0
20 |  | M/s Base Trading Co (CA-61/2015)
|  |  | 1 | 2857143 |  | 0 | 0 | 142857.15 | 0 | 214285.725 | 2500000.125 | 0 | 0 | 0 | 2500000.125 | 2500000 | 0 | 2500000 | 0.125 | 74557238 | 2015-10-14
|  |  | 2 | 3272728 |  |  |  | 327273 | -700000 | 245455 |  |  |  |  | 2000000 | 2000000 |  | 2000000 |  | 81511460 | 2016-02-15
|  |  | 3 | 1142857 |  |  |  | 57143 |  | 85714 |  |  |  |  | 1000000 | 1000000 |  | 1000000 |  | 00210767 | 2016-03-01
|  |  | 4 | 2285715 |  | 0 | 0 | 114286 | 0 | 171429 |  |  |  | 0 | 2000000 | 2000000 | 0 | 2000000 | 0 | 00220306 | 2016-04-14
|  |  | 5 | 3428572 |  | 0 | 0 | 171429 |  | 257143 |  |  |  |  | 3000000 | 3000000 | 0 | 3000000 | 0 | 00220338 | 2016-04-26
| Total :- |  |  | 12987015 | 0 | 0 | 0 | 812988.15 | -700000 | 974026.725 | 2500000.125 | 0 | 0 | 0 | 10500000.125 | 10500000 | 0 | 10500000 | 0 | 0
21 |  | M/s Karim Baksh Son (MOU/Lab Agreement)
|  |  | 1 | 723346 |  | 0 | 0 | 0 | -119339 | 72335 | 531672 | 0 | 0 | 0 | 531672 | 531672 | 0 | 531672 | 0 | 74557238 | 2015-10-14
| Total :- |  |  | 723346 | 0 | 0 | 0 | 0 | -119339 | 72335 | 531672 | 0 | 0 | 0 | 531672 | 531672 | 0 | 531672 | 0 | 0 | 42419
0
22 |  | M/s Rana Azam & Saqib Ali
|  |  | 1 | 995421 |  | 0 | 0 | 49771 | 0 | 99542 | 846108 | 0 | 0 | 0 | 846108 | 600000 | 0 | 600000 | 246108 | 74557238 | 2015-10-14
[16 empty] | 246108 |  | 246108 | -246108
| Total :- |  |  | 995421 | 0 | 0 | 0 | 49771 | 0 | 99542 | 846108 | 0 | 0 | 0 | 846108 | 846108 | 0 | 846108 | 0 | 0 | 0
23 |  | M/s Mehmood Khan & Co (CA-43/2015)
|  |  | 1 | 4848484 |  | 0 | 0 | 484848 | 0 | 363636.3 | 3999999.7 | 0 | 0 | 0 | 3999999.7 | 4000000 | 0 | 4000000 | -0.3 | 74557238 | 2015-10-14
|  |  | 2 | 2285715 |  | 0 | 0 | 114286 | 0 | 171429 |  |  |  | 0 | 2000000 | 2000000 |  | 2000000 | 0 | 00220305 | 2016-04-14
| Total :- |  |  | 7134199 | 0 | 0 | 0 | 599134 | 0 | 535065.3 | 3999999.7 | 0 | 0 | 0 | 5999999.7 | 6000000 | 0 | 6000000 | -0.3 | 0 | 0
24 |  | M/s Tijarat Developers (CA-72/2015)
|  |  | 1 | 2021712 |  | 0 | 0 | 202171 | 0 | 151628 | 1667913 | 0 | 0 | 0 | 1667913 | 1667913 | 0 | 1667913 | 0 | 00220333 | 2016-04-25
| Total :- |  |  | 2021712 | 0 | 0 | 0 | 202171 | 0 | 151628 | 1667913 | 0 | 0 | 0 | 1667913 | 1667913 | 0 | 1667913 | 0 | 0 | 42291
25 |  | M/s Tijarat Developers (CA-73/2015)
|  |  | 1 | 11311621 |  | 0 | 0 | 1131162 | 1000000 | 848372 | 10332087 | 0 | 0 | 0 | 8332087 | 8332087 | 0 | 8332087 | 0 | 00220334 | 2016-04-25
| Total :- |  |  | 11311621 | 0 | 0 | 0 | 1131162 | 1000000 | 848372 | 10332087 | 0 | 0 | 0 | 8332087 | 8332087 | 0 | 8332087 | 0 | 0 | 0
|  | Grand Total |  | 943440948.9 |  | 14476293.25 | 28085941.4 | 67676857.745 | 8182810 | 71680008.7025 | 98695152.375 | 78749.875 | 42247564 | 7817569.3937 | 819899403.7087 | 723172830.925 | 94934096.7537 | 818106927.6787 | 1792475.905

## Anx G
Anx "G"
Detail Of Const Material
Project Control Unit:- Dev of C-15 Islamabad
Item | Purchased |  |  |  |  | Consumed |  |  |  | Remarks
| During the Month | Upto Date | A/U | Upto Date | Year to Date | During the month | Upto Date | Qty consumed | Year to Date
| Cost | Cost |  | Qtys | Cost | Cost | Cost |  | Cost
Total Cost (Rs in Million) | 0 | 0 |  |  | 0 | 0 | 0 |  | 0

## Anx G (1) (hidden)
Anx "G1"
Supplier wise detail Of Const Material
Project Control:- Mandra Chakwal Road Project
Project:- Dualization and improvement of Mandra - Chakwal Road Project
Item | Unit | Purchases (Rs) | [6 empty] | Issued to subcontractors | Consumed (Rs) | [5 empty] | Balance held (Rs in Million) |  |  |  | Remarks
|  | Total Qty Req | During the Month |  | Upto Date |  | Year to Date |  |  | During the Month |  | Upto Date |  | Year to Date |  | Upto date |  | Year to Date
|  |  | Qty | Cost | Qty | Cost | Qty | Cost |  | Qty | Cost | Qty | Cost | Qty | Cost | Qty | Cost | Qty | Cost
Sand
1.Al-Qayam | Cft | 2041335 | 220100 | 994852 | 2041335 | 7430319.605 | 220100 | 994852 |  | 220100 | 994852 | 2041335 | 7430319.605 | 220100 | 994852 | 0 | 0 | 0 | 0
Water Bound Macdam
1. Rawal Associates | Cft | 103193.6103 | 0 | 0 | 103193.6103 | 3569466.98 | 0 | 0 | [7 empty] | 103193.6103 | 3569466.98 | 103193.6103 | 3569466.98
2. Al Imran | Cft | 108082.844 | 0 | 0 | 108082.844 | 3738585.5735 | 0 | 0 | [7 empty] | 108082.844 | 3738585.5735 | 108082.844 | 3738585.5735
3. Ch Atif Nazar | Cft | 122750.9685 | 0 | 0 | 122750.9685 | 4245956 | 0 | 0 | [7 empty] | 122750.9685 | 4245956 | 122750.9685 | 4245956
4. SHL | Cft | 132908.7887 | 0 | 0 | 132908.7887 | 4597315 | 0 | 0 | [7 empty] | 132908.7887 | 4597315 | 132908.7887 | 4597315
5. Kazmi | Cft | 95554.4027 | 0 | 0 | 95554.4027 | 3305226.79 | 0 | 0 | [7 empty] | 95554.4027 | 3305226.79 | 95554.4027 | 3305226.79
6. Afridi & Co | Cft | 96900.3273 | 0 | 0 | 96900.3273 | 3351782.32 | 0 | 0 | [7 empty] | 96900.3273 | 3351782.32 | 96900.3273 | 3351782.32
7. Noor Enterprises | Cft | 47367 | 0 | 0 | 47367 | 1638424.53 | 0 | 0 | [7 empty] | 47367 | 1638424.53 | 47367 | 1638424.53
8. STS Enterprises | Cft | 11495.95 | 0 | 0 | 11495.95 | 397644.91 | 0 | 0 | [7 empty] | 11495.95 | 397644.91 | 11495.95 | 397644.91
9. Techworld | Cft | 96127.1755 | 0 | 0 | 96127.1755 | 3325039 | 0 | 0 | [7 empty] | 96127.1755 | 3325039 | 96127.1755 | 3325039
10. Khwaja enterprises | Cft | 51426 | 0 | 0 | 51426 | 1778825.34 | 0 | 0 | [7 empty] | 51426 | 1778825.34 | 51426 | 1778825.34
11. Cepro | Cft | 7320.2 | 0 | 0 | 7320.2 | 253205.718 | 0 | 0 | [7 empty] | 7320.2 | 253205.718 | 7320.2 | 253205.718
Sub base
1.Potohar | Cft | 3647.0357 | 0 | 0 | 3647.0357 | 102117 | 0 | 0 |  | 0 | 0 | 3647.0357 | 102117 | 0 | 0 | 0 | 0 | 0 | 0
2.Techworld | Cft | 8521.5714 | 0 | 0 | 8521.5714 | 238604 | 0 | 0 |  | 0 | 0 | 8521.5714 | 238604 | 0 | 0 | 0 | 0 | 0 | 0
3.Ch Atif Nazar | Cft | 223320.21 | 55454 | 1426848 | 223320.21 | 5601003 | 55454 | 1426848 |  | 55454 | 1426848 | 223320.21 | 5601003 | 55454 | 1426848 | 0 | 0 | 0 | 0
4. Al Imran | Cft | 195669.6 | 36141 | 924506 | 195669.6 | 4889955 | 36141 | 924506 |  | 36141 | 924506 | 195669.6 | 4889955 | 36141 | 924506 | 0 | 0 | 0 | 0
5. Cepro | Cft | 866.15 | 0 | 0 | 866.15 | 24252.2 | 0 | 0 |  | 0 | 0 | 866.15 | 24252.2 | 0 | 0 | 0 | 0 | 0 | 0
6. Noor Enterprises | Cft | 116340 | 23041 | 590490 | 116340 | 2908874 | 23041 | 590490 |  | 23041 | 590490 | 116340 | 2908874 | 23041 | 590490 | 0 | 0 | 0 | 0
7. Rawal Associates | Cft | 52955.8 | 27890.6 | 714218 | 52955.8 | 1319793 | 27890.6 | 714218 |  | 27890.6 | 714218 | 52955.8 | 1319793 | 27890.6 | 714218 | 0 | 0 | 0 | 0
8. Usman Stone Crusher | Cft | 52474 | 13978 | 354761 | 52474 | 1331790 | 13978 | 354761 |  | 13978 | 354761 | 52474 | 1331790 | 13978 | 354761
9. Unique Enterprises | Cft | 18152 | 18152 | 469955 | 18152 | 469955 | 18152 | 469955 |  | 18152 | 469955 | 18152 | 469955 | 18152 | 469955
10. Khawaja & Co | Cft | 84329 | 84329 | 393870 | 84329 | 393870 | 84329 | 393870 |  | 69362.252 | 112164 | 84329 | 393870 | 69362.252 | 112164
Asphalt
1.Asphalt GP NLC | Cft | 149 | 0 | 0 | 149 | 830526 | 0 | 0 |  | 0 | 0 | 149 | 830526 | 0 | 0 | 0 | 0 | 0 | 0
Steel
1.Potohar Steel | Cft | 608.413 | 0 | 0 | 608.413 | 50369805 | 0 | 0 | 8651247 | 0 | 0 | 414.4566 | 34275558 | 0 | 0 | 90 | 7443000 | 90 | 7443000 |  | 50369805 | -7901405.64
[21 empty] | 44580805 | 2403841 | 42176964
Cement
1. Askari Cement Ltd. | Tons | 370.396 | 35 | 309500 | 370.396 | 3626000 | 35 | 309500 | 3316500 | 35.396 | 309500 | 35.396 | 309500 | 35.396 | 309500 | 0 | 0 | 0 | 0
Crush (Aggregate)
1. Khawaja & Company | Cft | 4637 | 0 | 0 | 4637 | 15831.51 | 0 | 0 |  | -5280.9842 | -168554 | 4637 | 15831.51 | -5280.9842 | -168554
2. Usman Stone Crusher | Cft | 6689 | 0 | 0 | 6689 | 289165.47 | 0 | 0 |  | 0 | 0 | 6689 | 289165.47 | 0 | 0
3. Atif Nazar | Cft | 4994 | 0 | 0 | 4994 | 215890.62 | 0 | 0 |  | 0 | 0 | 4994 | 215890.62 | 0 | 0
Sand
1. Atif Nazar | Cft | 11272 | 0 | 0 | 11272 | 315052.4 | 0 | 0 |  | 0 | 0 | 11272 | 315052.4 | 0 | 0
Khaka(Stone dust)
1. Atif Nazar | Cft | 4707 | 0 | 0 | 4707 | 50985 | 0 | 0 |  | -3058.987 | -43201 | 4707 | 50985 | -3058.987 | -43201
2. Khawaja & Company | Cft | 2631 | 0 | 0 | 2631 | 52646.31 | 0 | 0 |  | 0 | 0 | 2631 | 52646.31 | 0 | 0
Other
Trumpet Cone from Amjad Engineering Services | Piece | 5900 | 0 | 0 | 5900 | 994480.8 | 0 | 0 | [7 empty] | 5900 | 994480.8 | 5900 | 994480.8
Sheath Pipe- Amjad Engineering Services | Piece | 550 | 0 | 0 | 550 | 55247.5 | 0 | 0 | [7 empty] | 550 | 55247.5 | 550 | 55247.5
Total Cost (Rs in Million) |  |  |  | 6179000 |  | 111727635.5765 |  | 6179000 | 11967747 |  | 5685539 |  | 61065688.115 |  | 5685539 |  | 38694200.4615 |  | 38694200.4615
[6 empty] | 50661947.4615 |  |  |  |  | 5.6855 |  | 61.0657

## Anx H (3) (hidden)
Anx "H" | [20 empty] | For the year updated.Update upto year along with hiring charges for the month
Detail of Equipments, Plants & Machinery & Vehicles
Project Control:- Mandra Chakwal Road Project
Project:- Dualization and improvement of Mandra - Chakwal Road Project
Ser | Regd No | Description | During the Month | [7 empty] | Upto Date |  |  |  |  | Year to Date
|  |  | Hours/Kms | Amount of hiring* (Rs) | Adjustment for previous months | Adjusted Hiring (Rs) | Amount of Fuel Issued | Amount of Fuel Adjustment for previous months | Adjusted POL (Rs) | Total Amount Payable | Hours/Kms | Amount of hiring* | Amount of Fuel Issued | Repair/ Maint | Total Amount Payable | Hours/Kms | Amount of hiring* | Amount of Fuel Issued | Repair/ Maint | Total Amount Payable
|  | Project hiring | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
1 | RIE-2556 | Water Bowzer Bed Ford | Kms | 0.037986 | -0.020171 | 0.017816 | 0.014353 |  |  | 0.032169 | Kms | 0.14545 | 0.028219 | 0 | 0.17367 | Kms | 0.12326 | 0.028219 | 0 | 0.15148
2 | TKG-877 | Water Bowzer Nissan | Kms | 0 | 0 | 0 | 0 |  |  | 0 | Kms | 0 | 0.067916 | 0 | 0.067916 | Kms | 0 | 0.067916 | 0 | 0.067916
3 | TKZ-119 | Nissan Dumper | Kms | 0.061838 | -0.032836 | 0.029002 | 0.033491 |  |  | 0.062493 | Kms | 0.45009 | 0.26258 | 0 | 0.71267 | Kms | 0.41397 | 0.26258 | 0 | 0.67655
4 | TKN 335 | Nissan Dumper | Kms | 0.061838 | -0.032836 | 0.029002 | 0.017543 |  |  | 0.046545 | Kms | 0.15029 | 0.15408 | 0 | 0.30436 | Kms | 0.11417 | 0.15408 | 0 | 0.26824
5 | TKY-854 | Hino Dumper | Kms | 0 | 0 | 0 | 0 |  |  | 0 | Kms | 0.47857 | 0.26456 | 0 | 0.74313 | Kms | 0.47857 | 0.26456 | 0 | 0.74313
6 | LSC-2574 | Hino Dumper | Kms | 0 | 0 | 0 | 0 |  |  | 0 | Kms | 0.43821 | 0.22668 | 0 | 0.66488 | Kms | 0.43821 | 0.22668 | 0 | 0.66488
7 | TKU-050 | Hino Dumper | Kms | 0 | 0 | 0 | 0 |  |  | 0 | Kms | 0.47857 | 0.28897 | 0 | 0.76754 | Kms | 0.47857 | 0.28897 | 0 | 0.76754
8 | TKV-342 | Hino Dumper | Kms | 0 | 0 | 0 | 0 |  |  | 0 | Kms | 0.12685 | 0.082092 | 0 | 0.20894 | Kms | 0.12685 | 0.082092 | 0 | 0.20894
9 | TKL 460 | Hino Dumper | Kms | 0 | 0 | 0 | 0 |  |  | 0 | Kms | 0.3171 | 0.18727 | 0 | 0.50437 | Kms | 0.3171 | 0.18727 | 0 | 0.50437
10 | LES 3203 | Hino Dumper | Kms | 0 | 0 | 0 | 0 |  |  | 0 | Kms | 0.3171 | 0.1857 | 0 | 0.5028 | Kms | 0.3171 | 0.1857 | 0 | 0.5028
11 | TKD 674 | Hino Dumper | Kms | 0 | 0 | 0 | 0 |  |  | 0 | Kms | 0.27962 | 0.12399 | 0 | 0.40361 | Kms | 0.27962 | 0.12399 | 0 | 0.40361
12 | TKA 263 | Hino Dumper | Kms | 0 | 0 | 0 | 0 |  |  | 0 | Kms | 0.44227 | 0.22673 | 0 | 0.66901 | Kms | 0.48317 | 0.22673 | 0 | 0.7099
13 | TKU 489 | Hino Dumper | Kms | 0.061838 | -0.032836 | 0.029002 | 0.019138 |  |  | 0.04814 | Kms | 0.51928 | 0.23184 | 0 | 0.75113 | Kms | 0.48317 | 0.23184 | 0 | 0.71501
14 | P 6505 | Hino Dumper | Kms | 0.061838 | -0.032836 | 0.029002 | 0.019138 |  |  | 0.04814 | Kms | 0.51928 | 0.22809 | 0 | 0.74737 | Kms | 0.48317 | 0.22809 | 0 | 0.71126
15 | TKW 705 | Hino Dumper | Kms | 0 | 0 | 0 | 0 |  |  | 0 | Kms | 0.23062 | 0.1472 | 0 | 0.37782 | Kms | 0.23062 | 0.1472 | 0 | 0.37782
16 | TAD-070 | Hino Dumper | Kms | 0 | 0 | 0 | 0 |  |  | 0 | Kms | 0.14991 | 0.11373 | 0 | 0.26364 | Kms | 0.14991 | 0.11373 | 0 | 0.26364
17 | P 8346 | Hino Dumper | Kms | 0 | 0 | 0 | 0 |  |  | 0 | Kms | 0.28251 | 0.166 | 0 | 0.4485 | Kms | 0.28251 | 0.166 | 0 | 0.4485
18 | SAE 815 | Hino Dumper | Kms | 0 | 0 | 0 | 0 |  |  | 0 | Kms | 0.32287 | 0.19444 | 0 | 0.51731 | Kms | 0.32287 | 0.19444 | 0 | 0.51731
19 | TKD 438 | Hino Dumper | Kms | 0.061838 | -0.032836 | 0.029002 | 0.033491 |  |  | 0.062493 | Kms | 0.5827 | 0.2336 | 0 | 0.8163 | Kms | 0.54658 | 0.2336 | 0 | 0.78019
20 | TKC 230 | Hino Dumper | Kms | 0 | 0 | 0 | 0 |  |  | 0 | Kms | 0.32863 | 0.20804 | 0 | 0.53668 | Kms | 0.32863 | 0.20804 | 0 | 0.53668
21 | 1443 | Excavator | Hours | 0 | 0 | 0 | 0 |  |  | 0 | Hours | 0.34339 | 0.39021 | 0 | 0.7336 | Hours | 0.34339 | 0.39021 | 0 | 0.7336
22 | YX-04 JWZ | Excavator DX | Hours | 0.064047 | -0.034009 | 0.030038 | 0.094093 |  |  | 0.12413 | Hours | 0.71698 | 0.7046 | 0 | 1.4216 | Hours | 0.67957 | 0.7046 | 0 | 1.3842
23 | S-620402 | Motor Grader | Hours | 0.11622 | -0.061713 | 0.054507 | 0.18978 |  |  | 0.24429 | Hours | 0.72677 | 0.4773 | 0 | 1.2041 | Hours | 0.65889 | 0.4773 | 0 | 1.1362
24 | GD 505 | Motor Grader | Hours | 0 | 0 | 0 | 0 |  |  | 0 | Hours | 0.84934 | 0.42479 | 0 | 1.2741 | Hours | 0.84934 | 0.42479 | 0 | 1.2741
25 | GD-605 | Motor Grader | Hours | 0.11622 | -0.061713 | 0.054507 | 0.14417 |  |  | 0.19868 | Hours | 1.161 | 0.92585 | 0 | 2.0869 | Hours | 1.1682 | 0.92585 | 0 | 2.0941
26 | GD-611 | Motor Grader | Hours | 0.11622 | -0.061713 | 0.054507 | 0.046249 |  |  | 0.10076 | Hours | 1.2686 | 0.65678 | 0 | 1.9254 | Hours | 1.2007 | 0.65678 | 0 | 1.8575
27 | 710 | Motor Grader | Hours | 0 | 0 | 0 | 0 |  |  | 0 | Hours | 0.67731 | 0.43959 | 0 | 1.1169 | Hours | 0.67731 | 0.43959 | 0 | 1.1169
28 | 140 | Motor Grader | Hours | 0 | 0 | 0 | 0 |  |  | 0 | Hours | 0.58519 | 0.26349 | 0 | 0.84868 | Hours | 0.58519 | 0.26349 | 0 | 0.84868
29 | CA-251 | Plain Roller | Hours | 0.084064 | -0.044638 | 0.039426 | 0.017543 |  |  | 0.056969 | Hours | 0.90978 | 0.17985 | 0 | 1.0896 | Hours | 0.86068 | 0.17985 | 0 | 1.0405
30 | 2420 | Plain Roller | Hours | 0 | 0 | 0 | 0 |  |  | 0 | Hours | 0.49383 | 0.096674 | 0 | 0.5905 | Hours | 0.49383 | 0.096674 | 0 | 0.5905
31 | D-2420 | Plain Roller | Hours | 0.084064 | -0.044638 | 0.039426 | 0.011164 |  |  | 0.05059 | Hours | 0.70597 | 0.18401 | 0 | 0.88999 | Hours | 0.65687 | 0.18401 | 0 | 0.84089
32 | CA-301 | Plain Roller | Hours | 0.084064 | -0.044638 | 0.039426 | 0.017543 |  |  | 0.056969 | Hours | 0.91762 | 0.12134 | 0 | 1.039 | Hours | 0.86851 | 0.12134 | 0 | 0.98985
33 | CA- 301 | Plain Roller | Hours | 0.084064 | -0.044638 | 0.039426 | 0.024321 |  |  | 0.063747 | Hours | 0.90488 | 0.20908 | 0 | 1.114 | Hours | 0.85578 | 0.20908 | 0 | 1.0649
34 | C-251 | Sheep foot Roller | Hours | 0.084064 | -0.044638 | 0.039426 | 0.035086 |  |  | 0.074512 | Hours | 0.88626 | 0.26929 | 0 | 1.1556 | Hours | 0.83716 | 0.26929 | 0 | 1.1065
35 | TA-251 | Sheep foot Roller | Hours | 0.084064 | -0.044638 | 0.039426 | 0.022327 |  |  | 0.061753 | Hours | 0.91762 | 0.21905 | 0 | 1.1367 | Hours | 0.86851 | 0.21905 | 0 | 1.0876
36 | CA-262 | Sheep foot Roller | Hours | 0 | 0 | 0 | 0 |  |  | 0 | Hours | 0.69763 | 0.2018 | 0 | 0.89943 | Hours | 0.69763 | 0.2018 | 0 | 0.89943
37 | 2420 | Sheep foot Roller | Hours | 0.084064 | -0.044638 | 0.039426 | 0.027112 |  |  | 0.066538 | Hours | 0.69814 | 0.15984 | 0 | 0.85798 | Hours | 0.64903 | 0.15984 | 0 | 0.80888
38 | 2510 SSD | Sheep foot Roller | Hours | 0 | 0 | 0 | 0 |  |  | 0 | Hours | 0.40173 | 0.12861 | 0 | 0.53034 | Hours | 0.40173 | 0.12861 | 0 | 0.53034
39 | LXK 5415 | Tractor 480 Fiat | Hours | 0.019877 | -0.010554 | 0.0093221 | 0.023922 |  |  | 0.033244 | Hours | 0.076108 | 0.078192 | 0 | 0.1543 | Hours | 0.064498 | 0.078192 | 0 | 0.14269
40 | JGB 8823 | Tractor 480 Fiat with Plough | Hours | 0.019877 | -0.010554 | 0.0093221 | 0.023523 |  |  | 0.032845 | Hours | 0.10391 | 0.094525 | 0 | 0.19843 | Hours | 0.092299 | 0.094525 | 0 | 0.18682
41 | VRA-4256 | Tractor 480 Fiat with Tank | Hours | 0.019877 | -0.010554 | 0.0093221 | 0.020732 |  |  | 0.030054 | Hours | 0.10391 | 0.046176 | 0 | 0.15009 | Hours | 0.092299 | 0.046176 | 0 | 0.13848
42 | SAC-4742 | Tractor 480 Fiat with Tank | Hours | 0.019877 | -0.010554 | 0.0093221 | 0.011961 |  |  | 0.021283 | Hours | 0.094183 | 0.077625 | 0 | 0.17181 | Hours | 0.082573 | 0.077625 | 0 | 0.1602
43 | RID 4091 | Water Bowzer Bed Ford | Kms | 0 | 0 | 0 | 0 |  |  | 0 | Kms | 0.10744 | 0.013507 | 0 | 0.12095 | Kms | 0.10744 | 0.013507 | 0 | 0.12095
44 | AJK-8883 | Water Bowzer Bed Ford | Kms | 0 | 0 | 0 | 0 |  |  | 0 | Kms | 0.19127 | 0.060316 | 0 | 0.25158 | Kms | 0.19127 | 0.060316 | 0 | 0.25158
45 | MDXA-17 | Water Bowzer Bed Ford | Kms | 0 | 0 | 0 | 0 |  |  | 0 | Kms | 0.092092 | 0.01308 | 0 | 0.10517 | Kms | 0.092092 | 0.01308 | 0 | 0.10517
46 | C-2392 | Water Bowzer Bed Ford | Kms | 0 | 0 | 0 | 0 |  |  | 0 | Kms | 0.092092 | 0.025942 | 0 | 0.11803 | Kms | 0.092092 | 0.025942 | 0 | 0.11803
47 | LET 8609 | Water Bowzer Bed Ford | Kms | 0 | 0 | 0 | 0 |  |  | 0 | Kms | 0 | 0.03117 | 0 | 0.03117 | Kms | 0 | 0.03117 | 0 | 0.03117
48 | TKB 996 | Hino Dumper | Kms | 0 | 0 | 0 | 0 |  |  | 0 | Kms | 0.29984 | 0.075563 | 0 | 0.3754 | Kms | 0.29984 | 0.075563 | 0 | 0.3754
49 | FG 85 | Motor Grader | Hours | 0 | 0 | 0 | 0 |  |  | 0 | Hours | 0.53101 | 0.35937 | 0 | 0.89038 | Hours | 0.53101 | 0.35937 | 0 | 0.89038
51 | MNE-6752 | Tractor 480 Fiat | Hours | 0 | 0 | 0 | 0 |  |  | 0 | Hours | 0 | 0.0074741 | 0 | 0.0074741 | Hours | 0 | 0.0074741 | 0 | 0.0074741
52 | 437 | Hino Dumper | Kms | 0 | 0 | 0 | 0 |  |  | 0 | Kms | 0 | 0.060897 | 0 | 0.060897 | Kms | 0 | 0.060897 | 0 | 0.060897
53 | TKZ-119 | Nissan Dumper | Kms | 0 | 0 | 0 | 0 |  |  | 0 | Kms | 0.086767 | 0.052162 | 0 | 0.13893 | Kms | 0.086491 | 0.052162 | 0 | 0.13865
54 | TKN 335 | Nissan Dumper | Kms | 0 | 0 | 0 | 0 |  |  | 0 | Kms | 0.369 | 0.041046 | 0 | 0.41004 | Kms | 0.369 | 0.041046 | 0 | 0.41004
55 | 114 | Motor Grader | Hours | 0 | 0 | 0 | 0 |  |  | 0 | Hours | 0 | 0.069291 | 0 | 0.069291 | Hours | 0 | 0.069291 | 0 | 0.069291
56 | GLT-3116 | Water Bowzer Bed Ford | Hours | 0 | 0 | 0 | 0 |  |  | 0 | Hours | 0.046046 | 0.013682 | 0 | 0.059728 | Hours | 0.046046 | 0.013682 | 0 | 0.059728
57 | EA-2612 | Hino Dumper | Hours | 0 | 0 | 0 | 0 |  |  | 0 | Hours | 0.086491 | 0.061569 | 0 | 0.14806 | Hours | 0.086491 | 0.061569 | 0 | 0.14806
58 | 655 | Motor Grader | Hours | 0.11622 | -0.061713 | 0.054507 | 0.13396 |  |  | 0.18847 | Hours | 0.31828 | 0.16418 | 0 | 0.48246 | Hours | 0.3121 | 0.16418 | 0 | 0.47629
59 |  | Diesel Engine (WP) Jatli | Hours | 0 | 0 | 0 | 0 |  |  | 0 | Hours | 0 | 0.012741 | 0 | 0.012741 | Hours | 0 | 0.012741 | 0 | 0.012741
60 |  | Diesel Engine (WP) | Hours | 0 | 0 | 0 | 0.0031896 |  |  | 0.0031896 | Hours | 0 | 0.011972 | 0 | 0.011972 | Hours | 0 | 0.011972 | 0 | 0.011972
61 |  | Gen Set Jatli | Hours | 0 | 0 | 0 | 0.023922 |  |  | 0.023922 | Hours | 0 | 0.050452 | 0 | 0.050452 | Hours | 0 | 0.050452 | 0 | 0.050452
62 |  | Gen Set Mandra | Hours | 0 | 0 | 0 | 0.055818 |  |  | 0.055818 | Hours | 0 | 0.03848 | 0 | 0.03848 | Hours | 0 | 0.03848 | 0 | 0.03848
63 | 605 K | Motor Grader | Hours | 0.11622 | -0.061713 | 0.054507 | 0.065387 |  |  | 0.11989 |  | 0.054507
64 | G-06 | Motor Grader | Hours | 0.11622 | -0.061713 | 0.054507 | 0.04306 |  |  | 0.097567 |  | 0.054507
65 | kb-559 | water Bowzer B/Ford | Hours | 0.037986 | -0.020171 | 0.017816 | 0.014353 |  |  | 0.032169 |  | 0.017816
66 | TKN615 | Dumper Nissan | Hours | 0.061838 | -0.032836 | 0.029002 | 0.015948 |  |  | 0.04495 |  | 0.029002
67 | TKC-695 | Dumper Nissan | Hours | 0.061838 | -0.032836 | 0.029002 | 0.015948 |  |  | 0.04495 |  | 0.029002
68 | TKB-045 | dumper Nissan | Hours | 0.061838 | -0.032836 | 0.029002 | 0.015948 |  |  | 0.04495 |  | 0.029002
Subtotal of Hired Machinery |  |  |  | 2 | -1.062 | 0.938 | 1.2342 |  |  | 2.1722 |  | 23.2342 | 11.1333 |  | 34.1537 |  | 22.296 | 11.1333 |  | 33.4292
Owned Vehicles
1 | RIC-11-311 | Toyota Hilux D/Cabin | Kms | 0 |  |  | 0.040428 |  |  | 0.040428 | Kms | 0 | 0.31006 |  | 0.31006 | Kms | 0 | 0.31006 | 0 | 0.31006
2 | RIC-11-292 | Toyota Hilux D/Cabin | Kms | 0 |  |  | 0.025357 |  |  | 0.025357 | Kms | 0 | 0.32659 |  | 0.32659 | Kms | 0 | 0.32659 | 0 | 0.32659
3 | 858524 | Toyota Hilux S/Cabin | Kms | 0 |  |  | 0 |  |  | 0 | Kms | 0 | 0 |  | 0 | Kms | 0 | 0 | 0 | 0
4 | RIC-11-297 | Toyota Hilux S/Cabin | Kms | 0 |  |  | 0.034846 |  |  | 0.034846 | Kms | 0 | 0.18356 |  | 0.18356 | Kms | 0 | 0.18356 | 0 | 0.18356
5 | RIC-11-299 | Toyota Hilux S/Cabin | Kms | 0 |  |  | 0.039471 |  |  | 0.039471 | Kms | 0 | 0.16992 |  | 0.16992 | Kms | 0 | 0.16992 | 0 | 0.16992
6 | RIC-11-303 | Toyota Hilux S/Cabin | Kms | 0 |  |  | 0.053187 |  |  | 0.053187 | Kms | 0 | 0.15778 |  | 0.15778 | Kms | 0 | 0.15778 | 0 | 0.15778
7 | 895660 | Toyota Hilux S/Cabin | Kms | 0 |  |  | 0.029504 |  |  | 0.029504 | Kms | 0 | 0.28423 |  | 0.28423 | Kms | 0 | 0.28423 | 0 | 0.28423
8 | 895521 | Toyota Hilux S/Cabin | Kms | 0 |  |  | 0.038355 |  |  | 0.038355 | Kms | 0 | 0.33526 |  | 0.33526 | Kms | 0 | 0.33526 | 0 | 0.33526
9 | RIC-11-306 | Toyota Hilux S/Cabin | Kms | 0 |  |  | 0 |  |  | 0 | Kms | 0 | 0 |  | 0 | Kms | 0 | 0 | 0 | 0
10 | 882437 | Hyundai Shahzore | Kms | 0 |  |  | 0.012918 |  |  | 0.012918 | Kms | 0 | 0.045639 |  | 0.045639 | Kms | 0 | 0.045639 | 0 | 0.045639
11 | 882411 | Hyundai Shahzore | Kms | 0 |  |  | 0.025277 |  |  | 0.025277 | Kms | 0 | 0.072658 |  | 0.072658 | Kms | 0 | 0.072658 | 0 | 0.072658
14 | 895358 | Motor Cycle Pak Hero -70CC | Kms | 0 |  |  | 0 |  |  | 0 | Kms | 0 | 0 |  | 0 | Kms | 0 | 0 | 0 | 0
14 | 895325 | Motor Cycle Pak Hero -70CC | Kms | 0 |  |  | 0 |  |  | 0 | Kms | 0 | 0 |  | 0 | Kms | 0 | 0 | 0 | 0
14 | 895370 | Motor Cycle Pak Hero -70CC | Kms | 0 |  |  | 0.0018851 |  |  | 0.0018851 | Kms | 0 | 0.002222 |  | 0.002222 | Kms | 0 | 0.002222 | 0 | 0.002222
16 | 895365 | Motor Cycle Pak Hero -70CC | Kms | 0 |  |  | 0 |  |  | 0 | Kms | 0 | 0 |  | 0 | Kms | 0 | 0 | 0 | 0
17 | 895355 | Motor Cycle Pak Hero -70CC | Kms | 0 |  |  | 0 |  |  | 0 | Kms | 0 | 0 |  | 0 | Kms | 0 | 0 | 0 | 0
18 | 858524 | Water Bowzer | Kms |  |  |  | 0.010366 |  |  |  | Kms |  | 0.057734 |  | 0.057734 |  |  | 0.057734 |  | 0.057734
Subtotal of Vehicles |  |  |  | 0 |  |  | 0.31159 |  |  | 0.30123 |  |  | 1.9456 |  | 1.9456 |  |  | 1.9456 |  | 1.9456
Total Amounts Rs in Million |  |  |  | 2 |  |  | 1.5458 |  |  | 2.4734 |  | 23.2342 | 13.0789 | 0 | 36.0993 |  | 22.296 | 13.0789 | 0 | 35.3749
1.062
[7 empty] | 0.30123 | [5 empty] | 6425.9609
0.006426
13.0854
13.0789
15.3274
14.6248
0.70264
8890991
|  | 895660Toyota Hilux D/Cabin 4x2 | 347 | 108.64 |  |  | 37698.08
|  | 895521 Toyota Hilux D/Cabin | 485 | 108.64 |  |  | 52690.4
|  | RIC-11-292 Toyota Hilux D/Cabin | 272 | 108.64 |  |  | 29550.08
|  | RIC-11-296 Toyota Hilux D/Cabin | 398 | 108.64 |  |  | 43238.72
|  | RIC-11-295 Toyota Hilux D/Cabin | 207 | 108.64 |  |  | 22488.48
|  | RIC-11-311Toyota Hilux D/Cabin | 422 | 108.64 |  |  | 45846.08
|  | RIC-11-301Toyota Hilux S/Cabin | 485 | 108.64 |  |  | 52690.4
|  | RIC-11-297Toyota Hilux S/Cabin | 64 | 108.64 |  |  | 6952.96
|  | RIC-11-299Toyota Hilux S/Cabin | 125 | 108.64 |  |  | 13580
|  | RIC-11-303Toyota Hilux S/Cabin | 75 | 108.64 |  |  | 8148
|  | RIC-11-306 Toyota Hilux S/Cabin | 185 | 108.64 |  |  | 20098.4
|  | 882437 Hyundai Shahzore | 63 | 108.64 |  |  | 6844.32
|  | 882411 Hyundai Shahzore | 25 | 108.64 |  |  | 2716
895725 Motor Cycle Pak Hero -70CC
895715 Motor Cycle Pak Hero -70CC
895358 Motor Cycle Pak Hero -70CC
895370 Motor Cycle Pak Hero -70CC
895365Motor Cycle Pak Hero -70CC
895355 Motor Cycle Pak Hero -70CC

## Anx H (2) (hidden)
Anx "H" | [18 empty] | For the year updated.Update upto year along with hiring charges for the month
Detail of Equipments, Plants & Machinery & Vehicles
Project Control:- Mandra Chakwal Road Project
Project:- Dualization and improvement of Mandra - Chakwal Road Project
Ser | Regd No | Description | During the Month | [5 empty] | Upto Date |  |  |  |  | Year to Date
|  |  | Hours/Kms | Amount of hiring* (Rs) | Amount of Fuel Issued | Total Amount Payable | Adjustments in POL for previous months | Total Amount Payable after adj | Hours/Kms | Amount of hiring* | Amount of Fuel Issued | Repair/ Maint | Total Amount Payable | Hours/Kms | Amount of hiring* | Amount of Fuel Issued | Repair/ Maint | Total Amount Payable
|  | Project hiring | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
1 | RIE-2556 | Water Bowzer Bed Ford | Kms | 0.047309 | 0.0034188 | 0.050727 |  |  | Kms | 0.049615 | 0.024786 | 0 | 0.074402 | Kms | 0.049615 | 0.024786 | 0 | 0.074402
2 | TKG-877 | Water Bowzer Nissan | Kms | 0 | 0 | 0 |  |  | Kms | 0 | 0.067883 | 0 | 0.067883 | Kms | 0 | 0.067883 | 0 | 0.067883
3 | TKZ-119 | Nissan Dumper | Kms | 0.077014 | 0 | 0.077014 |  |  | Kms | 0.27997 | 0.26245 | 0 | 0.54242 | Kms | 0.27997 | 0.26245 | 0 | 0.54242
4 | TKN 335 | Nissan Dumper | Kms | 0.077014 | 0.0068376 | 0.083852 |  |  | Kms | 0 | 0.14716 | 0 | 0.14716 | Kms | 0 | 0.14716 | 0 | 0.14716
5 | TKY-854 | Hino Dumper | Kms | 0 | 0 | 0 |  |  | Kms | 0.44691 | 0.26443 | 0 | 0.71134 | Kms | 0.44691 | 0.26443 | 0 | 0.71134
6 | LSC-2574 | Hino Dumper | Kms | 0 | 0 | 0 |  |  | Kms | 0.40922 | 0.22656 | 0 | 0.63578 | Kms | 0.40922 | 0.22656 | 0 | 0.63578
7 | TKU-050 | Hino Dumper | Kms | 0 | 0 | 0 |  |  | Kms | 0.44691 | 0.28883 | 0 | 0.73574 | Kms | 0.44691 | 0.28883 | 0 | 0.73574
8 | TKV-342 | Hino Dumper | Kms | 0 | 0 | 0 |  |  | Kms | 0.11846 | 0.082051 | 0 | 0.20051 | Kms | 0.11846 | 0.082051 | 0 | 0.20051
9 | TKL 460 | Hino Dumper | Kms | 0 | 0 | 0 |  |  | Kms | 0.29612 | 0.18717 | 0 | 0.4833 | Kms | 0.29612 | 0.18717 | 0 | 0.4833
10 | LES 3203 | Hino Dumper | Kms | 0 | 0 | 0 |  |  | Kms | 0.29612 | 0.18561 | 0 | 0.48173 | Kms | 0.29612 | 0.18561 | 0 | 0.48173
11 | TKD 674 | Hino Dumper | Kms | 0 | 0 | 0 |  |  | Kms | 0.26112 | 0.12393 | 0 | 0.38505 | Kms | 0.26112 | 0.12393 | 0 | 0.38505
12 | TKA 263 | Hino Dumper | Kms | 0.077014 | 0.010256 | 0.08727 |  |  | Kms | 0.34458 | 0.21637 | 0 | 0.56095 | Kms | 0.34458 | 0.21637 | 0 | 0.56095
13 | TKU 489 | Hino Dumper | Kms | 0.077014 | 0.008547 | 0.085561 |  |  | Kms | 0.34458 | 0.22318 | 0 | 0.56777 | Kms | 0.34458 | 0.22318 | 0 | 0.56777
14 | P 6505 | Hino Dumper | Kms | 0.077014 | 0.008547 | 0.085561 |  |  | Kms | 0.34458 | 0.21943 | 0 | 0.56402 | Kms | 0.34458 | 0.21943 | 0 | 0.56402
15 | TKW 705 | Hino Dumper | Kms | 0 | 0 | 0 |  |  | Kms | 0.21536 | 0.14713 | 0 | 0.36249 | Kms | 0.21536 | 0.14713 | 0 | 0.36249
16 | TAD-070 | Hino Dumper | Kms | 0 | 0 | 0 |  |  | Kms | 0.13999 | 0.11368 | 0 | 0.25367 | Kms | 0.13999 | 0.11368 | 0 | 0.25367
17 | P 8346 | Hino Dumper | Kms | 0 | 0 | 0 |  |  | Kms | 0.26382 | 0.16592 | 0 | 0.42973 | Kms | 0.26382 | 0.16592 | 0 | 0.42973
18 | SAE 815 | Hino Dumper | Kms | 0 | 0 | 0 |  |  | Kms | 0.30151 | 0.19434 | 0 | 0.49585 | Kms | 0.30151 | 0.19434 | 0 | 0.49585
19 | TKD 438 | Hino Dumper | Kms | 0.077014 | 0.008547 | 0.085561 |  |  | Kms | 0.40381 | 0.22494 | 0 | 0.62875 | Kms | 0.40381 | 0.22494 | 0 | 0.62875
20 | TKC 230 | Hino Dumper | Kms | 0 | 0 | 0 |  |  | Kms | 0.30689 | 0.20794 | 0 | 0.51483 | Kms | 0.30689 | 0.20794 | 0 | 0.51483
21 | 1443 | Excavator | Hours | 0 | 0 | 0 |  |  | Hours | 0.32068 | 0.39002 | 0 | 0.71069 | Hours | 0.32068 | 0.39002 | 0 | 0.71069
22 | YX-04 JWZ | Excavator DX | Hours | 0.079765 | 0.047863 | 0.12763 |  |  | Hours | 0.52419 | 0.65639 | 0 | 1.1806 | Hours | 0.52419 | 0.65639 | 0 | 1.1806
23 | S-620402 | Motor Grader | Hours | 0.14474 | 0.082051 | 0.22679 |  |  | Hours | 0.41492 | 0.39501 | 0 | 0.80993 | Hours | 0.41492 | 0.39501 | 0 | 0.80993
24 | GD 505 | Motor Grader | Hours | 0 | 0 | 0 |  |  | Hours | 0.79316 | 0.42458 | 0 | 1.2177 | Hours | 0.79316 | 0.42458 | 0 | 1.2177
25 | GD-605 | Motor Grader | Hours | 0.14474 | 0.063248 | 0.20799 |  |  | Hours | 0.89056 | 0.86215 | 0 | 1.7527 | Hours | 0.89056 | 0.86215 | 0 | 1.7527
26 | GD-611 | Motor Grader | Hours | 0.14474 | 0.049573 | 0.19431 |  |  | Hours | 0.92092 | 0.60688 | 0 | 1.5278 | Hours | 0.92092 | 0.60688 | 0 | 1.5278
27 | 710 | Motor Grader | Hours | 0 | 0 | 0 |  |  | Hours | 0.6325 | 0.43937 | 0 | 1.0719 | Hours | 0.6325 | 0.43937 | 0 | 1.0719
28 | 140 | Motor Grader | Hours | 0 | 0 | 0 |  |  | Hours | 0.54648 | 0.26336 | 0 | 0.80984 | Hours | 0.54648 | 0.26336 | 0 | 0.80984
29 | CA-251 | Plain Roller | Hours | 0.1047 | 0 | 0.1047 |  |  | Hours | 0.6588 | 0.17976 | 0 | 0.83856 | Hours | 0.6588 | 0.17976 | 0 | 0.83856
30 | 2420 | Plain Roller | Hours | 0 | 0 | 0 |  |  | Hours | 0.46116 | 0.096627 | 0 | 0.55779 | Hours | 0.46116 | 0.096627 | 0 | 0.55779
31 | D-2420 | Plain Roller | Hours | 0.1047 | 0.0051282 | 0.10982 |  |  | Hours | 0.46848 | 0.1788 | 0 | 0.64728 | Hours | 0.46848 | 0.1788 | 0 | 0.64728
32 | CA-301 | Plain Roller | Hours | 0.1047 | 0.0068376 | 0.11153 |  |  | Hours | 0.66612 | 0.11444 | 0 | 0.78056 | Hours | 0.66612 | 0.11444 | 0 | 0.78056
33 | CA- 301 | Plain Roller | Hours | 0.1047 | 0.0034188 | 0.10811 |  |  | Hours | 0.65422 | 0.20556 | 0 | 0.85978 | Hours | 0.65422 | 0.20556 | 0 | 0.85978
34 | C-251 | Sheep foot Roller | Hours | 0.1047 | 0.008547 | 0.11324 |  |  | Hours | 0.63684 | 0.26061 | 0 | 0.89745 | Hours | 0.63684 | 0.26061 | 0 | 0.89745
35 | TA-251 | Sheep foot Roller | Hours | 0.1047 | 0.0068376 | 0.11153 |  |  | Hours | 0.66612 | 0.21211 | 0 | 0.87823 | Hours | 0.66612 | 0.21211 | 0 | 0.87823
36 | CA-262 | Sheep foot Roller | Hours | 0 | 0 | 0 |  |  | Hours | 0.65148 | 0.2017 | 0 | 0.85318 | Hours | 0.65148 | 0.2017 | 0 | 0.85318
37 | 2420 | Sheep foot Roller | Hours | 0.1047 | 0 | 0.1047 |  |  | Hours | 0.46116 | 0.15976 | 0 | 0.62092 | Hours | 0.46116 | 0.15976 | 0 | 0.62092
38 | 2510 SSD | Sheep foot Roller | Hours | 0 | 0 | 0 |  |  | Hours | 0.37515 | 0.12855 | 0 | 0.5037 | Hours | 0.37515 | 0.12855 | 0 | 0.5037
39 | LXK 5415 | Tractor 480 Fiat | Hours | 0.024754 | 0.013675 | 0.03843 |  |  | Hours | 0.025962 | 0.064478 | 0 | 0.09044 | Hours | 0.025962 | 0.064478 | 0 | 0.09044
40 | JGB 8823 | Tractor 480 Fiat with Plough | Hours | 0.024754 | 0.013675 | 0.03843 |  |  | Hours | 0.051924 | 0.080804 | 0 | 0.13273 | Hours | 0.051924 | 0.080804 | 0 | 0.13273
41 | VRA-4256 | Tractor 480 Fiat with Tank | Hours | 0.024754 | 0.0068376 | 0.031592 |  |  | Hours | 0.051924 | 0.039316 | 0 | 0.09124 | Hours | 0.051924 | 0.039316 | 0 | 0.09124
42 | SAC-4742 | Tractor 480 Fiat with Tank | Hours | 0.024754 | 0.0034188 | 0.028173 |  |  | Hours | 0.042841 | 0.074168 | 0 | 0.11701 | Hours | 0.042841 | 0.074168 | 0 | 0.11701
43 | RID 4091 | Water Bowzer Bed Ford | Kms | 0 | 0 | 0 |  |  | Kms | 0.10033 | 0.0135 | 0 | 0.11383 | Kms | 0.10033 | 0.0135 | 0 | 0.11383
44 | AJK-8883 | Water Bowzer Bed Ford | Kms | 0 | 0 | 0 |  |  | Kms | 0.17862 | 0.060286 | 0 | 0.2389 | Kms | 0.17862 | 0.060286 | 0 | 0.2389
45 | MDXA-17 | Water Bowzer Bed Ford | Kms | 0 | 0 | 0 |  |  | Kms | 0.086 | 0.013073 | 0 | 0.099073 | Kms | 0.086 | 0.013073 | 0 | 0.099073
46 | C-2392 | Water Bowzer Bed Ford | Kms | 0 | 0 | 0 |  |  | Kms | 0.086 | 0.025929 | 0 | 0.11193 | Kms | 0.086 | 0.025929 | 0 | 0.11193
47 | LET 8609 | Water Bowzer Bed Ford | Kms | 0 | 0 | 0 |  |  | Kms | 0 | 0.031155 | 0 | 0.031155 | Kms | 0 | 0.031155 | 0 | 0.031155
48 | TKB 996 | Hino Dumper | Kms | 0 | 0 | 0 |  |  | Kms | 0.28 | 0.075526 | 0 | 0.35553 | Kms | 0.28 | 0.075526 | 0 | 0.35553
49 | FG 85 | Motor Grader | Hours | 0 | 0 | 0 |  |  | Hours | 0.49588 | 0.35919 | 0 | 0.85507 | Hours | 0.49588 | 0.35919 | 0 | 0.85507
51 | MNE-6752 | Tractor 480 Fiat | Hours | 0 | 0 | 0 |  |  | Hours | 0 | 0.0074704 | 0 | 0.0074704 | Hours | 0 | 0.0074704 | 0 | 0.0074704
52 | 437 | Hino Dumper | Kms | 0 | 0 | 0 |  |  | Kms | 0 | 0.060867 | 0 | 0.060867 | Kms | 0 | 0.060867 | 0 | 0.060867
53 | TKZ-119 | Nissan Dumper | Kms | 0 | 0.008547 | 0.008547 |  |  | Kms | 0.080769 | 0.04359 | 0 | 0.12436 | Kms | 0.080769 | 0.04359 | 0 | 0.12436
54 | TKN 335 | Nissan Dumper | Kms | 0 | 0 | 0 |  |  | Kms | 0.34459 | 0.041026 | 0 | 0.38561 | Kms | 0.34459 | 0.041026 | 0 | 0.38561
55 | 114 | Motor Grader | Hours | 0 | 0 | 0 |  |  | Hours | 0 | 0.069257 | 0 | 0.069257 | Hours | 0 | 0.069257 | 0 | 0.069257
56 | GLT-3116 | Water Bowzer Bed Ford | Hours | 0 | 0 | 0 |  |  | Hours | 0.043 | 0.013675 | 0 | 0.056675 | Hours | 0.043 | 0.013675 | 0 | 0.056675
57 | EA-2612 | Hino Dumper | Hours | 0 | 0 | 0 |  |  | Hours | 0.080769 | 0.061538 | 0 | 0.14231 | Hours | 0.080769 | 0.061538 | 0 | 0.14231
58 | 655 | Motor Grader | Hours | 0.14474 | 0.059829 | 0.20457 |  |  | Hours | 0.09108 | 0.10427 | 0 | 0.19535 | Hours | 0.09108 | 0.10427 | 0 | 0.19535
59 |  | Diesel Engine (WP) Jatli | Hours | 0 | 0.0008547 | 0.0008547 |  |  | Hours | 0 | 0.01188 | 0 | 0.01188 | Hours | 0 | 0.01188 | 0 | 0.01188
60 |  | Diesel Engine (WP) | Hours | 0 | 0 | 0 |  |  | Hours | 0 | 0.011966 | 0 | 0.011966 | Hours | 0 | 0.011966 | 0 | 0.011966
61 |  | Gen Set Jatli | Hours | 0 | 0.022222 | 0.022222 |  |  | Hours | 0 | 0.028205 | 0 | 0.028205 | Hours | 0 | 0.028205 | 0 | 0.028205
62 |  | Gen Set Mandra | Hours | 0 | 0.026496 | 0.026496 |  |  | Hours | 0 | 0.011966 | 0 | 0.011966 | Hours | 0 | 0.011966 | 0 | 0.011966
0
Subtotal of Hired Machinery |  |  |  | 2 | 0.47521 | 2.4752 | 0.54252 | -0.067303 |  | 18.0522 | 10.6526 |  | 28.7048 |  | 18.0522 | 10.6526 |  | 28.7048
Owned Vehicles
1 | RIC-11-311 | Toyota Hilux D/Cabin | Kms | 0 | 0.036581 | 0.036581 |  |  | Kms | 0 | 0.27332 |  | 0.27332 | Kms | 0 | 0.27332 | 0 | 0.27332
2 | RIC-11-292 | Toyota Hilux D/Cabin | Kms | 0 | 0.038547 | 0.038547 |  |  | Kms | 0 | 0.28789 |  | 0.28789 | Kms | 0 | 0.28789 | 0 | 0.28789
3 | 858524 | Toyota Hilux S/Cabin | Kms | 0 | 0 | 0 |  |  | Kms | 0 | 0 |  | 0 | Kms | 0 | 0 | 0 | 0
4 | RIC-11-297 | Toyota Hilux S/Cabin | Kms | 0 | 0.021453 | 0.021453 |  |  | Kms | 0 | 0.16202 |  | 0.16202 | Kms | 0 | 0.16202 | 0 | 0.16202
5 | RIC-11-299 | Toyota Hilux S/Cabin | Kms | 0 | 0.033504 | 0.033504 |  |  | Kms | 0 | 0.13633 |  | 0.13633 | Kms | 0 | 0.13633 | 0 | 0.13633
6 | RIC-11-303 | Toyota Hilux S/Cabin | Kms | 0 | 0.042479 | 0.042479 |  |  | Kms | 0 | 0.11522 |  | 0.11522 | Kms | 0 | 0.11522 | 0 | 0.11522
7 | 895660 | Toyota Hilux S/Cabin | Kms | 0 | 0.027692 | 0.027692 |  |  | Kms | 0 | 0.2564 |  | 0.2564 | Kms | 0 | 0.2564 | 0 | 0.2564
8 | 895521 | Toyota Hilux S/Cabin | Kms | 0 | 0.025299 | 0.025299 |  |  | Kms | 0 | 0.3098 |  | 0.3098 | Kms | 0 | 0.3098 | 0 | 0.3098
9 | RIC-11-306 | Toyota Hilux S/Cabin | Kms | 0 | 0 | 0 |  |  | Kms | 0 | 0 |  | 0 | Kms | 0 | 0 | 0 | 0
10 | 882437 | Hyundai Shahzore | Kms | 0 | 0.0025641 | 0.0025641 |  |  | Kms | 0 | 0.043053 |  | 0.043053 | Kms | 0 | 0.043053 | 0 | 0.043053
11 | 882411 | Hyundai Shahzore | Kms | 0 | 0.017607 | 0.017607 |  |  | Kms | 0 | 0.055015 |  | 0.055015 | Kms | 0 | 0.055015 | 0 | 0.055015
14 | 895358 | Motor Cycle Pak Hero -70CC | Kms | 0 | 0 | 0 |  |  | Kms | 0 | 0 |  | 0 | Kms | 0 | 0 | 0 | 0
14 | 895325 | Motor Cycle Pak Hero -70CC | Kms | 0 | 0 | 0 |  |  | Kms | 0 | 0 |  | 0 | Kms | 0 | 0 | 0 | 0
14 | 895370 | Motor Cycle Pak Hero -70CC | Kms | 0 | 0 | 0 |  |  | Kms | 0 | 0.0022209 |  | 0.0022209 | Kms | 0 | 0.0022209 | 0 | 0.0022209
16 | 895365 | Motor Cycle Pak Hero -70CC | Kms | 0 | 0 | 0 |  |  | Kms | 0 | 0 |  | 0 | Kms | 0 | 0 | 0 | 0
17 | 895355 | Motor Cycle Pak Hero -70CC | Kms | 0 | 0 | 0 |  |  | Kms | 0 | 0 |  | 0 | Kms | 0 | 0 | 0 | 0
18 | 858524 | Water Bowzer | Kms |  | 0.0068376 |  |  |  | Kms |  | 0.050868 |  | 0.050868 |  |  | 0.050868 |  | 0.050868
Subtotal of Vehicles |  |  |  | 0 | 0.24573 | 0.24573 | 0.072395 | 0.17333 |  |  | 1.6921 |  | 1.6921 |  |  | 1.6921 |  | 1.6921
Bill no 7
1 | RIC-11-295 | Toyota Hilux D/Cabin | Kms | 0 | 0.033248 | 0.033248 |  |  | Kms | 0 | 0.25991 |  | 0.25991 | Kms | 0 | 0.25991 | 0 | 0.25991
2 | RIC-11-296 | Toyota Hilux D/Cabin | Kms | 0 | 0 | 0 |  |  | Kms | 0 | 0.20507 |  | 0.20507 | Kms | 0 | 0.20507 | 0 | 0.20507
3 | RIC-11-301 | Toyota Hilux S/Cabin | Kms | 0 | 0 | 0 |  |  | Kms | 0 | 0.19343 |  | 0.19343 | Kms | 0 | 0.19343 | 0 | 0.19343
4 | RIC-11-306 | Toyota Hilux S/Cabin | Kms | 0 | 0 | 0 |  |  | Kms | 0 | 0.10719 |  | 0.10719 | Kms | 0 | 0.10719 | 0 | 0.10719
5 | RIC-11-294 | Toyota Hilux S/Cabin | Kms | 0 | 0 | 0 |  |  | Kms | 0 | 0.014084 |  | 0.014084 | Kms | 0 | 0.014084 | 0 | 0.014084
6 | IDE-8019 D/Cabin | Toyota Hilux S/Cabin | Kms | 0 | 0.024359 | 0.024359 |  |  | Kms | 0 | 0.082932 |  | 0.082932 | Kms | 0 | 0.082932 | 0 | 0.082932
Subtotal of Vehicles under bill no 7 |  |  |  |  | 0.057607 | 0.057607 | 0.018554 | 0.039053 |  |  | 0.86262 |  | 0.86262 |  |  | 0.86262 |  | 0.86262
Total Amounts Rs in Million |  |  |  | 2 | 0.77855 | 2.7786 | 0.63347 | 0.14508 |  | 18.0522 | 13.2074 | 0 | 31.2595 |  | 18.0522 | 13.2074 | 0 | 31.2595
|  |  |  | 2000009.572 | [8 empty] | 70534.22
[6 empty] | 0.92023 | [6 empty] | 0.070534 | 0.025962 | 0.01861
[6 empty] | 920225.42 | [7 empty] | 0.025962
8890991
|  | 895660Toyota Hilux D/Cabin 4x2 | 347 | 108.64 | 37698.08
|  | 895521 Toyota Hilux D/Cabin | 485 | 108.64 | 52690.4
|  | RIC-11-292 Toyota Hilux D/Cabin | 272 | 108.64 | 29550.08
|  | RIC-11-296 Toyota Hilux D/Cabin | 398 | 108.64 | 43238.72
|  | RIC-11-295 Toyota Hilux D/Cabin | 207 | 108.64 | 22488.48
|  | RIC-11-311Toyota Hilux D/Cabin | 422 | 108.64 | 45846.08
|  | RIC-11-301Toyota Hilux S/Cabin | 485 | 108.64 | 52690.4
|  | RIC-11-297Toyota Hilux S/Cabin | 64 | 108.64 | 6952.96
|  | RIC-11-299Toyota Hilux S/Cabin | 125 | 108.64 | 13580
|  | RIC-11-303Toyota Hilux S/Cabin | 75 | 108.64 | 8148
|  | RIC-11-306 Toyota Hilux S/Cabin | 185 | 108.64 | 20098.4
|  | 882437 Hyundai Shahzore | 63 | 108.64 | 6844.32
|  | 882411 Hyundai Shahzore | 25 | 108.64 | 2716
895725 Motor Cycle Pak Hero -70CC
895715 Motor Cycle Pak Hero -70CC
895358 Motor Cycle Pak Hero -70CC
895370 Motor Cycle Pak Hero -70CC
895365Motor Cycle Pak Hero -70CC
895355 Motor Cycle Pak Hero -70CC

## Anx H
Anx "H"
Detail of Equipments, Plants & Machinery & Vehicles
Project Control Unit:- Dev of C-15 Islamabad
Ser | Regd No | During the Month | [6 empty] | Upto Date |  |  |  |  | Year to Date
|  | Hours/Kms | Amount of hiring (Rs) | Adjustment for previous months | Amount of Fuel Issued | Amount of Fuel Adjustment for previous months | Adjusted POL (Rs) | Total Amount Payable | Hours/Kms | Amount of hiring* | Amount of Fuel Issued | Repair/ Maint | Total Amount Payable | Hours/Kms | Amount of hiring | Amount of Fuel Issued | Repair/ Maint | Total Amount Payable
Total Amounts Rs in Million |  |  | 0 | #REF! | 0 | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Anx J
Anx "J"
Status of Interim Payment Certificates
Project Control Unit:- Dev of C-15 Islamabad
Ser | IPC No | Date of Approval by Consultant / Client | Submission Date | Mob Adv | Vetted Work Done | Deduction | [5 empty] | Receivable from Client | Received From Client | Remarks
[6 empty] | Retention Money | Mob Adv | Water Charges | Rebate Exp | Deduction of Design Charges | Total
1 | Mob Adv I |  |  | 79352467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79352467 | 79352467 | Chq no 29128214 dated 10 Nov 2022
2 | Mob Adv II |  |  | 79352467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79352467 | 79352467
3 | IPC-I |  | 2023-06-01 | 0 | 142579457 | 14257946 | 0 | 712897 | 0 | 0 | 14970843 | 127608614 | 127608614 | Chq no 1005719516 dated 23 Jun 2023
4 | IPC-II |  | 2023-09-21 | 0 | 128327514 | 12832751 | 12832751 | 641638 | 0 | 0 | 26307140 | 102020374 | 102020374 | Chq no 1005721016 dated 13 Nov 2023
5 | IPC-III |  | 2024-06-01 | 0 | 62653341 | 6265334 | 6265334 | 313267 | 0 | 0 | 12843935 | 49809406 | 49809405 | Chq no 00028713 dated 28 Jun 2024
|  |  |  | 158704934 | 333560312 | 33356031 | 19098085 | 1667802 | 0 | 0 | 54121918 | 438143328 | 438143327
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!

## Anx K
Anx "K"
State of Claims
Project Control Unit:- Dev of C-15 Islamabad
Ser/IPC | Type of Claim | Date of Submission | Date of Approval by Consultant / Client | Revenue Expected | Retention Money Deducted | Mob Adv Deducted | Recievable | Recieved | Bal | Remarks
| Total |  |  | 0 | 0 | 0 | 0
| Note :- | Less :- Esclation on Deducted
|  | Over Payment Amount |  | 0 | ( Total Esclation)
0.041356

## Anx L
Anx "L"
Detail of Assets
Project Control Unit:- Dev of C-15 Islamabad
Sr. No. | Description | Amount
1 | Bal with PL-I Account | 223.68
2 | Contract Receivable(R.M) | 33.356
3 | Cash and bank balances | 1.002
Total (Rs. In Millions) |  | 258.038

## Anx M
Anx "M"
Detail of Liabilities
Project Control Unit:- Dev of C-15 Islamabad
Sr. No. | Description | Amount
1 | Retention money to sub contractors | 11.8281
2 | sub contractors Payable | 66.8
3 | Total (Rs. In Millions) | 78.6281
4 | Total Equity | 179.4099
5 | G.Total | 258.038

## MCRP (hidden)
List of Assets
Timergara-Mundra Chakwal Road Project
As on 30 Sep 2014
a. | Fixed Assets Transferred to Proj Con:
S.No | Cat of Assets | Transferred |  |  |  | Cost(Rs) | Depreciation for the month ( if applicable) | Acc/Dep in DCRP/TARP | Acc/Dep in TMRP | Depreciation upto date | Depreciation YTD | Transferred Assets Value
|  | From | Date | to | Date
1 | [6 empty] | 0 |  | 0 | 0 | 0 | 0
2 | [6 empty] | 0 |  | 0 | 0 | 0 | 0
3 | [6 empty] | 0 |  | 0 | 0 | 0 | 0
4 | [6 empty] | 0 |  | 0 | 0 | 0 | 0
5 | [6 empty] | 0 |  | 0 | 0 | 0 | 0
6 | [6 empty] | 0 |  | 0 | 0 | 0 | 0
7 | [6 empty] | 0 |  | 0 | 0 | 0 | 0
8 | [6 empty] | 0 |  | 0 | 0 | 0 | 0
9 | [6 empty] | 0 |  | 0 | 0 | 0 | 0
10 | [6 empty] | 0 |  | 0 | 0 | 0 | 0
11 | [6 empty] | 0 |  | 0 | 0 | 0 | 0
12 | [6 empty] | 0 |  | 0 | 0 | 0 | 0
13 | [6 empty] | 0 |  | 0 | 0 | 0 | 0
14 | [6 empty] | 0 |  | 0 | 0 | 0 | 0
15 | [6 empty] | 0 |  | 0 | 0 | 0 | 0
16 | [6 empty] | 0 |  | 0 | 0 | 0 | 0
17 | [6 empty] | 0 |  | 0 | 0 | 0 | 0
18 | [6 empty] | 0 |  | 0 | 0 | 0 | 0
19 | [6 empty] | 0 |  | 0 | 0 | 0 | 0
20 | [6 empty] | 0 |  | 0 | 0 | 0 | 0
21 | [6 empty] | 0 |  | 0 | 0 | 0 | 0
22 | [6 empty] | 0 |  | 0 | 0 | 0 | 0
23 | [6 empty] | 0 |  | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. | Fixed Assets Purchased by Proj Con:
S.No | Cat of Assets | Cheque No | Date | Transferred in any |  | Cost(Rs) | Depreciation for the month ( if applicable) | Depreciation upto date | Depreciation YTD | W D Value
|  |  |  | To | Date
13 | [6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0