## Summary
SUMMARY OF MONTHLY MONITORING REPORT
1 | Proj Con |  |  | Proj Con 10th Avenue Islamabad NLC
2 | Name of Proj |  |  | Const of 10th Avenue from IJP Road to Srinagar Highway, Islamabad
3 | Month |  |  | 2025-07-31
4 | Progress
| a. | Physical
|  | (1) | Planned |  | 4967
|  | (2) | Achieved |  | 1881.2924 | 0.37876
5 | Schedule of Proj |  |  |  |  | 30.475
| a. | Date of Commencement |  |  | 2022-03-21
| b. | Date of Completion |  |  | 2023-12-20 | 82.3225
| c. | Revised Date of Completion |  |  | 2025-12-31
6 | Financial State
| a. | Original Cost of Proj |  |  | 10286.2474
| b. | Revised Cost of Proj |  |  | 0
| c. | Funds Received from Client |  |  | 3246.5594
| d. | Cost of Work upto Previous Month |  |  | 1871.5149 | 302.7272
| e. | Cost of Work Done during the month by Proj Con / Hired Lab |  |  | 9.7775
| f. | Cost of Work Done during the month by Petty Contrs |  |  | 0
| g. | Total Cost of Work Done during the month by Proj Con / Hired Lab & Petty Contrs (e+f) |  |  | 9.7775
| h. | Total Cost of Work Done till to date (d+g) |  |  | 1881.2924 |  |  |  | 242.649
| i. | Assets |  |  | 17.7 |  |  |  | 241.938
| j. | Revenue against (MT, Lab & Handling Charges) |  |  | 0 |  |  |  | 0.711
| k. | Total Cost of Work Done incl Assets & Revenue against Recoveries till to date (h+j+k) |  |  | 1898.9924
| l. | Exp upto last month ( Incl Liab ) |  |  | 2808.0834
| m. | Exp during the month ( Incl Liab ) |  |  | 36.7221
| n. | Total Exp till to date Incl Laib (m+n) |  |  | 2844.8055
| o. | Liabilities till to date att as per Anx " M" |  |  | 47.16
| p. | Total Cost of work done without claim |  |  | 1881.2924
| q. | Total Cost of vetted work |  |  | 2051.337
| r. | Slippage (h-r ) |  |  | -170.0446 |  | 22
| s. | Escalation claims |  |  | 488.431
| t. | Claim of withheld amount / Non BOQ items |  |  | 0
7 |  | Financial Health
|  | (1) | Based on vetted work without claim |  | -793.4685
|  | (2) | Based on vetted work incl claim |  | -305.0374
|  | (3) | Based on Work Done incl claim (h+ k+ t - n ) |  | -475.0821
8 | Reasons for Delay in Progress
[7 empty] | 212.1736 | 134.91 | 77.2636
9 | Any Special Activity Carried out | [7 empty] | 318.3864
10 | Comd Remarks

## Anx A
Anx A of MMR
PROJ HIGHLIGHTS AS ON 31st July 2025
Const of 10th Avenue from IJP Road to Srinagar Highway, Islamabad
1 | Schedule of Project
| a. Date of Commencement | [6 empty] | 2022-03-21
| b. Date of Completion | [6 empty] | 2023-12-20
| c. Revised Completion Date (If any) | [6 empty] | 2025-12-31
2 | Salient Features of Proj.
| a. |  | Length of Rd |  |  |  |  | 4.1 KM
| b. | No of Bridges / Underpasses | [5 empty] | 7 x Bridge
| c. | Bldg Works |  |  | …………….N.A……………….
| d. | Infrastructure Works |  |  | …………….N.A……………….
3 | Client | [6 empty] | CDA
4 | Consultant | [6 empty] | Zeeruk Int'l (Pvt.) Ltd.
5 | Progress Work Done |  |  |  |  | Rs (Million) |  | %age
|  |  | (1) Planned (% on Work Done) - Revised |  |  | 4967 |  | 48.29%
|  |  | (2) Achieved (% on Vetted Work Done) |  |  | 1881.2924 |  | 18.29%
6 | Financial State | [6 empty] | Rs (Million)
| a.Original Cost of Proj (Pkg-01 & 02) | [6 empty] | 10286.2474 | [5 empty] | 10286247408.7
| b. Revised Cost of Project (If any) | [6 empty] | 0
| c. Total Funds Received from Client | [6 empty] | 3246.5594
| d. Total Funds Released to Project agaist cash requsition | [6 empty] | 40.1889
7 | Income State
|  |  |  | Work Done |  |  | Vetted Work
|  |  |  | During The Month | Upto Date | Year to Date | Upto Date | Year to Date | [6 empty] | 318.8143 | 86.0799
| a. |  | Revenue of the Proj | [11 empty] | 1562.4781 | 392.85 | 25.14%
|  | (1) | Workdone | [12 empty] | 478.9299
|  |  | (i) Self Exec | 9.7775 | 1881.2924 | 9.7775 | 2051.337 | [6 empty] | 1881292380 | -1881290328.663 | 1881292389.7775 | -1881290318.8855
|  |  | (ii) Sub-Contractor | [11 empty] | 170.3581
|  | (2) | Expected EPC's / Other Claims | 0 | 488.431 | 0 | 291.758 | [6 empty] | 488431048.83 | 160.896 | 1881292380
|  | (3) | Other Income | 0.028239 | 20.5493 | 0.028239 | 0.40224 | 0.028239 |  |  |  |  | 508.9803 | 20549259.46 |  | 508980308.29
| b. |  | Total Revenue | 9.8057 | 2390.2727 | 9.8057 | 2343.4973 | 0.028239 | [5 empty] | 508980308.29 | 470.3231 | 2343497260.3458
|  | (1) | Direct Cost | 34.4938 | 2652.0472 | 34.4928 | 2652.0472 | 34.4928 | 52.5741 | 87.0678 |  |  |  | 508979819.859 | 508980212.4901
|  | (2) | Gross Profit | -24.688 | -261.7745 | -24.687 | -308.5499 | -34.4645 | 18.9959 | -5.6921 |  |  |  |  | -508979742.167
|  | (3) | Gen & Adm Exp | 2.2284 | 192.7583 | 2.2287 | 192.7583 | 2.2287 | 9.5532 | 11.7816 |  |  |  | 392.6312 | 71.8391
|  | (4) | Operating Profit | -26.9164 | -454.5328 | -26.9157 | -501.3083 | -36.6932 | 9.4427 | -17.4737 |  |  |  | 508979915.6588
|  | (5) | Financial Charges | [11 empty] | 1780.2189
| c. |  | Net Profit (Million) | -26.9164 | -454.5328 | -26.9157 | -501.3083 | -36.6932 | [5 empty] | 1871.51 | 1789.9964
| d. |  | Net Profit %age | -274.5% | -19.02% | -274.5% | -21.39% | -129938% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | -1881290508.49
[10 empty] | 86.8548 |  |  |  | -583200057.6319
8 | Income State as per IAS-11 | [12 empty] | -583199665.0007 | -31161985%
|  |  |  | Work Done |  |  | Vetted Work
|  |  |  | During The Month | Upto Date | Year to Date | Upto Date | Year to Date
Revenue
Direct Cost
Gross Profit
Gen & Adm Exp
Operating Profit
Financial Charges
Other Income
Net Profit (Million)
Net Profit % age
8 |  |  | Remarks of PM/PD
|  |  |  | 134.19 | 91.053
|  |  |  | 134.19 | 85.003

## Anx B
Anx "B"
Detail of Work Self Exec Done By NLC /Hired Labour
Const of 10th Avenue from IJP Road to Srinagar Highway, Islamabad
Bill # | Activity | Amount Rs in Million
|  | CA Amount | Work Done During the Month | Workdone up to Date | Workdone Year to Date | Vetted Workdone up to Date | Vetted Workdone Year to Date
1 | Earthwork and Allied Activities | 984.4009 | 3.726 | 148.59 | 3.726 | 182.4884 |  | 148.59 |  | 0 | 139.3583
2 | Sub-Base and Base | 1616.2315 | 0.938 | 16.61 | 0.938 | 112.7116 |  | 16.61 |  | 0 | 358.6995
3 | Surface Course & Pavement | 580.5401 | 0 | 4.84 | 0 | 4.8003 |  | 4.84 |  | 0 | 83.0057
4a | Structure (Bridges) | 2997.1964 | 3.168 | 1180.6 | 3.168 | 1197.6974 |  | 1180.6 |  | 0 | 63.3399
4b | Culverts (Box) | 121.1433 | 0 |  | 0 | 0 |  |  |  | 0 | 86.1196
4c | Structure (RCC Retaining wall) | 464.4857 | 0 | 277.7096 | 0 | 265.8219 |  | 277.7096 |  | 0 | 85.4607
4b | Structure (Underpasses) | 282.8956 | 0 |  | 0 | 0 |  |  | 0 | 0 | 381.7137
4d | Structure (RRM Retaining/Breast Walls) | 189.3358 | 1.7115 | 53.05 | 1.7115 | 47.366 |  | 53.05 |  | 2e-05 | 1197.6974
| Rigid Pavement | 101.2461 | 0 |  | 0 | 0 |  |  |  | 0
4e | Mechanical Stabilized Earth | 1463.4917 | 0.234 | 58.5251 | 0.234 | 79.2679 |  | 58.5253 | 40.3707 | 0.0002
5 | Drainage and Erosion Works | 691.3978 | 0 | 66.442 | 0 | 44.3342 |  | 66.442 |  | 0
6 | Ancillary Works | 288.2997 | 0 | 2.11 | 0 | 1.2295 |  | 2.11 |  | 0
7 | General Items Package 1 & 2 | 37.905 | 0 | 32.445 | 0 | 20.5225 |  | 32.445 |  | 0
8 | Electrification | 111.4976 | 0 |  | 0 | 0 |  |  |  | 0
9 | Pedestrian Bridges | 96.18 | 0 |  | 0 | 0 |  |  |  | 0
10 | Bus Bays | 160 | 0 |  | 0 | 0 |  |  | 0 | 0
11 | Intelligent Transport System | 50 | 0 |  | 0 | 0 |  |  | 0 | 0
12 | Grass & Plantation | 50 | 0 |  | 0 | 0 | 0 |  | 0 | 0
13 | VO-01 |  | 0 |  | 0 | 47.8962 |  |  | 0 | 0
| Pkg 2 |  |  |  | 0 | 47.2012
| Grand Total Amount | 10286.2474 | 9.7775 | 1840.9216 | 9.7775 | 2051.337 | 0 | 1840.9219
|  |  | 0 | 40.3707
|  |  | 9.7775 | 1881.2924
[5 empty] | . |  | 0

## Anx C
Anx "C" of MMR
DETAIL OF WORK DONE BY SUB CONTRACTORS
Const of 10th Avenue from IJP Road to Srinagar Highway, Islamabad
Rupees in Million
Ser | CA No. | Contractor | Amount Rs in Million
|  |  | NLC's CA Amount | Sub Cont CA Amount | Work Done During the Month | Runing Total Upto Date | Runing Total YTD | Upto YTD 2016-17 | Upto YTD 2014-15 | Upto YTD 2013-14 | YTD 2012-13 | Vetted Work Done up to Date | Vetted Work Done YTD | Remarks
| Mechanicaly Stablized Earth Walls / Reinforced Earth Retaining Wall at Proj 10th Ave Road, Islamabad | [13 empty] | 40.3707
1 | 10th Avenue/14/2022/PDN/NLC | M/S Freypak Pvt Ltd | 146.7349 | 125.9893 | 0 | 40.3707 | 0 | 290.0305 | 290.0305 | 290.0305 | 290.0305 | 0 | 0 |  | -10.0063
|  |  | 146.7349 | 125.9893 | 0 | 40.3707 | 0 | 290.0305 | 290.0305 | 290.0305 | 290.0305 | 0 | 0

## Anx D
Anx "D"
DETAIL OF EXPENDITURES
Const of 10th Avenue from IJP Road to Srinagar Highway, Islamabad
Ser | Head of A/c | Expenditures (Rs in Million)
|  | During the Month | Upto Date | Year to Date
Work Expenditures
1 | Stores Consumed / purchased
| Cost | 6.603 | 1921.5209 | 6.603 | 1914.9179 | 1921.5209 | 0
2 | Sub Contractor Cost |  |  | 0 |  | 0 | 0
| a. Net Payments | 16.3219 | 301.4515 | 16.3219 | 285.1296 | 301.4515 | 1.05e-06
| b.POL | 1.0876 | 48.6963 | 1.0876 | 47.6086 | 48.6963 | 0
| c. Retention Money | 0.54292 | 11.3472 | 0.54292 | 10.8043 | 11.3472 | 0
| d. Income Tax | 0.87328 | 25.9638 | 0.87328 | 25.0905 | 25.9638 | 0
| e. T&P | 0.16108 | 5.0039 | 0.16108 | 4.8429 | 5.0039 | 0
| f. Material Lab Charges |  |  | 0 |  | 0 | 0
| g. Other Charges |  |  |  |  | 0 | 0
| h. Sec/Mob Adv (Paid)/Rec |  |  |  |  | 0 | 0
3 | Hiring of Plt / Eqpt / Mach |  |  |  |  | 0 | 0
| POL | 1.7082 | 133.4649 | 1.7082 | 131.7567 | 133.4649 | 0
| Repair/ Maint | 0.42475 | 3.3002 | 0.42475 | 2.8755 | 3.3002 | 0
| Hiring charges | 1.971 | 105.7111 | 1.97 | 103.7401 | 105.7111 | 0
[6 empty] | 0 | 0
4 | Salary and Benefits |  |  |  |  | 0 | 0
| Contractual Empolyees / Daily wages | 4.8 | 95.5873 | 4.8 | 90.7873 | 95.5873 | 0
| Total Operating Exp | 34.4938 | 2652.0472 | 34.4928 | 2652047207.6914 | 2652047242.1852 | -2652044590.138
5 | Any Other |  |  |  |  | 0 | 0
| Misc Exp |  | 2.743 |  | 2.743 | 2.743 | 0
| b.Misc Store consumed | 0.45376 | 68.4755 | 0.45376 | 68.0218 | 68.4755 | 0
| Stationary | 0.16318 | 3.2374 | 0.16318 | 3.0742 | 3.2374 | 0
| Repair/Maintenance Veh/Plt/Eqpt |  | 19.3122 |  | 19.3122 | 19.3122 | 0
| Entertainment | 0.009686 | 4.2768 | 0.01 | 4.2671 | 4.2768 | 0
| Lab Testing/Air Ambient Test |  | 0.2895 |  | 0.2895 | 0.2895 | 0
| Geo Technical |  | 0.37 |  | 0.37 | 0.37 | 0
| Trn/fr Charges |  | 2.8663 |  | 2.8663 | 2.8663 | 0
| Survey Equipment |  | 0.255 |  | 0.255 | 0.255 | 0
| Hiring of Petty Labour |  | 30.586 |  | 30.586 | 30.586 | 0
| Exp against Bill No 7 | 0.959 | 19.1617 | 0.959 | 18.2027 | 19.1617 | 0
| Electricity Expense | 0.64273 | 8.9214 | 0.64273 | 8.2787 | 8.9214 | 0
| Inauguration Ceremony |  | 4.084 |  | 4.084 | 4.084 | 0
| Office Containers |  | 2.018 |  | 2.018 | 2.018 | 0
| Air Ambinent Testing |  | 0.121 |  | 0.121 | 0.121 | 0
| Camp Development |  |  |  |  | 0 | 0
| Proj Insurance |  | 22 |  | 22 | 22 | 0
| Signboards |  | 0.768 |  | 0.768 | 0.768 | 0
| Water filing charges |  | 3.256 |  | 3.256 | 3.256 | 0
| Water connection charges |  | 0.0165 |  | 0.0165 | 0.0165 | 0
Gen Exp |  | 2.2284 | 192.7583 | 2.2287 | 192758303 | 192758305.2284 | -192758112.4701
| Total Expenditure | 36.7221 | 2844.8055 | 36.7214 | 2808.0834 | 2844.8055 | 1.05e-06
2844805510.6914
2808.0834
1707.1527
1743.8749
Note on B31: Author:

## Anx E
Anx "E"
DETAIL OF PAYMENTS TO SUB CONTRACTORS
Const of 10th Avenue from IJP Road to Srinagar Highway, Islamabad
Ser | CA No | Contractor | NLC CA Amount | Sub Contr CA Amount | During the Month | [8 empty] | Upto Date | [8 empty] | Year to Date | [8 empty] | Margin | [6 empty] | Previous YTD 15-16
[5 empty] | Sub Contr's Work Done | Retention Money | POL Recovery | T & P Recovered | Income Tax | Lab Charges | With held Amount | Secure Advance & Mob Adv | Net Payment Due | Sub Contr's Work Done | Retention Money | POL Recovery | T & P Recovered | Income Tax | Lab Charges | With held Amount | Secure Advance & Mob Adv | Net Payment Due | Sub Contr's Work Done | Retention Money | POL Recovery | T & P Recovered | Income Tax | Lab Charges | With held Amount | Secure Advance & Mob Adv | Net Payment Due | [7 empty] | POL Recovery | T & P Recovered | Income Tax 6% / 7% | Lab Charges | Other Charges | Secure Advance & Mob Adv
| Labour Rate Contracts | [12 empty] | 0 | [24 empty] | 0 | 0 | 1.7289 | 0.159 | 0 | 1.134
1 | LRA/03/2022/10th Ave/NLC | M/S Ghamrani Builders (CA-03) |  | 7.5555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.5357 | 0 | 0 | 0 | 0.65356 | 0 | 0 | 0 | 5.8821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.6712 | 0.675 | 0 | 14.3653
2 | LRA/04/2022/10th Ave/NLC | M/S Isa Khelvi Const (CA-04) |  | 14.9574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.6315 | 0 | 0 | 0 | 1.2632 | 0 | 0 | 0 | 11.3684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.6712 | 0.675 | 0 | 14.3653
3 | LRA/05/2022/10th Ave/NLC | M/S Condrill (Pvt) Ltd construction and drilling Engineers (CA-05) |  | 14.9562 | -1.131e-07 | 0.73769 | 0 | 0 | 0 | 0 | 0 | 0 | -0.73769 | 14.7538 | 0.73769 | 2.6003 | 0 | 0.97228 | 0 | 0 | 0 | 10.4435 | -1.131e-07 | 0.73769 | 0 | 0 | 0 | 0 | 0 | 0 | -0.73769 |  | 0 | -1.131e-07 | -5.6551e-09 | -1.0745e-07 | -1.0745e-08 | -9.6702e-08 | 0 | 0 | 6.6712 | 0.675 | 0 | 14.3653
4 | LRA/06/2022/10th Ave/NLC | M/S Rana Azam & Saqib Ali (CA-06) |  | 14.6525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0301 | 0.1515 | 0 | 0 | 0.28786 | 0 | 0 | 0 | 2.5907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
5 | LRA/07/2022/10th Ave/NLC | M/S Isa Khelvi Const (CA-07) |  | 14.9574 | 0 | 0 | 0 | 0 | -0.034474 | 0 | 0 | 0 | 0.034474 | 14.3739 | 0 | 11.2486 | 0 | 0.27806 | 0 | 0 | 0 | 2.8472 | 0 | 0 | 0 | 0 | -0.034474 | 0 | 0 | 0 | 0.034474 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.6712 | 0.675 | 0 | 14.3653
6 | LRA/08/2022/10th Ave/NLC | M/s Khilji (CA-08) |  | 14.9355 | -3.175e-07 | -1.5875e-08 | 0 | 0 | 0 | 0 | 0 | 0 | -0.25748 | 6.4799 | 0.32399 | 0 | 0.6445 | 0.55114 | 0 | 0 | 0 | 4.9603 | -3.175e-07 | -1.5875e-08 | 0 | 0 | 0 | 0 | 0 | 0 | -0.25748 |  | 0 | -3.175e-07 | -1.5875e-08 | -3.0163e-07 | -3.0163e-08 | -2.7146e-07
7 | LRA/09/2022/10th Ave/NLC | M/S Afzal Thakedar & All Civ Works (CA-09) |  | 14.9977 | -2e-07 | -1e-08 | 0 | 0 | 0 | 0 | 0 | 0 | -1.9e-07 | 4.3995 | 0.21998 | 0 | 0 | 0.41796 | 0 | 0 | 0 | 3.7616 | -2e-07 | -1e-08 | 0 | 0 | 0 | 0 | 0 | 0 | -1.9e-07 |  | 0 | -2e-07 | -1e-08 | -1.9e-07 | -1.9e-08 | -1.71e-07
8 | LRA/10/2022/10th Ave/NLC | M/s Freypak (CA-10) |  | 125.9893 | 12.5989 | 0 | 0 | 0 | 0.94492 | 0 | 0 | 0 | 11.654 | 75.5936 | 0 | 0 | 0 | 5.4175 | 0 | 0 | 0 | 70.176 | 12.5989 | 0 | 0 | 0 | 0.94492 | 0 | 0 | 0 | 11.654 |  | 0 | 12.5989 | 0.62995 | 11.969 | 1.1969 | 10.7721
9 | LRA/11/2022/10th Ave/NLC | M/S Condrill (Pvt) Ltd construction and drilling Engineers (CA-11) |  | 14.742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.1723 | 0 | 0.45699 | 0 | 0.45722 | 0 | 0 | 0 | 5.258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
10 | LRA/12/2022/10th Ave/NLC | M/s Grappler Developers and Contractors (CA-12) |  | 14.9942 | 1.9665e-07 | 9.8325e-09 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8682e-07 | 6.6963 | 0.33481 | 3.2324 | 0.06004 | 0.3069 | 0 | 0 | 0 | 2.7621 | 1.9665e-07 | 9.8325e-09 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8682e-07 |  | 0 | 1.9665e-07 | 9.8325e-09 | 1.8682e-07 | 1.8682e-08 | 1.6814e-07
11 | LRA/13/2022/10th Ave/NLC | M/S Noble Builders and Construction (CA-13) |  | 2.0123 | -3.2827e-07 | -1.6414e-08 | 0 | 0 | 0 | 0 | 0 | 0 | -3.1186e-07 | 1.0322 | 0.051609 | 0 | 0 | 0.098058 | 0 | 0 | 0 | 0.88252 | -3.2827e-07 | -1.6414e-08 | 0 | 0 | 0 | 0 | 0 | 0 | -3.1186e-07 |  | 0 | -3.2827e-07 | -1.6414e-08 | -3.1186e-07 | -3.1186e-08 | -2.8067e-07
12 | LRA/14/2022/10th Ave/NLC | M/S Qutab Khan Arebzai & Brothers (CA-14) |  | 14.9624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.7151 | 0.28575 | 0 | 0 | 0.54293 | 0 | 0 | 0 | 4.8864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
13 | LRA/15/2022/10th Ave/NLC | M/S Mavia Construction (CA-15) |  | 11.2491 | 2.6664 | 0.13332 | 0 | 0.060443 | 0.19286 | 0 | 0 | 0 | 2.2798 | 4.5751 | 0.22876 | 0 | 0.060443 | 0.37419 | 0 | 0 | 0 | 3.9117 | 2.6664 | 0.13332 | 0 | 0.060443 | 0.19286 | 0 | 0 | 0 | 2.2798 |  | 2.6664 | 0 | 0 | 0 | 0 | 0
14 | LRA/16/2022/10th Ave/NLC | M/S Afzal Thakedar & All Civ Works (CA-16) |  | 14.9805 | -0.69254 | -0.034627 | 0 | 0 | -0.065792 | 0 | 0 | 0 | -0.59213 | 2.5125 | 0.12562 | 0 | 0 | 0.23868 | 0 | 0 | 0 | 2.1482 | -0.69254 | -0.034627 | 0 | 0 | -0.065792 | 0 | 0 | 0 | -0.59213 |  | 0 | -0.69254 | -0.034627 | -0.65792 | -0.065792 | -0.59213
15 | LRA/17/2022/10th Ave/NLC | M/S Rana Azam & Saqib Ali (CA-17) |  | 14.9805 | 0.8399 | 0.041995 | 0 | 0 | 0.047786 | 0 | 0 | 0 | 0.75012 | 1.6844 | 0.084221 | 0 | 0 | 0.12802 | 0 | 0 | 0 | 1.4722 | 0.8399 | 0.041995 | 0 | 0 | 0.047786 | 0 | 0 | 0 | 0.75012 |  | 0 | 0.8399 | 0.041995 | 0.7979 | 0.07979 | 0.71811
16 | LRA/18/2022/10th Ave/NLC | M/S Afzal Thakedar & All Civ Works (CA-18) |  | 14.994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8627 | 0.043135 | 0 | 0 | 0.081957 | 0 | 0 | 0 | 0.73761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
17 | LRA/19/2022/10th Ave/NLC | Ms Haji Lal Khan & Sons (CA 19) |  | 14.1267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6261 | 0.081305 | 0 | 0 | 0.15448 | 0 | 0 | 0 | 1.3903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
18 | LRA/20/2022/10th Ave/NLC | Ms Mavia (CA 20) |  | 14.98 | 0.35092 | 0.017546 | 0 | 0 | -0.025253 | 0 | 0 | 0 | 0.35863 | 3.0837 | 0.15419 | 0 | 0 | 0.23436 | 0 | 0 | 0 | 2.6952 | 0.35092 | 0.017546 | 0 | 0 | -0.025253 | 0 | 0 | 0 | 0.35863 |  | 0 | 0.35092 | 0.017546 | 0.33338 | 0.033338 | 0.30004
19 |  | Ms Eagle Grip (CA 21) |  | 14.9958 | -0.1907 | -0.0095351 | -0.2279 | 0 | 0.0046731 | 0 | 0 | 0 | 0.042058 | [9 empty] | -0.1907 | -0.0095351 | -0.2279 | 0 | 0.0046731 | 0 | 0 | 0 | 0.042058 |  | 0 | -0.1907
20 | LRA/21/2022/10th Ave/NLC | M/S Noble Builders and Construction (CA-21) |  | 14.9694 | 2.9865e-07 | 1.4933e-08 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8372e-07 | 1.8456 | 0.092281 | 0 | 0 | 0.16266 | 0 | 0 | 0 | 1.5907 | 2.9865e-07 | 1.4933e-08 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8372e-07 |  | 0 | 2.9865e-07
21 | LRA/22/2022/10th Ave/NLC | Ms Mavia (CA 22) |  | 14.904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.52414 | 0.026207 | 0 | 0 | 0.049793 | 0 | 0 | 0 | 0.44814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
22 | LRA/23/2022/10th Ave/NLC | M/s Billal Traders |  | 14.935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9032 | 0.09516 | 0.716 | 0 | 0.087363 | 0 | 0 | 0 | 1.0047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #REF! | #REF!
23 | LRA/24/2022/10th Ave/NLC | M/s Billal Traders |  | 14.935 | -0.24854 | -0.012427 | 0 | 0 | -0.032501 | 0 | 0 | 0 | -0.20361 | 0.89006 | 0.044503 | 0 | 0 | 0.067645 | 0 | 0 | 0 | 0.77792 | -0.24854 | -0.012427 | 0 | 0 | -0.032501 | 0 | 0 | 0 | -0.20361 |  | #REF! | #REF!
24 | LRA/25/2022/10th Ave/NLC | M/s Billal Traders |  | 14.8313 | 0 | 0 | 0 | 0 | -0.01681 | 0 | 0 | 0 | 0.01681 | 5.4168 | 0.27084 | 1.5357 | 0 | 0.28882 | 0 | 0 | 0 | 3.3214 | 0 | 0 | 0 | 0 | -0.01681 | 0 | 0 | 0 | 0.01681 |  | #REF! | #REF!
25 | LRA/26/2022/10th Ave/NLC | M/s Faisal Jalil |  | 14.7 | 9e-06 | 0.00015045 | 0 | 0 | -1.1316e-05 | 0 | 0 | 0 | -0.00013013 | 4.363 | 0.21815 | 0 | 0 | 0.33159 | 0 | 0 | 0 | 3.8133 | 9e-06 | 0.00015045 | 0 | 0 | -1.1316e-05 | 0 | 0 | 0 | -0.00013013 |  | #REF! | #REF!
26 | LRA/27/2022/10th Ave/NLC | M/s Shah Behram |  | 14.8 | 0.00044 | 2.2e-05 | 0 | 2.2e-06 | 3.3264e-05 | 0 | 0 | 0 | 0.00038254 | 3.7765 | 0.18883 | 0 | 0.018883 | 0.28551 |  |  |  | 3.2833 | 0.00044 | 2.2e-05 | 0 | 2.2e-06 | 3.3264e-05 | 0 | 0 | 0 | 0.00038254 |  | #REF! | #REF!
27 | LRA/28/2024/10th Ave/NLC | M/s Haji Lal Khan |  | 14.3 | 0 | 0 | -2e-07 | 0 | -0.031935 | 0 | 0 | 0 | 0.031935 | 1.1866 | 0.059329 | 0.062768 | 0 | 0.085158 | 0 | 0 | 0 | 0.97932 | 0 | 0 | -2e-07 | 0 | -0.031935 | 0 | 0 | 0 | 0.031935 |  | #REF! | #REF!
28 | LRA/29/2024/10th Ave/NLC | M/s Karimdad & Co (Final Billl) |  | 14.8323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.9633 | 0 | 3.1401 | 1.4355 | 0.42284 | 0 | 0 | 0 | 2.9648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.16478 | -0.16478 | 0.81294 | 0.089436 | 0.90238 | 0.90238
29 | LRA/30/2024/10th Ave/NLC | M/s RTS |  | 14.5674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8183 | 0 | 2.927 | 1.3085 | 0.30547 |  | 0 | 0 | 2.2773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #REF! | #REF!
30 | LRA/31/2024/10th Ave/NLC | M/s AJK Ent |  | 14.552 | 0 | 0 | 0 | 0 | -0.20382 | 0 | 0 | 0 | 0.20382 | 8.49 | 0.4245 | 1.0353 | 0 | 0.56242 | 0 | 0 | 0 | 6.4678 | 0 | 0 | 0 | 0 | -0.20382 | 0 | 0 | 0 | 0.20382 |  | #REF! | #REF!
31 | LRA/32/2024/10th Ave/NLC | M/s Maken Brothers |  | 14.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6825 | 0.13413 | 0.17659 | 0 | 0.18974 | 0 | 0 | 0 | 2.182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #REF! | #REF!
32 | LRA/33/2024/10th Ave/NLC | M/S BIN SHAMS ENTERPRISES |  | 14.8188 | 0 | 0 | 0 | 0 | -1.6e-07 | 0 | 0 | 0 | 1.6e-07 | 13.3826 | 0 | 0 | 0.066913 | 1.0653 |  | 0 | 0 | 12.2504 | 0 | 0 | 0 | 0 | -1.6e-07 | 0 | 0 | 0 | 1.6e-07 |  | #REF! | #REF!
33 | LRA/34/2024/10th Ave/NLC | M/S BIN SHAMS ENTERPRISES |  | 14.9996 | 1.4e-07 | -0.26933 | 0 | 0.026933 | 0.00079233 | 0 | 0 | 0 | 0.24161 | 5.3867 |  | 0 | 0.026933 | 0.42878 | 0 | 0 | 0 | 4.931 | 1.4e-07 | -0.26933 | 0 | 0.026933 | 0.00079233 | 0 | 0 | 0 | 0.24161 |  | #REF! | #REF!
34 | LRA/35/2024/10th Ave/NLC | M/S BIN SHAMS ENTERPRISES |  | 14.962 | 2e-07 | -0.25792 | 0 | 0.025792 | -0.031976 | 0 | 0 | 0 | 0.2641 | 5.1583 |  | 0 | 0.025792 | 0.4106 | 0 | 0 | 0 | 4.7219 | 2e-07 | -0.25792 | 0 | 0.025792 | -0.031976 | 0 | 0 | 0 | 0.2641 |  | #REF! | #REF!
35 | LRA/36/2024/10th Ave/NLC | M/S APEXFORCE PAK PVT LTD |  | 9.3601 | 2.34 | 0.117 | 0 | 0.0495 | 0.17388 | 0 | 0 | 0 | 1.9996 | 9.9001 | 0.495 | 0 | 0.0495 | 0.74845 | 0 | 0 | 0 | 8.6071 | 2.34 | 0.117 | 0 | 0.0495 | 0.17388 | 0 | 0 | 0 | 1.9996 |  | #REF! | #REF!
36 | LRA/37/2024/10th Ave/NLC | M/S APEXFORCE PAK PVT LTD |  | 9.5087 | 2e-07 | 1e-08 | 0 | -0.066561 | 0.0053249 | 0 | 0 | 0 | 0.061236 | 13.3121 | 0.66561 | 0 |  | 1.0117 |  |  |  | 11.6348 | 2e-07 | 1e-08 | 0 | -0.066561 | 0.0053249 | 0 | 0 | 0 | 0.061236 |  | #REF! | #REF!
37 | LRA/38/2024/10th Ave/NLC | M/s AJK Ent |  | 14.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.799 | 0.58995 | 0.87191 | 0 | 0.82697 | 0 | 0 | 0 | 9.5102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #REF! | #REF!
38 | LRA/39/2024/10th Ave/NLC | M/S Yousaf Construction |  | 14.49 | -0.000138 | -6.9e-06 | 0 | -6.9e-07 | -1.0433e-05 | 0 | 0 | 0 | -0.00011998 | 1.3696 | 0.06848 | 0 | 0.006848 | 0.10354 |  |  |  | 1.1907 | -0.000138 | -6.9e-06 | 0 | -6.9e-07 | -1.0433e-05 | 0 | 0 | 0 | -0.00011998 |  | #REF! | #REF!
39 | LRA/40/2024/10th Ave/NLC | M/S AJK Ent |  | 14.95 | -0.0005 | -2.5e-05 | -0.000156 | 0 | 0.00046648 | 0 | 0 | 0 | -0.00078548 | 5.8765 | 0.29383 | 0.59683 | 0 | 0.39887 | 0 | 0 | 0 | 4.587 | -0.0005 | -2.5e-05 | -0.000156 | 0 | 0.00046648 | 0 | 0 | 0 | -0.00078548 |  | #REF! | #REF!
40 | LRA/41/2024/10th Ave/NLC | M/S APEXFORCE PAK PVT LTD |  | 1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.0005 | 1.25 | 0.0625 | 0 | 0 | 0.095 | 0 | 0 | 0 | 1.0925 | [8 empty] | 1.0925 |  | #REF! | #REF!
41 | LRA/42/2024/10th Ave/NLC | M/s Maken Brothers |  | 14.492 | -1.5524 | -0.077622 | 0 | 0 | -0.11798 | 0 | 0 | 0 | -1.3568 | 2.4423 | 0.12212 |  | 0 | 0.18562 | 0 | 0 | 0 | 2.1346 | -1.5524 | -0.077622 | 0 | 0 | -0.11798 | 0 | 0 | 0 | -1.3568 |  | #REF! | #REF!
42 | LRA/43/2024/10th Ave/NLC | M/s Maken Brothers |  | 14.997 | 0 | 0 | -0.000525 | 0 | -0.00019 | 0 | 0 | 0 | 0.000815 | 8.398 | 0.4199 | 2.0555 | 0 | 0.47381 | 0 | 0 | 0 | 5.4488 | 0 | 0 | -0.000525 | 0 | -0.00019 | 0 | 0 | 0 | 0.000815 |  | #REF! | #REF!
43 | LRA/44/2024/10th Ave/NLC | M/s Maken Brothers |  | 14.997 | 0 | 0 | 0.164 | 0 | -0.077315 | 0 | 0 | 0 | -0.08728 | 9.1983 | 0.45991 | 2.9578 | 0 | 0.46244 | 0 | 0 | 0 | 5.3181 | 0 | 0 | 0.164 | 0 | -0.077315 | 0 | 0 | 0 | -0.08728 |  | #REF! | #REF!
44 | LRA/45/2024/10th Ave/NLC | M/s Synergy Enterprises |  | 14.997 | 5.1056 | 0.25528 | 1.1522 | 0.047095 | 0.2919 | 0 | 0 | 0 | 3.3588 | 9.419 | 0.47095 | 1.1522 | 0.047095 | 0.6199 | 0 | 0 | 0 | 7.1288 | 5.1056 | 0.25528 | 1.1522 | 0.047095 | 0.2919 | 0 | 0 | 0 | 3.3588 |  | #REF! | #REF!
46 | LRA/46/2024/10th Ave/NLC | M/s AJK Enterprises |  | 6.2963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0.05 | 0 | 0 | 0.075999 | 0 | 0 | 0 | 0.874 | [10 empty] | #REF! | #REF!
47 | LRA/47/2024/10th Ave/NLC | M/s Ahmad Engg Services |  | 14.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.2468 | 0.56234 | 1.562 | 0.056234 | 0.7253 |  |  |  | 8.341 | [10 empty] | #REF! | #REF!
48 | LRA/48/2024/10th Ave/NLC | M/s Shabbir Construction Company |  | 14.9016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.3865 | 0.51932 | 0 | 0.051932 | 0.78522 | 0 | 0 | 0 | 9.03 | [8 empty] | 0 |  | #REF! | #REF!
49 | LRA/49/2024/10th Ave/NLC | M/s Shabbir Construction Company |  | 14.9294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.36 | 0.668 | 0 | 0.0668 | 1.01 | 0 | 0 | 0 | 11.6152 | [8 empty] | 0 |  | #REF! | #REF!
50 | LRA/50/2024/10th Ave/NLC | M/s Shabbir Construction Company |  | 7.275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.715 | 0.08575 | 0 | 0.008575 | 0.12965 | 0 | 0 | 0 | 1.491 | [8 empty] | 0 |  | #REF! | #REF!
51 | LRA/51/2025/10th Ave/NLC | M/s Jan & Sons |  | 14.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.3947 | 0.26973 | 3.2855 | 0.026973 | 0.145 |  |  |  | 1.6674 | [8 empty] | 0 |  | #REF! | #REF!
52 | LRA/52/2024/10th Ave/NLC | M/s Karimdad & Co |  | 1.95 | -0.035168 | -0.0017584 | 0 | 0.006429 | -0.0031871 | 0 | 0 | 0 | -0.036652 | 1.2857 | 0.064286 | 0.85238 | 0.3681 | 7.7484e-05 |  |  |  | 0.00089107 | -0.035168 | -0.0017584 | 0 | 0.006429 | -0.0031871 | 0 | 0 | 0 | -0.036652 |  | #REF! | #REF!
53 | LRA/54/2025/10th Ave/NLC | M/s RTS Contractors |  | 3.323 | -0.31122 | -0.015561 | 0 | 0.01145 | -0.024569 | 0 | 0 | 0 | -0.28254 | 2.2901 | 0.1145 | 1.3988 | 0.57553 | 0.016096 |  |  |  | 0.18511 | -0.31122 | -0.015561 | 0 | 0.01145 | -0.024569 | 0 | 0 | 0 | -0.28254 |  | #REF! | #REF!
54 | LRA/55/2025/10th Ave/NLC | M/s Shabbir Construction Company |  | 14.979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.375 | 0.068752 |  | 0.0068752 | 0.10395 |  |  |  | 1.1955 | [8 empty] | 0 |  | #REF! | #REF!
55 | LRA/56/2025/10th Ave/NLC | M/s Yousaf Construction Company |  | 14.955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.3743 | 0.26872 | 1.2164 | 0.026872 | 0.30898 |  |  |  | 3.5533 | [8 empty] | 0 |  | #REF! | #REF!
56 | LRA/57/2025/10th Ave/NLC | M/s Jan & Sons |  | 14.989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [8 empty] | 0 |  | #REF! | #REF!
57 | LRA/58/2025/10th Ave/NLC | M/s DHS Enterprises |  | 14.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.0214 | 0.65107 | 5.6152 | 0.065107 | 0.53521 |  |  |  | 6.1549 | [8 empty] | 0 |  | #REF! | #REF!
58 | LRA/58/2025/10th Ave/NLC | M/s DHS Enterprises |  | 14.99 | -1.6254 | -0.08127 | 0 | 0 | -0.12353 | 0 | 0 | 0 | -1.4206 | 0 | 0 |  |  | 0 |  |  |  | 0 | -1.6254 | -0.08127 | 0 | 0 | -0.12353 | 0 | 0 | 0 | -1.4206 |  | #REF! | #REF!
59 | LRA/xxx/2022/10th Ave/NLC | Asphalt Group | [10 empty] | 0 | 11.5024 | [7 empty] | 11.5024 | [10 empty] | #REF! | #REF!
TOTAL |  |  |  | 853.6857 | 19.2456 | 0.54292 | 1.0876 | 0.16108 | 0.87328 | 0 | 0 | 0 | 16.3219 | 392.4627 | 11.3472 | 48.6963 | 5.0039 | 25.9638 | 0 | 0 | 0 | 301.4515 | 19.2456 | 0.54292 | 1.0876 | 0.16108 | 0.87328 | 0 | 0 | 0 | 17.4149 |  |  | 12.9065 |  |  |  |  | 2.024 | 17.1542 | 114.5228 | 16.8908 | 43.6765 | 232.8217
[5 empty] | 0 | [8 empty] | 373.2172 | [8 empty] | 97.0435 | 3.8088 | 11.9485 | 1.0256 | 5.9118 | 0.101 | 0 | 0 | 80.6962 | 0
19.2456
373.2172
-0.16108

## Anx F Jul 25
Anx "F"
1
PAYMENT DETAIL OF SUB CONTRACTORS
Const of 10th Avenue from IJP Road to Srinagar Highway, Islamabad
Rs in Million
Ser | CA No | Contractor | Upto Date | [15 empty] | Cheque No | Date | Remarks
|  |  | RAR No | Sub Contr's Work Done | POL | Store | Retention Money | Withheld/any Deduction | Handling Charges | Income Tax 8% / 10% | Lab Charges | Other Charges | Mob / Sec Advance | Net Payment Due after D/d | Mob / Sec Adv Due | Total Payment Due | Paid Amount | Due Payment
1 | LRA/01/2022/10th Ave/NLC | M/S West ARC Construction | 1 | 5056764.0525 |  |  | 252838.2026 |  |  | 336274.8499 |  |  |  | 4467651 |  | 4467651 | 4467651 | 0 | 00645694 | 28-04-22
|  |  | 2 | 5202282 |  |  | 260114.1 |  |  | 494216.9 |  |  |  | 4447951 |  | 4447951 | 4447951 | 0 | 00660168 | 30-06-22 |  | 0%
|  |  | 3 | 3383302.5675 |  |  | 169165.1284 |  |  | 321413.7439 |  |  |  | 2892723.6952 |  | 2892723.6952 | 2000000 |  | 00674838 | 2022-09-09
|  |  | 3 | [12 empty] | 0 | 892724 |  | 00677433 | 2022-09-21
|  |  | Final | 682116.9973 | [5 empty] | 54569.3598 |  |  |  | 627547.6375 |  | 627547 | 627547 |  | 817833 | 2024-07-03
|  | Total |  | 14324465.6173 | 0 | 0 | 682117.431 | 0 | 0 | 1206474.8536 | 0 | 0 | 0 | 12435873.3327 | 0 | 12435872.6952 | 12435873 | 0
2 | LRA/02/2022/10th Ave/NLC | M/S HM Akbar & Sons | 1 | 650903 |  |  | 32545.15 |  |  | 61835.785 |  |  |  | 556522.065 |  | 556522.065 | 556522.065 | 0
|  |  | 2 | 1218987.86 |  |  | 60949.393 |  |  | 115803.87 |  |  |  | 1042234.597 |  | 1042234.597 | 1042234.597 |  | 680036 | 2022-10-07
|  |  | 3 | 398717 |  |  | 19935.85 |  |  | 30302.492 |  |  |  | 348478.658 |  | 348478.658 | 348479 | - | 00806854 | 2024-04-18
|  | Total |  | 2268607.86 | 0 | 0 | 113430.393 | 0 | 0 | 207942.147 | 0 | 0 | 0 | 1947235.32 | 0 | 1947235.32 | 1947235.662 | -0.342
3 | LRA/03/2022/10th Ave/NLC | M/S Ghamrani Builders | 1 | 5881150 |  |  | 294057.5 |  |  | 558709.25 |  |  |  | 5028383.25 |  | 5028383.25 | 5028383.25 | 0
|  |  | 2 | 654500 |  |  | 32725 |  |  | 62177.5 |  |  |  | 559597.5 |  | 559597.5 | 559597.5
|  |  | Final | 326782.5 | [5 empty] | 32678.25 |  |  |  | 294104.25 |  | 294104.25 | 294104.25
|  | Total |  | 6862432.5 | 0 | 0 | 326782.5 | 0 | 0 | 653565 | 0 | 0 | 0 | 5882085 | 0 | 5882085 | 5882085 | 0
4 | LRA/04/2022/10th Ave/NLC | M/S Isa Khelvi Cons | 1 | 12631520 |  |  | 631576 | 1263152 |  | 1073679.2 |  |  |  | 9663112.8 |  | 9663112.8 | 9663112.8 | 0 | 00662756 (Askari) | Dated 08-07-2022
|  |  |  | 1263152 | [5 empty] | 126315.2 |  |  |  | 1136836.8 |  | 1136836.8 | 1136836.8
|  |  | Final | 631576 | [5 empty] | 63157.6 |  |  |  | 568418.4 |  | 568418.4 | 568418.4
|  | Total |  | 14526248 | 0 | 0 | 631576 | 1263152 | 0 | 1263152 | 0 | 0 | 0 | 11368368 | 0 | 11368368 | 11368368 | 0
5 | LRA/05/2022/10th Ave/NLC | M/S Condrill (Pvt) Ltd construction and drilling Engineers | 1 | 7591242.3494 |  |  | 379562.1175 |  |  | 576934.4186 |  |  |  | 6634745.8134 |  | 6634745.8134 | 6634745.8134 | 0 | 00666219 (Askari) | Dated 20-07-2022
|  |  | 2 | 5663964 | 1850784.3 |  | 283198.2 |  | 55523.529 | 277956.6377 |  |  |  | 3196501.3333 |  | 3196501.3333 | 3196501.3333 | 0
|  |  | 3 | 1498577 | 673809.8 |  | 74928.85 |  | 20214.294 | 58369.9245 |  |  |  | 671254.1315 |  | 671254.1315 | 671254.1315
|  |  | Final | 737689.1675 | [5 empty] | 59015.1334 |  |  |  | 678674.0341 |  | 678674.0341 | 678674.0341
|  | Total |  | 15491472.5169 | 2524594.1 | 0 | 737689.1675 | 0 | 75737.823 | 972276.1141 | 0 | 0 | 0 | 11181175.3123 | 0 | 11181175.3123 | 11181175.3123 | 0
6 | LRA/06/2022/10th Ave/NLC | M/S Rana Azam & Saqib Ali | 1 | 1586627.8 |  |  | 79331.39 |  |  | 150729.641 |  |  |  | 1356566.769 |  | 1356566.769 | 1356566.769 | 0 |  |  | Not Avail in ERP
|  |  | 2 | 1443454.8 |  |  | 72172.74 |  | 0 | 137128.21 |  |  |  | 1234153.85 |  | 1234153.85 | 1234153.85 | 0 | 138835 | 2022-09-14
|  | Total |  | 3030082.6 | 0 | 0 | 151504.13 | 0 | 0 | 287857.851 | 0 | 0 | 0 | 2590720.619 | 0 | 2590720.619 | 2590720.619 | 0
7 | LRA/07/2022/10th Ave/NLC | M/S Isa Khelvi Cons | 1 | 13655071.6996 | 11248605.486 |  | 682753.585 |  |  | 137897.0103 |  |  |  | 1585815.6184 |  | 1585815.6184 | 1585815.6184 | 0
|  |  | 2 | 718835 |  |  | 35941.75 |  |  | 68289.34 |  |  |  | 614603.91 |  | 614603.91 | 614604.06 |  | 690341 | 2022-12-08
|  | Final |  | 718695.335 | [5 empty] | 71869.5335 |  |  |  | 646825.8015 |  | 646825.8015 | 646825.8015
|  | Total |  | 15092602.0346 | 11248605.486 | 0 | 718695.335 | 0 | 0 | 278055.8838 | 0 | 0 | 0 | 2847245.3298 | 0 | 2847245.3298 | 2847245.4798 | 0
8 | LRA/08/2022/10th Ave/NLC | M/s Khilji Builders | 1 | 4633704.89 |  |  | 231685.2445 |  | 0 | 440201.9645 |  |  |  | 3961817.6809 |  | 3961817.6809 | 3961817.6809 | 0 | 685133 | 2022-10-17
|  |  | 2 | 1846189.99 |  | 644500 | 92309.4995 |  |  | 110938.0491 |  |  |  | 998442.4415 |  | 998442.4415 | 998442 |  | 690179 | 2022-11-24
|  | Total |  | 6479894.88 | 0 | 644500 | 323994.744 | 0 | 0 | 551140.0136 | 0 | 0 | 0 | 4960260.1224 | 0 | 4960260.1224 | 4960259.6809 | 0
9 | LRA/09/2022/10th Ave/NLC | M/S Afzal Thakedar & All Civ Works | 1 | 1950232 |  |  | 97511.6 |  | 0 | 185272.04 |  |  |  | 1667448.36 |  | 1667448.36 | 1667448.02 |  | 687474 | 2022-11-08
|  |  | 2 | 2174810.6 |  |  | 108740.53 |  |  | 206607.007 |  |  |  | 1859463.063 |  | 1859463.063 | 1859463.06 |  | 690340 | 2022-12-08
|  |  | 3 | 274500 |  |  | 13725 |  |  | 26077.5 |  |  |  | 234697.5 |  | 234697.5 | 234697.5 |  | 690340 | 2023-02-20
|  | Total |  | 4399542.6 | 0 | 0 | 219977.13 | 0 | 0 | 417956.547 | 0 | 0 | 0 | 3761608.923 | 0 | 3761608.923 | 3761608.58 | 0
10 | LRA/10/2022/10th Ave/NLC | M/S Freypak Pvt Ltd | 1 | 25197852.8 |  |  |  |  | 0 | 1637860.43 |  |  |  | 23559992.37 |  | 23559992.37 | 9999999.99 | 13559992.38 | 690251 | 2022-12-05
[17 empty] | 5000000 | -5000000 | 694395 | 2022-12-16
[17 empty] | 8559992.38 | -8559992.38 | 694421 | 2022-12-19
|  |  | 2 | 12598926.4 | [5 empty] | 944919.48 |  |  |  | 11654006.92 |  | 11654006.92 | 3000000 | 8654006.92 | 817831 | 2024-07-03
[17 empty] | 2000000 | 6654006.92 | 826958 | 2024-07-11
[17 empty] | 5000000 | 1654006.92
1654006
|  |  | 3 | 12598926 | [5 empty] | 944919.45 |  |  |  | 11654006.55 |  | 11654006.55 | 3000000 | 8654006.55 | 817831 | 2024-07-03
[17 empty] | 2000000 | 6654006.55 | 826958 | 2024-07-11
[17 empty] | 2000000 | 4654006.55 | 852882 | 2025-01-13
[17 empty] | 3000000 | 0 | 852947 | 2025-01-20
[17 empty] | 1654007 | 0 | 865209 | 2025-02-13
|  |  | 4 | 12598926 | [5 empty] | 944919.45 |  |  |  | 11654006.55 |  | 11654006.55 | 3000000 |  | 867918 | 2025-05-06
[17 empty] | 2000000 |  | 876407 | 2025-05-15
[17 empty] | 2000000 |  | 876453 | 2025-05-16
[17 empty] | 2000000 |  | 876493 | 2025-05-20
[17 empty] | 2000000 |  | 884441 | 2025-06-03
[17 empty] | 654006 |  | 884606 | 2025-07-02
|  |  | 5 | 12598926 | [5 empty] | 944919.45 |  |  |  | 11654006.55 |  | 11654006.55 | 0 | 11654006.55
|  | Total |  | 75593557.2 | 0 | 0 | 0 | 0 | 0 | 5417538.26 | 0 | 0 | 0 | 70176018.94 | 0 | 70176018.94 | 58522011.37 | 11654006.55
11 | LRA/11/2022/10th Ave/NLC | M/S Condrill Pvt Ltd | 1 | 4716468 | 291696 |  | 235823.4 |  |  | 335115.888 |  |  |  | 3853832.712 |  | 3853832.712 | 3853832.712 | 0 | 687576 | 2022-11-15
|  |  | 2 | 1455783.6 | 165294 |  | 72789.18 |  |  | 97416.0336 |  |  |  | 1120284.3864 |  | 1120284.3864 | 1095930 | 24354.3864 | 694514 | 2022-12-22
[17 empty] | 24354.02 | -24354.02 | 694518 | 2022-12-22
|  | Final |  | 308612.58 | [5 empty] | 24689.0064 |  |  |  | 283923.5736 |  | 283923.5736 | 283923.5736 | 0
|  | Total |  | 6480864.18 | 456990 | 0 | 308612.58 | 0 | 0 | 457220.928 | 0 | 0 | 0 | 5258040.672 | 0 | 5258040.672 | 5258040.3056 | 1
12 | LRA/12/2022/10th Ave/NLC | M/S Grappler Developers | 1 | 5283945 | 2684724 |  | 264197.25 |  |  | 233502.67 |  |  |  | 2101521.08 |  | 2101521.08 | 2101521.08 | 0 | 690230 | 2022-12-01
|  |  | 2 | 1092436 | 547700 | 60040 | 54621.8 |  |  | 43007.42 |  |  |  | 387066.78 |  | 387066.78 | 387066.78 | 0 |  |  | Not Avail in ERP
|  |  | 3 | 319903 |  |  | 15995.15 |  |  | 30390.785 |  |  |  | 273517.065 |  | 273517.065 | 273517.065 | 0 | 718456 | 2023-04-11
|  | Total |  | 6696284 | 3232424 | 60040 | 334814.2 | 0 | 0 | 306900.875 | 0 | 0 | 0 | 2762104.925 | 0 | 2762104.925 | 2762104.925 | 0
13 | LRA/13/2022/10th Ave/NLC | M/S Noble Builders | 1 | 1032187 |  |  | 51609.35 |  |  | 98057.765 |  |  |  | 882519.885 |  | 882519.885 | 882519.885 | 0 | 690228 | 2022-12-01
|  | Total |  | 1032187 | 0 | 0 | 51609.35 | 0 | 0 | 98057.765 | 0 | 0 | 0 | 882519.885 | 0 | 882519.885 | 882519.885
14 | LRA/14/2022/10th Ave/NLC | M/S Qutab Khan | 1 | 2640075 |  |  | 132003.75 |  |  | 250807.125 |  |  |  | 2257264.125 |  | 2257264.125 | 2257264.125 |  | 704183 | 2023-01-26
|  |  | 2 | 3074977 |  |  | 153748.85 |  |  | 292122.815 |  |  |  | 2629105.335 |  | 2629105.335 | 2629105.335 |  | 738159 | 2023-07-06
|  | Total |  | 5715052 | 0 | 0 | 285752.6 | 0 | 0 | 542929.94 | 0 | 0 | 0 | 4886369.46 | 0 | 4886369.46 | 4886369.46
15 | LRA/15/2022/10th Ave/NLC | M/S Mavia Construction | 1 | 1908740.45 |  |  | 95437.0225 |  |  | 126931.24 |  |  |  | 1686372.1875 |  | 1686372.1875 | 1686372.19 |  | 709382 | 2023-02-15
|  |  | 2 | 2666390.4 |  |  | 133319.52 | 60443.1 |  | 247262.78 |  |  |  | 2225365 |  | 2225365 | 2225365 | 0 | 724122 | 2023-04-19 | Other Deduction
|  | Total |  | 4575130.85 | 0 | 0 | 228756.5425 | 60443.1 | 0 | 374194.02 | 0 | 0 | 0 | 3911737.1875 | 0 | 3911737.1875 | 3911737.19 | 0
16 | LRA/16/2022/10th Ave/NLC | M/S Afzal Thakedar | 1 | 1142452 |  |  | 57122.6 |  |  | 108532.94 |  |  |  | 976796.46 |  | 976796.46 | 976796.46 |  | 694513 | 2022-12-22
|  |  | 2 | 817917 |  |  | 40895.85 |  |  | 77702.115 |  |  |  | 699319.035 |  | 699319.035 | 699319.035 |  | 709368 | 2023-02-15
|  |  | 3 | 552092 |  |  | 27604.6 |  |  | 52448.74 |  |  |  | 472038.66 |  | 472038.66 | 472038.66 |  | 724120 | 2023-04-19
|  | Total |  | 2512461 | 0 | 0 | 125623.05 | 0 | 0 | 238683.795 | 0 | 0 | 0 | 2148154.155 | 0 | 2148154.155 | 2148154.155
17 | LRA/17/2022/10th Ave/ NLC | M/S Rana Azam | 1 | 844515 |  |  | 42225.75 |  |  | 80228.95 |  |  |  | 722060.3 |  | 722060.3 | 722060.3 |  | 694515 | 2022-12-22
|  |  | 2 | 839898 |  |  | 41994.9 |  |  | 159580.62 |  |  |  | 638322.48 |  | 638322.48 | 638322.48 |  | 724176 | 2023-04-20
|  | Total |  | 1684413 | 0 | 0 | 84220.65 | 0 | 0 | 239809.57 | 0 | 0 | 0 | 1360382.78 | 0 | 1360382.78 | 1360382.78
18 | LRA/18/2022/10th Ave/NLC | M/S Afzal Thakedar | 1 | 684500 |  |  | 34225 |  |  | 65027.5 |  |  |  | 585247.5 |  | 585247.5 | 585247.5 |  | 704255 | 2023-02-02
|  |  | 2 | 178200 |  |  | 8910 |  |  | 16929 |  |  |  | 152361 |  | 152361 | 152361 |  | 724121 | 2023-04-19
|  | Total |  | 862700 | 0 | 0 | 43135 | 0 | 0 | 81956.5 | 0 | 0 | 0 | 737608.5 | 0 | 737608.5 | 737608.5
19 | LRA/19/2022/10th Ave/NLC | M/S Haji Lal Khan & Sons | 1 | 1060200 |  |  | 53010 |  |  | 100719 |  |  |  | 906471 |  | 906471 | 906471 |  | 700422 | 2023-01-06
|  |  | 2 | 565905 |  |  | 28295.25 |  |  | 53760.975 |  |  |  | 483848.775 |  | 483848.775 | 483848.775 |  | 709331 | 2023-02-13
|  | Total |  | 1626105 |  |  | 81305.25 |  |  | 154479.975 |  |  |  | 1390319.775 |  | 1390319.775 | 1390319.775
20 | LRA/20/2022/10th Ave/NLC | M/S Mavia Construction | 1 | 2732828.84 |  |  | 136641.442 |  |  | 181730.62 |  |  |  | 2414456.778 |  | 2414456.778 | 2414456.778 |  | 704184 | 2023-01-26
|  |  | 2 | 350925.09 |  |  | 17546.2545 |  |  | 24679.89 |  |  |  | 308698.9455 |  | 308698.9455 | 308698.9455 |  | 718454
|  | Total |  | 3083753.93 |  |  | 154187.6965 |  |  | 206410.51 |  |  |  | 2723155.7235 |  | 2723155.7235 | 2723155.7235
21 | LRA/21/2022/10th Ave/NLC | M/S Noble Builders | 1 | 1178369 |  |  | 58918.45 |  |  | 111945.055 |  |  |  | 1007505.495 |  | 1007505.495 | 1007505.495 | 0 | 724131 | 2023-04-19
|  |  | 2 | 667254 |  |  | 33362.7 |  |  | 50711.304 |  |  |  | 583179.996 |  | 583179.996 | 583180 | -0.004 | 860737 | 2025-01-30
|  | Total |  | 1845623 |  |  | 92281.15 |  |  | 162656.359 |  |  |  | 1590685.491 |  | 1590685.491 | 1590685.495 | -0.004
22 | LRA/22/2022/10th Ave/NLC | M/S Mavia Construction | 1 | 524135.24 |  |  | 26206.762 |  |  | 49792.8478 |  |  |  | 448135.6302 |  | 448135.6302 | 448135.6302 |  | 724123 | 2023-04-19
|  | Total |  | 524135.24 |  |  | 26206.762 |  |  | 49792.8478 |  |  |  | 448135.6302 |  | 448135.6302 | 448135.6302
23 | LRA/23/2023/10th Ave/NLC | M/S Bilal Traders | 1 | 1308420 | 715998.835 |  | 65421 |  |  | 42160 |  |  |  | 484840.165 |  | 484840.165 | 484840.165 | 0 | 777963 | 2024-01-08
|  |  | 2 | 594780 |  |  | 29739 |  |  | 45203.28 |  |  |  | 519837.72 |  | 519837.72 | 519838 | -0.28 | 00826961 | 2024-07-11
|  | Total |  | 1903200 | 715998.835 | 0 | 95160 | 0 | 0 | 87363.28 | 0 | 0 | 0 | 1004677.885 | 0 | 1004677.885 | 1004678.165 | -0.28
24 | LRA/24/2023/10th Ave/NLC | M/S Bilal Traders | 1 | 716452.29 |  |  | 35822.6145 |  |  | 54450.374 |  |  |  | 626179.3015 |  | 626179.3015 | 626179.3015 |  | 782048 | 2024-01-22
|  |  | 2 | 173615 |  |  | 8680.75 |  |  | 13195 |  |  |  | 151739.25 |  | 151739.25 | 151739 |  | 817834 | 2024-07-03
|  | Total |  | 890067.29 | 0 | 0 | 44503.3645 | 0 | 0 | 67645.374 | 0 | 0 | 0 | 777918.5515 | 0 | 777918.5515 | 777918.3015
25 | LRA/25/2023/10th Ave/NLC | M/S Bilal Traders | 1 | 1637273 | 714923 |  | 81863.65 |  |  | 67238.87 |  |  |  | 773247.48 |  | 773247.48 | 773247.48 | 0 | 786374 | 2024-07-11
|  |  | 2 | 3779495 | 820742.3675 |  | 188974.75 |  |  | 221582.2306 |  |  |  | 2548195.6519 |  | 2548195.6519 | 1700000 | 848195.6519 | 00817654 | 2024-06-14 |  | 848195.6479
|  | Total |  | 5416768 | 1535665.3675 | 0 | 270838.4 | 0 | 0 | 288821.1006 | 0 | 0 | 0 | 3321443.1319 | 0 | 3321443.1319 | 2473247.48 | 848195.6519
26 | LRA/26/2023/10th Ave/NLC | M/S Faisal Jalil | 1 | 1507642 |  |  | 75382.1 |  |  | 114580.792 |  |  |  | 1317679.108 |  | 1317679.108 | 1317679.108 |  | 00786392 | 2024-02-01
|  |  | 2 | 1663924 |  |  | 83196.2 |  |  | 126458.224 |  |  |  | 1454269.576 |  | 1454269.576 | 1454270 |  | 00801115 | 2024-03-27
|  |  | 3 | 887457 |  |  | 44372.85 |  |  | 67446.732 |  |  |  | 775637.418 |  | 775637.418 | 775637 |  | 00816886 | 2024-06-13
|  |  | 4 | 216223 |  |  | 10811.15 |  |  | 16432.948 |  |  |  | 188978.902 |  | 188978.902 | 188979 |  | 00838717 | 2024-10-02
|  |  | 5 | 87763 |  |  | 4388.15 |  |  | 6669.988 |  |  |  | 76704.862 |  | 76704.862 | 76705 |  | 00847765 | 2024-12-17
|  | Total |  | 4363009 | 0 | 0 | 218150.45 | 0 | 0 | 331588.684 | 0 | 0 | 0 | 3813269.866 | 0 | 3813269.866 | 3813270.108 | 0
27 | LRA/27/2023/10th Ave/NLC | M/S Shah Behram | 1 | 472068 |  |  | 23603.4 |  |  | 35877.168 |  |  |  | 412587.432 |  | 412587.432 | 412587.432 |  | 781892 | 2024-01-11
|  |  | 2 | 588806 |  |  | 29440.3 |  |  | 44749.256 |  |  |  | 514616.444 |  | 514616.444 | 514616 | - | 00804386 | 2024-04-08
|  |  | 3 | 490271 |  |  | 24513.55 |  |  | 37260.596 |  |  |  | 428496.854 |  | 428496.854 | 428497 | - | 00816888 | 2024-06-13
|  |  | 4 | 358927 |  |  | 17946.35 |  |  | 27278.452 |  |  |  | 313702.198 |  | 313702.198 | 313702 | - | 00838718 | 2024-10-02
|  |  | 5 | 400368 |  |  | 20018.4 |  |  | 30427.968 |  |  |  | 349921.632 |  | 349921.632 | 349922 | - | 00847766 | 2024-12-17
|  |  | 6 | 964617 |  |  | 48230.85 | 16375.285 |  | 72000.8692 |  |  |  | 828009.9958 |  | 828009.9958 | 828010 | - | 00867728 | 2025-03-27
|  |  | 7 | 501486 |  |  | 25074.3 | 2507.43 |  | 37912.3416 |  |  |  | 435991.9284 |  | 435991.9284 | 435992 | - | 00884421 | 2025-06-02
|  | Total |  | 3776543 | 0 | 0 | 188827.15 | 18882.715 | 0 | 285506.6508 | 0 | 0 | 0 | 3283326.4842 | 0 | 3283326.4842 | 3283326.432 | 0
28 | LRA/28/2024/10th Ave/NLC | M/S Haji Lal Khan | 1 | 1186575 | 62768 |  | 59328.75 |  |  | 85158.26 |  |  |  | 979319.99 |  | 979319.99 | 979319.99 |  | 792160 | 2024-02-16
|  | Total |  | 1186575 | 62768 |  | 59328.75 |  |  | 85158.26 |  |  |  | 979319.99 |  | 979319.99 | 979319.99
29 | LRA/29/2024/10th Ave/NLC | M/S Karimdad & Co | 1 | 5080892.76 | 2819085 |  | 254044.638 |  |  | 321242.1 |  |  |  | 1686521.022 |  | 1686521.022 | 1686521.022 | 0 | 00802779 | 2024-04-08
|  |  | 2 | 3025735 | 321016 | 1435501 | 151286.75 |  |  | 83830 |  | 1435501 |  | 1034101.25 |  | 1034101.25 | 1034101 | 0.25 | 827084 | 2024-07-22
|  |  | Final | 261955 |  |  |  | 39816.335 |  | 17771.0932 |  |  |  | 204367.5718 |  | 204367.5718 | 204367 | 0.5718 | 00867876 | 2025-04-28
|  | Total |  | 8368582.76 | 3140101 | 1435501 | 405331.388 | 39816.335 | 0 | 422843.1932 | 0 | 1435501 | 0 | 2924989.8438 | 0 | 2924989.8438 | 2924989.022 | 0.5718
30 | LRA/30/2024/10th Ave/NLC | M/S RTS | 1 | 3056189 | 1667703.4 |  | 152809.45 |  |  | 197703 |  |  |  | 1037973.15 |  | 1037973.15 | 1037973 | 0.15 | 00802778 | 2024-04-08
|  |  | 2 | 3824145 | 1259286 | 1274404 | 191207.25 |  |  | 87939.82 |  |  |  | 1011307.93 |  | 1011307.93 | 1011307 | 0 | 00817662 | 2024-06-14
|  |  | Final | 281953 |  |  |  | 34091.345 |  | 19828.9324 |  |  |  | 228032.7226 |  | 228032.7226 | 102576 | 125456.7226 | 00865256 | 2025-02-18
|  | Total |  | 7162287 | 2926989.4 | 1274404 | 344016.7 | 34091.345 | 0 | 305471.7524 | 0 | 0 | 0 | 2277313.8026 | 0 | 2277313.8026 | 2151856 | 125456.7226
31 | LRA/31/2024/10th Ave/NLC | M/S AJK Enterprises | 1 | 7879000 | 690912 |  | 393950 |  |  | 347826.09 |  |  |  | 6446311.91 |  | 6446311.91 | 4000000 | 0 | 00804392 | 2024-04-08
[17 empty] | 2446312 |  | 00852831 | 2025-01-09
|  |  | 2 | 611000 | 344341 |  | 30550 |  |  | 18888.72 |  |  |  | 217220.28 |  | 217220.28 | 217215.68 | 4.6 | 00816884 | 2024-06-13
|  | Total |  | 8490000 | 1035253 |  | 424500 |  |  | 366714.81 |  |  |  | 6663532.19 |  | 6663532.19 | 6663527.68 | 4.6
32 | LRA/32/2024/10th Ave/NLC | M/S Maken Brothers | 1 | 1943000 | 117811 |  | 97150 |  |  | 138243.12 |  |  |  | 1589795.88 |  | 1589795.88 | 1589796 | 1 | 807153 | 2024-05-14
|  |  | 2 | 739500 | 58778 |  | 36975 |  |  | 51499.76 |  |  |  | 592247.24 |  | 592247.24 | 592247 |  | 00816885 | 2024-06-13
|  | Total |  | 2682500 | 176589 |  | 134125 |  |  | 189742.88 |  |  |  | 2182043.12 |  | 2182043.12 | 2182043 | 0
33 | LRA/33/2024/10th Ave/NLC | M/S Bin Shams | 1 | 3303300 |  |  | 165165 |  |  | 251050.8 |  | 0.08 |  | 2887084.2 |  | 2887084.2 | 2887084 | 0.2 | 00804389 | 2024-04-08
|  |  | 2 | 6373675 |  |  | 318683.75 |  |  | 484399.3 |  | 0.08 |  | 5570591.95 |  | 5570591.95 | 4000000 | 1570591.95 | 00817665 | 2024-06-14
|  |  | 2 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 1570592 | -1570592 | 00817829 | 2024-07-03
|  |  | 3 | 3705625 |  |  | 185281.25 |  |  | 281627.5 |  |  |  | 3238716.25 |  | 3238716.25 | 3238716 | 0.25 | 00829540 | 2024-08-30
|  |  | Final | 669130 |  |  | 0 | 66913 |  | 48177.36 |  |  |  | 554039.64 |  | 554039.64 | 554040 | -0.36 | 00865334 | 2025-02-26
|  | Total |  | 14051730 | 0 | 0 | 669130 | 66913 | 0 | 1065255.12 | 12250432.2 | 12250432.2 | 24500864.08 | 12250432.04 | 24500864.08 | 12250432.04 | 12250432 | 0
34 | LRA/34/2024/10th Ave/NLC | M/S Bin Shams | 1 | 652622 |  |  | 32631.1 |  |  | 49599.272 |  |  |  | 570391.628 |  | 570391.628 | 570392 | -0.372 | 00806853 | 2024-04-18
|  |  | 2 | 2567358 |  |  | 128367.9 |  |  | 195119.208 |  |  |  | 2243870.892 |  | 2243870.892 | 2243871 | -0.108 | 00816887 | 2024-06-13
|  |  | 3 | 2206501.25 |  |  | 110325.0625 |  |  | 167694.095 |  |  |  | 1928482.0925 |  | 1928482.0925 | 1928482 | 0.0925 | 00838787 | 2024-10-09
|  |  | Final | 231522 |  |  |  | 26933.395 |  | 16367.0884 |  |  |  | 188221.5166 |  | 188221.5166 | 188222 | -0.4834 | 00865402 | 2025-03-11 | Joint Cheque with LRA 35
|  | Total |  | 5658003.25 | 0 | 0 | 271324.0625 | 26933.395 | 0 | 428779.6634 | 0 | 0 | 0 | 4930966.1291 | 0 | 4930966.1291 | 4930967 | -0.8709
35 | LRA/35/2024/10th Ave/NLC | M/S Bin Shams | 1 | 1773539 |  |  | 88676.95 |  |  | 134788.964 |  |  |  | 1550073.086 |  | 1550073.086 | 1550073 | 0.086 | 00804388 | 2024-04-08
|  |  | 2 | 2831624 |  |  | 141581.2 |  |  | 215203.424 |  |  |  | 2474839.376 |  | 2474839.376 | 2474840 |  | 00826960 | 2024-07-11
|  |  | 3 | 557390 |  |  | 27869.5 |  |  | 42361.64 |  |  |  | 487158.86 |  | 487158.86 | 487159 | -0.14 | 00838719 | 2024-10-02 | In Finance
|  |  | Final | 253890 |  |  |  | 25791.58 |  | 18247.8736 |  |  |  | 209850.5464 |  | 209850.5464 | 209851 | -0.4536 | 00865402 | 2025-03-11 | Joint Cheque with LRA 34
|  | Total |  | 5416443 | 0 | 0 | 258127.65 | 25791.58 | 0 | 410601.9016 | 0 | 0 | 0 | 4721921.8684 | 0 | 4721921.8684 | 4721923 | -0.4536
36 | LRA/36/2024/10th Ave/NLC | M/S Apexforce | 1 | 5400048 |  |  | 270002.4 |  |  | 384754 |  |  |  | 4745291.6 |  | 4745291.6 | 3000000 | 1745291.6 | 00804384 | 2024-04-08
[17 empty] | 1745292 | -1745292 | 00806861 | 2024-04-18
|  |  | 2 | 2160019 |  |  | 108000.95 |  |  | 153901 |  |  |  | 1898117.05 |  | 1898117.05 | 1000000 | 0 | 00838788 | 2024-10-09
[17 empty] | 898117 |  | 00841175 | 2024-11-08
|  |  | 3 | 1800016 |  |  | 90000.8 |  |  | 153901 |  |  |  | 1556114.2 |  | 1556114.2 | 1000000 | 556114.2 | 00884419 | 2025-06-02
|  | Total |  | 9360083 | 0 | 0 | 468004.15 | 0 | 0 | 692556 | 0 | 0 | 0 | 8199522.85 | 0 | 8199522.85 | 7643409 | 556113.8
37 | LRA/37/2024/10th Ave/NLC | M/S Apexforce | 1 | 5134682 |  |  | 256734.1 |  |  | 365846.0925 |  |  |  | 4512101.8075 |  | 4512101.8075 | 2800000 | 1712101.8075 | 00816889 | 2024-06-13
[17 empty] | 1712102 | -1712102 | 00817830 | 2024-07-03
|  |  | 2 | 4373988 |  |  | 218699.4 |  |  | 311646.645 |  |  |  | 3843641.955 |  | 3843641.955 | 2000000 | 0 | 00841063 | 2024-10-29
[17 empty] | 1000000 |  | 00852677 | 2024-12-20
[17 empty] | 843643 |  | 00852831 | 2025-01-09
|  |  | 3 | 3803468 |  |  | 190173.4 |  |  | 270997.095 |  |  |  | 3342297.505 |  | 3342297.505 | 1500000 |  | 00852896 | 2025-01-13
[17 empty] | 1832339 | 9959 | 00860742 | 2025-01-30
|  | Total |  | 13312138 | 0 | 0 | 665606.9 | 0 | 0 | 948489.8325 | 0 | 0 | 0 | 11698041.2675 | 0 | 11698041.2675 | 11688084 | 9958.8075
38 | LRA/38/2024/10th Ave/NLC | M/S AJK Enterprises | 1 | 11799000 | 871915.6 |  | 589950 |  |  | 826970.752 |  |  |  | 9510163.648 |  | 9510163.648 | 2700000 | 6810163.648 | 00817666 | 2024-06-14
[17 empty] | 2205607 |  | 00817828 | 2024-07-03
[17 empty] | 2000000 | 4810163.648 | 00826957 | 2024-07-11
[17 empty] | 1000000 | 3810163.648 | 00838792 | 2024-10-09
[17 empty] | 1000000 | 2810163.648 | 00841174 | 2024-11-08
|  | Total |  | 11799000 | 871915.6 |  | 589950 |  |  | 826970.752 |  |  |  | 9510163.648 |  | 9510163.648 | 8905607 | 604556.648
39 | LRA/39/2024/10th Ave/NLC | M/S Yousaf Construction | 1 | 377017 |  |  | 18850.85 |  |  | 28653.292 |  |  |  | 329512.858 |  | 329512.858 | 329513 | 0 | 00816890 | 2024-06-13
|  |  | 2 | 469099 |  |  | 23454.95 |  |  | 35651.524 |  |  |  | 409992.526 |  | 409992.526 | 409992 |  | 00829538 | 2024-08-30
|  |  | 3 | 325862 |  |  | 16293.1 |  |  | 24765.512 |  |  |  | 284803.388 |  | 284803.388 | 284804 |  | 00847767 | 2024-12-17
|  |  | 4 | 197630 |  |  | 9881.5 | 6848.04 |  | 14472.0368 |  |  |  | 166428.4232 |  | 166428.4232 | 166429 |  | 00867727 | 2025-03-27
|  | Total |  | 1369608 | 0 | 0 | 68480.4 | 6848.04 | 0 | 103542.3648 | 0 | 0 | 0 | 1190737.1952 | 0 | 1190737.1952 | 1190738 | 0 | 0
40 | LRA/40/2024/10th Ave/NLC | M/S AJK Enterprises | 1 | 4496500 | 440844 |  | 224825 |  |  | 306466.48 |  |  |  | 3524364.52 |  | 3524364.52 | 1600000 | 1924364.52 | 00827090 | 2024-07-22
1255163
524364
|  |  | 2 | 1380000 | 155984 |  | 69000 |  |  | 92401.28 |  |  |  | 1062614.72 |  | 1062614.72 | 1062615 | 0 | 00852895 | 2025-01-13
|  | Total |  | 5876500 | 596828 | 0 | 293825 | 0 | 0 | 398867.76 | 0 | 0 | 0 | 4586979.24 | 0 | 4586979.24 | 2662615 | 1924364.52
41 | LRA/41/2024/10th Ave/NLC | M/S Apexforce | 1 | 1250277 |  |  | 62513.85 |  |  | 89082.2362 |  |  |  | 1098680.9138 |  | 1098680.9138 | 1098681 |  | 00829539 | 2024-08-30
|  | Total |  | 1250277 |  |  | 62513.85 |  |  | 89082.2362 |  |  |  | 1098680.9138 |  | 1098680.9138 | 1098681 | 0
42 | LRA/42/2024/10th Ave/NLC | M/s Maken Brothers | 1 | 872233 |  |  | 43611.65 |  |  | 66289.708 |  |  |  | 762331.642 |  | 762331.642 | 762331.64 | 0.002 | 00838784 | 2024-10-09
|  |  | 2 | 1570115 |  |  | 78505.75 |  |  | 119328.74 |  |  |  | 1372280.51 |  | 1372280.51 | 1372281 | 0 | 00860596 | 2025-01-23 | Joint Check with LRA 44
|  | Total |  | 2442348 | 0 | 0 | 122117.4 | 0 | 0 | 185618.448 | 0 | 0 | 0 | 2134612.152 | 0 | 2134612.152 | 2134612.64 | 0.002 | 0 | 0
43 | LRA/43/2024/10th Ave/NLC | M/s Maken Brothers | 1 | 8398812 | 2055475 |  | 419940.6 |  |  | 473871.712 |  |  |  | 5449524.688 |  | 5449524.688 | 5449524 |  | 00829541 | 2024-08-30
|  | Total |  | 8398812 | 2055475 |  | 419940.6 |  |  | 473871.712 |  |  |  | 5449524.688 |  | 5449524.688 | 5449524 | 0
44 | LRA/44/2024/10th Ave/NLC | M/s Maken Brothers | 1 | 5385693.9455 | 2157004 |  | 269284.6973 |  |  | 236752.4199 |  |  |  | 2722652.8283 |  | 2722652.8283 | 2722653 |  | 00841027 | 2024-10-25
|  |  | 2 | 3812577 | 800838 |  | 190628.85 |  |  | 225688.812 |  |  |  | 2595421.338 |  | 2595421.338 | 2595421 |  | 00860596 | 2025-01-23 | Joint Check with LRA 42
|  | Total |  | 9198270.9455 | 2957842 | 0 | 459913.5473 | 0 | 0 | 462441.2319 | 0 | 0 | 0 | 5318074.1663 | 0 | 5318074.1663 | 5318074 | 0
45 | LRA/45/2024/10th Ave/NLC | M/s Synergy Enterprises | 1 | 4313409 |  |  | 215670.45 |  |  | 327819.084 |  |  |  | 3769919.466 |  | 3769919.466 | 3769920 | - | 00829537 | 2024-08-30
|  |  | 2 | 5105603 | 1152218 |  | 255280.15 | 47095.06 |  | 292080.7832 |  |  |  | 3358929.0068 |  | 3358929.0068 | 2000000 |  | 00865406 | 2025-03-11
[17 empty] | 1000000 | 0 | 00867730 | 2025-03-27
[17 empty] | 358928 |  | 00876354 | 2025-05-13
|  | Total |  | 9419012 | 1152218 | 0 | 470950.6 | 47095.06 | 0 | 619899.8672 | 0 | 0 | 0 | 7128848.4728 | 0 | 7128848.4728 | 7128848 | 0
46 | LRA/46/2024/10th Ave/NLC | M/s AJK Enterprises | 1 | 999999 |  |  | 49999.95 |  |  | 75999.924 |  |  |  | 873999.126 |  | 873999.126 | 873999 | - | 00841038 | 2024-10-25
|  | Total |  | 999999 |  |  | 49999.95 |  |  | 75999.924 |  |  |  | 873999.126 |  | 873999.126 | 873999 | 0.126
47 | LRA/47/2024/10th Ave/NLC | M/s Ahmad Engg Services | 1 | 7279350 | 613989 |  | 363967.5 | 36396.75 |  | 501199.74 |  |  |  | 5763797.01 |  | 5763797.01 | 3000000 | 0 | 00865255 | 2025-02-18
[17 empty] | 2000000 | 0 | 00865332 | 2025-02-26
[17 empty] | 763769 | 28.01 | 00865408 | 2025-03-11
|  |  | 2 | 3967481 | 947993 |  | 198374.05 | 19837.405 |  | 224102.1236 |  |  |  | 2577174.4214 |  | 2577174.4214 | 500000 | 2077174.4214 | 00867726 | 2025-03-27
[17 empty] | 1000000 | 1077174.4214 | 00876353 | 2025-05-13
[17 empty] | 1077175 | 0 | 00876451 | 2025-05-16
|  | Total |  | 11246831 | 1561982 | 0 | 562341.55 | 56234.155 | 0 | 725301.8636 | 0 | 0 | 0 | 8340971.4314 | 0 | 8340971.4314 | 8340944 | 28.01
48 | LRA/48/2024/10th Ave/NLC | M/s Shabbir Construction Company | 1 | 5785746 |  |  | 289287.3 |  |  | 439716.696 |  |  |  | 5056742.004 |  | 5056742.004 | 1700000 | 0 | 00847764 | 2024-12-17
[17 empty] | 3356742 | 0 | 00852761 | 2025-01-06
|  |  | 2 | 1028482 |  |  | 51424.1 | 34071.14 |  | 75438.9408 |  |  |  | 867547.8192 |  | 867547.8192 | 867547.8192 | 0 | 00865403 | 2025-03-11 | Joint Cheque with LRA 50
|  |  | 3 | 1570530 |  |  | 78526.5 | 7852.65 |  | 118732.068 |  |  |  | 1365418.782 |  | 1365418.782 | 1365419 |  | 00867917 | 2025-05-05
|  |  | 4 | 2001704 |  |  | 100085.2 | 10008.52 |  | 151328.8224 |  |  |  | 1740281.4576 |  | 1740281.4576 | 1000000 | 0 | 00884604 | 2025-07-02
[17 empty] | 739362 | 919.4576 | 00889339 | 2025-07-24
|  | Total |  | 10386462 | 0 | 0 | 519323.1 | 51932.31 | 0 | 785216.5272 | 0 | 0 | 0 | 9029990.0628 | 0 | 9029990.0628 | 9029070.8192 | 919.4576
49 | LRA/49/2024/10th Ave/NLC | M/s Shabbir Construction Company | 1 | 3167988 |  |  | 158399.4 |  |  | 240767.088 |  |  |  | 2768821.512 |  | 2768821 | 2768821 | 0 | 00841040 | 2024-10-25
|  |  | 2 | 1579356 |  |  | 78967.8 | 23736.72 |  | 118132.1184 |  |  |  | 1358520 |  | 1358520 | 1358520 | 0 | 00865335 | 2025-02-26
|  |  | 3 | 2892722 |  |  | 144636.1 | 14463.61 |  | 218689.7832 |  |  |  | 2514932.5068 |  | 2514932 | 2500000 | 14932 | 00867729 | 2025-03-27
|  |  | 4 | 5720305 |  |  | 286015.25 | 28601.525 |  | 432455.058 |  |  |  | 4973233.167 |  | 4973233 | 4973233 |  | 00884422 | 2025-06-02 | Joint Cheque with LRA 55
|  | Total |  | 13360371 | 0 | 0 | 668018.55 | 66801.855 | 0 | 1010044.0476 | 0 | 0 | 0 | 11615507.1858 | 0 | 11615506 | 11600574 | 14932
50 | LRA/50/2024/10th Ave/NLC | M/s Shabbir Construction Company | 1 | 1225000 |  |  | 61250 | 6125 |  | 92610 |  |  |  | 1065015 |  | 1065015 | 1065015 | 0 | 00865403 | 2025-03-11 | Joint Cheque with LRA 48
|  |  | 2 | 490000 |  |  | 24500 | 2450 |  | 37044 |  |  |  | 426006 |  | 426006 | 426006 | 0 | 00876370 | 2025-05-13 | Joint Cheque with LRA 55
|  | Total |  | 1715000 | 0 | 0 | 85750 | 8575 | 0 | 129654 | 0 | 0 | 0 | 1491021 | 0 | 1491021 | 1491021 | 0
51 | LRA/51/2025/10th Ave/NLC | M/s Jan & Sons | 1 | 1694461 | 806336 |  | 84723.05 | 8472.305 |  | 63594.3716 |  |  |  | 731335.2734 |  | 731335 | 731335 | 0 | 00865336 | 2025-02-26
|  |  | 2 | 1095503 | 815770 |  | 54775.15 | 5477.515 |  | 17558.4268 |  |  |  | 201921.9082 |  | 201922 | 201922 | 0 | 00876371 | 2025-05-13
|  |  | 3 | 2604703 | 1663409 |  | 130235.15 | 13023.515 |  | 63842.8268 |  |  |  | 734192.5082 |  | 734193 |  | 734193
|  | Total |  | 5394667 | 3285515 | 0 | 269733.35 | 26973.335 | 0 | 144995.6252 | 0 | 0 | 0 | 1667449.6898 | 0 | 1667450 | 933257 | 734193
52 | LRA/52/2024/10th Ave/NLC | M/S Karimdad & Co | 1 | 1285729 | 852376 | 361669 | 64286.45 | 6428.645 |  | 77.5124 |  |  |  | 891.3926 |  | 891 | 891 | 0 | 00865405 | 2025-03-11
|  | Total |  | 1285729 | 852376 | 361669 | 64286.45 | 6428.645 | 0 | 77.5124 | 0 | 0 | 0 | 891.3926 | 0 | 891 | 891 | 0
53 | LRA/53/2025/10th Ave/NLC | M/S Maken Brothers | 1 | 0 | 0 | 0 | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0
|  | Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | LRA/54/2025/10th Ave/NLC | M/S RTS Contractors | 1 | 2290059 | 1398819 | 564085 | 114502.95 | 11450.295 |  | 16096.1404 |  |  |  | 185105.6146 |  | 185106 | 185106 | 0 | 00865404 | 2025-03-11
|  | Total |  | 2290059 | 1398819 | 564085 | 114502.95 | 11450.295 | 0 | 16096.1404 | 0 | 0 | 0 | 185105.6146 | 0 | 185106 | 185106 | 0
55 | LRA/55/2025/10th Ave/NLC | M/s Shabbir Construction Company | 1 | 1059599 | 0 | 0 | 52979.95 | 5297.995 |  | 80105.6844 |  |  |  | 921215.3706 |  | 921215 | 921215 | 0 | 00876370 | 2025-05-13 | Joint Cheque with LRA 50
|  |  |  | 315444 | 0 | 0 | 15772.2 | 1577.22 |  | 23847.5664 |  |  |  | 274247.0136 |  | 274247 | 274247 | 0 | 00884422 | 2025-06-02 | Joint Cheque with LRA 49
|  | Total |  | 1375043 | 0 | 0 | 68752.15 | 6875.215 | 0 | 103953.2508 | 0 | 0 | 0 | 1195462.3842 | 0 | 1195462 | 1195462 | 0
55 | LRA/56/2025/10th Ave/NLC | M/s Yousaf Construction Company | 1 | 3324428 | 1066421 | 0 | 166221.4 | 16622.14 |  | 166013.0768 |  |  |  | 1909150.3832 |  | 1909150 | 1000000 |  | 00876369 | 2025-05-13
[17 empty] | 909150 |  | 00876452 | 2025-05-16
|  |  | 2 | 2049899 | 150006 | 0 | 102494.95 | 10249.495 |  | 142971.8844 |  |  |  | 1644176.6706 |  | 1644177 | 1000000 | 0 | 00884420 | 2025-06-02
[17 empty] | 644177 |  | 00889338 | 2025-07-24
|  | Total |  | 5374327 | 1216427 | 0 | 268716.35 | 26871.635 | 0 | 308984.9612 | 0 | 0 | 0 | 3553327.0538 | 0 | 3553327 | 3553327 | 0
56 | LRA/58/2025/10th Ave/NLC | M/s DHS Enterprises | 1 | 13021421 | 5615157 | 0 | 651071.05 | 65107.105 |  | 535206.8676 |  |  |  | 6154878.9774 |  | 6154879 | 2000000 | 4154879 | 00884603 | 2025-07-02
|  | Total |  | 13021421 | 5615157 | 0 | 651071.05 | 65107.105 | 0 | 535206.8676 | 0 | 0 | 0 | 6154878.9774 | 0 | 6154879 | 2000000 | 4154879
|  | Total |  | 402949281.2542 | 48620532.7885 | 4340199 | 16049432.4737 | 1917216.12 | 75737.823 | 27141415.3495 | 12250432.2 | 13685933.2 | 24500864.08 | 304804748.4979 | 24500864.08 | 304804746.5622 | 284177139.166 | 20627608.5169
|  |  |  | 16593073 | [5 empty] | 304804747.6995
386356208.2542
51272

## Anx G
Anx "G"
DETAIL OF CONST MATERIAL
Const of 10th Avenue from IJP Road to Srinagar Highway, Islamabad
Rs in Million
Ser | Item | Unit | Purchases (Rs) | [6 empty] | Consumed (Rs) | [5 empty] | Balance Held |  |  |  | Remarks
|  |  | Total Qty Req | During the Month |  | Upto Date |  | Year to Date |  | During the Month |  | Upto Date |  | Year to Date |  | Upto Date |  | Year to Date
|  |  |  | Qty | Cost | Qty | Cost | Qty | Cost | Qty | Cost | Qty | Cost | Qty | Cost | Qty | Cost | Qty | Cost
1 | ASTM 615, GR-60 - 10mm | Tons |  |  |  | 119.628 | 30.2521 |  |  | 0.67146 | 0.1698 | 93.126 | 21.0213 | 0.67146 | 0.1698 | 26.502 | 6.7019
2 | ASTM 615, GR-60 - 12mm | Tons | 0 |  |  | 1190.385 | 295.7344 |  |  | 0.13356 | 0.033181 | 1029.0842 | 249.4506 | 0.13356 | 0.033181 | 161.3008 | 40.0729
3 | ASTM 615, GR-60 - 16mm | Tons |  |  |  | 1351.066 | 332.9197 |  |  |  |  | 1262.2247 | 311.0281 |  |  | 88.8413 | 21.8916
4 | ASTM 615, GR-60 - 20mm | Tons |  |  |  | 234.146 | 51.2901 |  |  |  |  | 183.9212 | 38.0978 |  |  | 50.2248 | 11.0018
5 | ASTM 615, GR-60 - 25mm | Tons |  |  |  | 1205.341 | 280.9654 |  |  |  |  | 1153.8047 | 268.9523 |  |  | 51.5363 | 12.0131
6 | ASTM 615, GR-60 - 32mm | Tons |  |  |  | 1386.255 | 335.204 |  |  |  |  | 1378.755 | 333.3904 |  |  | 7.5 | 1.8135
7 | Prestressing Wire | Tons |  |  | 0 | 264.815 | 98.8211 |  |  |  |  | 253.14 | 94.4643 |  |  | 11.675 | 4.3568
8 | A3 (SRC) Concr for Piles - 10th Ave | CUM |  |  |  | 7440.3 | 90.0418 | 0 | 0 | 0 | 0 | 7440.3 | 90.0418 | 0 | 0 |  | 0
9 | A3 (OPC) Concr - 10th Ave | CUM |  | 100.74 | 1.5945 | 14643.054 | 193.5735 | 100.74 | 1.5945 | 100.74 | 1.5945 | 14643.054 | 193.5735 | 100.74 | 1.5945 |  | 0
10 | A1 (OPC) Concr - 10th Ave | CUM |  | 194.3202 | 1.8925 | 4545.4134 | 49.2279 | 194.3202 | 1.8925 | 194.3202 | 1.8925 | 4545.4134 | 49.2279 | 194.3202 | 1.8925
11 | A2 (OPC) Concr - 10th Ave | CUM |  | 16.04 | 0.23106 | 95.207 | 1.3451 | 16.04 | 0.23106 | 16.04 | 0.23106 | 95.207 | 1.3451 | 16.04 | 0.23106 | 0
12 | D1 Conc - 10th Ave | CUM |  | 0 | 0 | 1644.083 | 27.4484 | 0 | 0 | 0 | 0 | 1644.083 | 27.4484 | 0 | 0 | 0 | 0
13 | D2 Conc - 10th Ave | CUM |  |  |  | 6009.524 | 101.5998 | 0 | 0 | 0 | 0 | 6009.524 | 101.5998 | 0 | 0 | 0 | 0
14 | Lean Concrete | CUM |  | 121 | 0.78387 | 1758.137 | 16.3274 | 121 | 0.78387 | 121 | 0.78387 | 1758.137 | 16.3165 | 121 | 0.78387 | 0
15 | Conc Class B | CUM |  | 37.12 | 0.45743 | 3189.525 | 35.7757 | 37.12 | 0.45743 | 37.12 | 0.45743 | 3189.525 | 35.7757 | 37.12 | 0.45743 | 0
16 | Fill Material for MSE Wall | CFt |  |  | 0 | 408549 | 27.3728 | 0 | 0 | 0 | 0 | 408549 | 27.3728 | 0 | 0 | 0
17 | Sub-Base material | CFt |  | 16372 | 1.4407 | 120088 | 10.5677 | 16372 | 1.4407 | 16372 | 1.4407 | 120088 | 10.5677 | 16372 | 1.4407 | 0
18 | FOE Material (Subhan) | CM |  |  | 0 | 25943.937 | 8.2502 | 0 | 0 | 0 | 0 | 25943.937 | 8.2502 | 0 | 0 | 0
19 | PT Bridge Supplies | [6 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
a | Trumpets 250x250x 35 | Nos |  |  |  | 387 | 2.0878 | 0 | 0 |  |  | 387 | 2.0878 | 0 | 0 | 0 | 0
b | Trumpets 270x270x 35 | Nos |  |  |  | 180 | 1.166 | 0 | 0 |  |  | 180 | 1.166 |  |  | 0 | 0
c | Stressing Block 12 Holes | Nos |  |  |  | 387 | 1.3104 | 0 | 0 |  |  | 387 | 1.3104 |  |  | 0 | 0
d | Stressing Block 15 Holes | Nos |  |  |  | 180 | 0.88349 | 0 | 0 |  |  | 180 | 0.88349 |  |  | 0 | 0
e | Wedges 0.5" Dia | Nos |  |  |  | 6980 | 1.9295 | 0 | 0 |  |  | 6980 | 1.9295 |  |  | 0 | 0
f | Sheath 75mm | Lm |  |  |  | 3233 | 0.95548 | 0 | 0 |  |  | 3233 | 0.95548 |  |  | 0 | 0
g | Sheath 78mm | Lm |  |  |  | 163 | 0.048589 | 0 | 0 |  |  | 163 | 0.048589 |  |  | 0 | 0
h | Sheath 65mm | Lm |  |  |  | 5867 | 1.4798 | 0 | 0 |  |  | 5867 | 1.4798 |  |  | 0 | 0
i | Sheath 68mm | Lm |  |  |  | 140 | 0.034598 | 0 | 0 |  |  | 140 | 0.034598 |  |  | 0 | 0
j | Plastic Saddle | Nos |  |  |  | 283 | 0.019827 | 0 | 0 |  |  | 283 | 0.019827 |  |  | 0 | 0
20 | 425x450x77.5 Bearing pad | Ccm |  |  |  | 800381.25 | 4.0019 |  |  |  |  | 800381.25 | 4.0019 |  |  | 0 | 0
21 | 400x450x77.5 Bearing pad | Ccm |  |  | 0 | 2232000 | 11.8226 |  |  |  |  | 2232000 | 11.8226 |  |  | 0
22 | 475x450x77.5 Bearing pad | Ccm |  |  | 0 | 2319187.5 | 13.9151 |  |  |  |  | 2319187.5 | 13.9151 |  |  | 0 | 0
23 | Expansion Joint | Lm |  |  |  | 138.3 | 3.9416 |  |  |  |  | 138.3 | 3.9416 |  |  | 0
| Store Items | [10 empty] | 0 | 0
23 | A36 Steel Shuttering | KG |  |  |  | 7367.28 | 2.43 |  |  |  |  | 0 | 0 |  |  | 7367.28 | 2.43
24 | Drill Machine | Nos | [13 empty] | 0 | 0
25 | Electric Fan Heater | Nos | [13 empty] | 0 | 0
26 | Electric Motor 3/P. 3HP | Nos | [13 empty] | 0 | 0
27 | Grinder 7" | Nos | [11 empty] | 0 | 0 | 0 | 0
28 | Grinder 9" | Nos | [11 empty] | 0 | 0 | 0 | 0
29 | Hilti China | Nos | [11 empty] | 0 | 0 | 0 | 0
30 | Hilti 1050 W China | Nos | [11 empty] | 0 | 0 | 0 | 0
31 | Pump 1 HP | Nos | [11 empty] | 0 | 0 | 0 | 0
32 | Oxygen Gas Cylender Large | Nos | [11 empty] | 0 | 0 | 0 | 0
| Genrator 15 Kva | Nos |  |  |  | 1 | 1.1181 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 1.1181
| Genrator 5 Kva |  |  |  |  | 1 | 0.7047 |  |  |  |  | 0 | 0 |  |  | 1 | 0.7047
Genrator 3 Kva
33 | Vibrator with Petrol Engine Robin EY20 | Nos |  |  |  | 2 | 0.188 |  |  |  |  | 0 | 0 | 0 | 0 | 2 | 0.188
34 | Spray Machine Steel | Nos | [11 empty] | 0 | 0 | 0 | 0
35 | Spray Tank 20 Ltr | Nos | [11 empty] | 0 | 0 | 0 | 0
36 | Steel Almirah | Nos | [13 empty] | 0 | 0
34 | Granular Material | CFT |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0
| Total Cost (Rs in Million) |  |  |  | 6.4001 |  | 2034.7547 |  | 6.4001 |  | 6.603 |  | 1921.5209 |  | 6.603 |  | 102.2925
[7 empty] | 1552.1089 |  | 126.3595 |  |  |  | 1800.0673 | 0 | 414.8142
121.4536
60.01
Note on G13: Author: 27.75 Ton Dated 13-4-22 22.25 Ton Dated 14-4-22 51.84 Ton dated 26-5-22

## Anx J
Anx "J"
Status of Interim Payment Certificates
Project Control Unit:- Construction of 10th Ave from IJP to Srinagar Highway
Ser | IPC No | Date of Approval by Consultant / Client | Submission Date | Mob Adv | Vetted Work Done | Deduction | [6 empty] | Receivable from Client | Received From Client | Remarks
[6 empty] | Retention Money | Mob Adv | Secured Adv | water charges | Withheld due to SP Items | IT | Total
1 | IPC No. 1 | 2022-11-10 | 2022-10-26 |  | 482.3428 | 48.2343 | [5 empty] | 48.2343 | 434.1085 | 55.565 | 1st installment (Rs 55,565,000) of IPC No. 1 Received
2 | Mob Adv | 2022-04-26 |  | 771.4684 |  |  |  |  | 0 |  |  |  | 771.4684 | 771.4684 | 1st installment (Rs 771.47 M) of Mob advance Received
3 | Mob Adv | 2022-06-25 |  | 400.096 |  |  |  |  | 0 |  |  |  | 400.096 | 400.096 | 2nd Installment (Rs.400.096 Mn) of Mob advance Received
4 | IPC No 2 | 2023-06-07 | 2023-06-02 |  | 425.6822 | 42.5682 | [5 empty] | 42.5682 | 383.114 | 761.6575 | Combined cheque
5 | Mob Adv | 2023-06-23 |  | 371.3724 |  |  |  |  | 0 |  |  |  | 371.3724 | 371.3724
6 | EPC No. 1 & 2 | 2023-06-23 | [6 empty] | 0 |  |  |  | 173.2605 | 173.2605
7 | IPC No 3 | 2024-03-22 | 2024-03-18 |  | 134.6884 | 13.4688 |  |  | 5.2136 |  |  | 18.6824 | 116.006 | 116.006 | B108774 dated 14-5-24, Combined cheque amount 147,054,864
8 | IPC No 4 | 2024-06-25 | 2024-06-10 |  | 218.779 | 21.8779 | 44.573 |  | 1.0939 |  |  | 67.5448 | 151.2342 | 151.2342 | B108784 dated 25-6-24, Combined cheque amount 185,529,370
9 | EPC No. 3 (Against IPC-03& 04) | 2024-10-23 | 2024-09-29 | [9 empty] | 118.498
10 | IPC No 5 | 2024-11-13 | 2024-10-31 |  | 140.1425 | 14.0143 | 17 |  | 0.70071 |  |  | 31.715 | 108.4276 | 108.4276 | B108793 dated 7-1-25, Combined cheque amount 131,146,790
11 | IPC No 6 | 2025-02-12 | 2025-02-07 |  | 158.6016 | 15.8602 | 68.35 |  | 0.79301 |  |  | 85.0032 | 73.5985 | 73.5985 | A921029 dated 28-4-25, Combined cheque amount 96,117,957
12 | IPC No 7 | 23/5/2025 | 14/5/2025 |  | 162.8321 | 16.2832 | 25 |  | 0.81416 |  |  | 42.0974 | 120.7347 | 120.7347 | A921036 dated 17-6-25, Combined cheque amount 146,791,165
13 | IPC No 8 | 20/6/2025 | 18/6/2025 |  | 328.2684 | 32.8268 | 97.676 |  | 1.6413 | 7 | 45.9855 | 185.1297 | 143.1388 | 143.1388 | A921037 dated 25-6-25, Combined cheque amount 192,140,454
Grand Total Amount |  |  |  | 1542.9367 | 2051.337 | 205.1337 | 252.599 | 0 | 10.2567 | 7 | 45.9855 | 520.9749 | 3365.0574 | 3246.5594
10.2567
|  | 2051337048 |  |  | 137.8321 | 120.7347 | 1290.3377 | [5 empty] | 118.498 | 118.498 | 3246559361.2
1.5632e-13
|  |  |  | 3594.2738 | 162832080 |  | 3594.2738 |  | 229.2164 |  |  | 1542.94 | 1542.94 |  | 3246559361.2
[5 empty] | 160895981 | [6 empty] | 1261.49 | 1041.656
[5 empty] | -1936099 | [6 empty] | 173.26 | 173.26
[12 empty] | 2977.69 | 2757.856
[5 empty] | 147.0549 | [6 empty] | 2834.955 | -77.099
13.4688
5.2136
|  |  |  | 6.5%DC | 12.3665
|  |  |  | water | 5.2136 |  |  | 75000
[5 empty] | 110.7924 |  |  | 738
101.626
75276
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!

## Anx K
Anx "K"
STATE OF CLAIMS / VARIATION ORDERS
Ser | Type of Claim | Work Done During the Month | Runing Total up to Date | Runing Total YTD | Vetted Workdone up to Date | Vetted Workdone Year to Date
1 | EPC | 0 | 488.431 | 0 | 0 | 0
2
3
4
5
Total |  | 0 | 488.431 | 0 | 0 | 0

## Anx H
Anx "H"
Detail of Equipments, Plants & Machinery & Vehicles
2025-07-01
Ser | Regd No | Description | During Month
|  |  | POL (Ltr) (1-15 Jul) | Rate | Amount | POL (Ltr) (16-31 Jul) | Rate | Amount | Total Amount of Fuel Issued | Repair/ Maint | Total Amount Payable
PETROL
2 | ADP 625 | Motor Cycle CD-70 | 15 | 267.71 | 4015.65 | 0 | 259.34 | 0 | 4015.65 |  | 4015.65
3 | 860933 | Motor Cycle CD-70 | 32 | 267.71 | 8566.72 | 0 | 259.34 | 0 | 8566.72 |  | 8566.72
4 | 895358 | Motor Cycle CD-70 | 0 | 267.71 | 0 | 0 | 259.34 | 0 | 0 |  | 0
5 | 921570 | Motor Cycle CD-70 | 0 | 267.71 | 0 | 0 | 259.34 | 0 | 0 |  | 0
6 | 8322 | Motor Cycle CD-70 | 24 | 267.71 | 6425.04 | 0 | 259.34 | 0 | 6425.04 |  | 6425.04
7 | - | 3xGen set 3kv | 35 | 267.71 | 9369.85 | 0 | 259.34 | 0 | 9369.85 |  | 9369.85
8 | - | 3xViberator s | 0 | 267.71 | 0 | 0 | 259.34 | 0 | 0 |  | 0 |  | 42 | 10416 | 38793.26
Total:- |  |  | 106 |  |  | 0 |  |  | 28377.26 |  | 28377.26 | 106
HSD
9 | GAS-192 | Revo D/Cabin | 97 | 260 | 25220 | 75 | 270.4 | 20280 | 45500 |  | 45500 |  | 172
10 | 895650 | D/Cabin | 76 | 260 | 19760 | 117 | 270.4 | 31636.8 | 51396.8 |  | 51396.8 |  | 193
11 | IDS 5313 | S/Cabin | 38 | 260 | 9880 | 0 | 270.4 | 0 | 9880 |  | 9880 |  | 38
12 | GAB 779 | S/Cabin | 98 | 260 | 25480 | 76 | 270.4 | 20550.4 | 46030.4 |  | 46030.4 |  | 174
13 | - | TM 8510205 | 145 | 260 | 37700 | 260 | 270.4 | 70304 | 108004 |  | 108004 |  | 405
14 | GAT 465 | ISUZU 1.8 Ton | 94 | 260 | 24440 | 69 | 270.4 | 18657.6 | 43097.6 |  | 43097.6 |  | 163
15 | Gen | Gen 100 KVA | 60 | 260 | 15600 | 20 | 270.4 | 5408 | 21008 |  | 21008 |  | 80
16 | Gen | Gen 60 KVA | 50 | 260 | 13000 | 0 | 270.4 | 0 | 13000 |  | 13000 |  | 50
17 | Gen | Gen 5 KVA | 0 | 260 | 0 |  | 270.4 | 0 | 0 |  | 0 |  | 0
18 | - | Plant Gen 250 KVA | 400 | 260 | 104000 | 400 | 270.4 | 108160 | 212160 |  | 212160 |  | 800
19 | - | Water Bowzer Sec-1 | 0 | 260 | 0 | 40 | 270.4 | 10816 | 10816 |  | 10816 |  | 40
20 | E-556 | Crane 50 Ton | 290 | 260 | 75400 | 0 | 270.4 | 0 | 75400 |  | 75400 |  | 290
21 | E-452 | Road Roller | 40 | 260 | 10400 | 0 | 270.4 | 0 | 10400 |  | 10400 |  | 40
22 | E-507 | Road Roller | 70 | 260 | 18200 | 50 | 270.4 | 13520 | 31720 |  | 31720 |  | 120
23 | E542 | Grader |  | 260 | 0 | 0 | 270.4 | 0 | 0 |  | 0 |  | 0
24 | E548 | Grader | 160 | 260 | 41600 | 40 | 270.4 | 10816 | 52416 |  | 52416 |  | 200
24 | JV 5825 | Dump Truck | 140 | 260 | 36400 | 230 | 270.4 | 62192 | 98592 |  | 98592 |  | 370
25 | AA-161 | Dump Truck |  | 260 | 0 |  | 270.4 | 0 | 0 |  | 0 |  | 0
Total:- |  |  | 1758 |  | 457080 | 1377 |  | 372340.8 | 829420.8 | 0 | 829420.8 | 3135
Hired Vehicles Plant / Machinery | [8 empty] | 0 | 0 | 0
26 | Solar-160 | Exvtr | 470 | 260 | 122200 | 440 | 270.4 | 118976 | 241176 |  | 241176 |  |  | 910
27 | B-950 | Loader | 220 | 260 | 57200 | 160 | 270.4 | 43264 | 100464 |  | 100464 |  |  | 380
28 | E-950 | Loader | 250 | 260 | 65000 | 130 | 270.4 | 35152 | 100152 |  | 100152 |  |  | 380
29 | 251 | Roller |  | 260 | 0 |  | 270.4 | 0 | 0 |  | 0 |  |  | 0
30 | 9526 | TM | 130 | 260 | 33800 | 0 | 270.4 | 0 | 33800 |  | 33800 |  |  | 130
31 | 550 | TM | 165 | 260 | 42900 | 255 | 270.4 | 68952 | 111852 |  | 111852 |  |  | 420
32 | 8630 | Tractor | 90 | 260 | 23400 | 20 | 270.4 | 5408 | 28808 |  | 28808 |  |  | 110
33 | 2336 | Tractor | 80 | 260 | 20800 | 30 | 270.4 | 8112 | 28912 |  | 28912 |  |  | 110
34 | 1622 | Tractor |  | 260 | 0 |  | 270.4 | 0 | 0 |  | 0 |  |  | 0
35 | 1191 | Lifter Crane |  | 260 | 0 |  | 270.4 | 0 | 0 |  | 0 |  |  | 0
36 | LE 142 | Dumper | 130 | 260 | 33800 | 210 | 270.4 | 56784 | 90584 |  | 90584 |  |  | 340
37 | 497 | C/Pump |  | 260 | 0 |  | 270.4 | 0 | 0 |  | 0 |  |  | 0
38 | 273 | Lifter Crane | 70 | 260 | 18200 | 65 | 270.4 | 17576 | 35776 |  | 35776 |  |  | 135
39 | 247 | TM | 220 | 260 | 57200 | 80 | 270.4 | 21632 | 78832 |  | 78832 |  |  | 300
Total:- |  |  | 1825 |  | 474500 | 1390 |  | 375856 | 850356 | 0 | 850356 | 3215
G Total:- | [8 empty] | 1708154.06 | 0 | 1708154.06

## Sheet4 (hidden)
|  | Qty | Amount
| = | 13.15 | 4.997 |  |  | 380000 |  |  |  |  | 24264900
|  | 12.5 | 4.75 |  |  | 380000
|  | 12.14 | 4.6132 |  |  | 380000
|  | 13.125 | 4.9875 |  |  | 380000
|  | 12.94 | 4.9172 |  |  | 380000
2024-10-09 |  | 39.71 | 14.7324 | [7 empty] | #REF!
2024-10-17 |  | 40.75 | 15.1182 | [7 empty] | #REF!
2024-12-20 |  | 40 | 14.84 | 184.315 | 68.9556 | 374118.0045 | 9352.9501 |  |  |  |  | Ser | Description | Bill 1 |  |  |  | Bill 1
2025-01-15 |  | 40.02 | 14.8474 |  |  |  | 0.009353 | 0.009346 |  |  |  | A | PT Bridge | Unit | Qty | Rate | Amount | Unit | Qty | Rate | Amount
2025-02-27 |  | 14.97 | 5.5539 | [8 empty] | 1 | Trumpets 250x250x 35 | Nos | 194 | 5394.9 | 1046610.6 | Nos | 193 | 5394.9 | 1041215.7 | 387 | 2.0878 | 2.0878
|  | 25.51 | 9.4642 | [8 empty] | 2 | Trumpets 270x270x 35 | Nos | 90 | 6477.71 | 582993.9 | Nos | 90 | 6477.71 | 582993.9 | 180 | 1.166 | 1.166
[12 empty] | 3 | Stressing Block 12 Holes | Nos | 194 | 3385.99 | 656882.06 | Nos | 193 | 3385.99 | 653496.07 | 387 | 1.3104 | 1.3104
[12 empty] | 4 | Stressing Block 15 Holes | Nos | 90 | 4908.28 | 441745.2 | Nos | 90 | 4908.28 | 441745.2 | 180 | 0.88349 | 0.88349
[12 empty] | 5 | Wedges 0.5" Dia | Nos | 3490 | 276.43 | 964740.7 | Nos | 3490 | 276.43 | 964740.7 | 6980 | 1.9295 | 1.9295
|  | 264.815 | 98.8211 | [8 empty] | 6 | Sheath 75mm | LM | 1617 | 295.54 | 477888.18 | LM | 1616 | 295.54 | 477592.64 | 3233 | 0.95548 | 0.95548
|  | 184.625 | 69.02 | 94.4643 | 25.4443 | 25444292.2298 | [5 empty] | 7 | Sheath 78mm | LM | 81 | 298.09 | 24145.29 | LM | 82 | 298.09 | 24443.38 | 163 | 0.048589 | 0.048589
|  | 80.19 | 29.8011 | [8 empty] | 8 | Sheath 65mm | LM | 2933 | 252.23 | 739790.59 | LM | 2934 | 252.23 | 740042.82 | 5867 | 1.4798 | 1.4798
[12 empty] | 9 | Sheath 68mm | LM | 70 | 247.13 | 17299.1 | LM | 70 | 247.13 | 17299.1 | 140 | 0.034598 | 0.034598
[8 empty] | 187057 |  |  |  | 10 | Plastic Saddle | Nos | 142 | 70.06 | 9948.52 | Nos | 141 | 70.06 | 9878.46 | 283 | 0.019827 | 0.019827
[8 empty] | 221492 |  |  |  |  | Total |  |  |  | 4962044.14 |  |  |  | 4953447.97
[8 empty] | 408549 | 67 | 27.3728 | [10 empty] | 9915492.11
|  | 64.14 | 380000 | 24.3732
|  | 120.485 | 371000 | 44.6999
|  |  |  | 69.0731 | 94.4643 | 25.3912
0.0032611

## Steel consumption (hidden)
STEEL CONSUMPTION SUMMARY
Ser | Description | Unit | Total Qty Received | Total Qty ACT CONSUMED | Total Qty CONSUMED | ADJUSTED | BAL QTY | IN STORE QTY | UN-ADJUSTED
1 | ASTM 615, GR-60 - 10mm | Tons | 119.628 | 82.4093 | 93.126 | 10.7168 | 26.502 | 18.364 | 8.138
2 | ASTM 615, GR-60 - 12mm | Tons | 1190.385 | 987.5895 | 1029.0842 | 41.4948 | 161.3008 | 85.193 | 76.1078
3 | ASTM 615, GR-60 - 16mm | Tons | 1351.066 | 1262.2247 | 1262.2247 | 0 | 88.8413 | 100.072 | -11.2307
4 | ASTM 615, GR-60 - 20mm | Tons | 234.146 | 167.6816 | 183.9212 | 16.2396 | 50.2248 | 30 | 20.2248
5 | ASTM 615, GR-60 - 25mm | Tons | 1205.341 | 1073.1257 | 1153.8047 | 80.679 | 51.5363 | 30 | 21.5363
6 | ASTM 615, GR-60 - 32mm | Tons | 1386.255 | 1342.0793 | 1378.755 | 36.6757 | 7.5 | 7.5 | 0
7 | SCRAP | Tons | [5 empty] | 17.5 | -17.5
TOTAL |  |  | 5486.821 | 4915.1101 | 5100.916 | 185.8058 | 385.905 | 288.629 | 97.276
[5 empty] | 5055 |  | 431.821

## Sheet1 (2) (hidden)
MSE Wall Railway Br
| Bearing pad |  |  | Nos | Length | Width | Thickness | Qty CCM |  | Nos | Length | Width | Thickness | Qty CCM
| Ramp A | 444656.3 |  | 30 | 42.5 | 45 | 7.75 | 444656.25 | Ramp A | 30 | 42.5 | 45 | 7.75 | 444656.25 | 6 | 2667937.5
| Ramp B | 1534500 |  | 110 | 40 | 45 | 7.75 | 1534500 | Br-02 | 12 | 42.5 | 45 | 7.75 | 177862.5 | 3.75 | 666984.375 | 666981
| Nikki Lae01 | 418500 |  | 30 | 40 | 45 | 7.75 | 418500 | Br-03 | 12 | 42.5 | 45 | 7.75 | 177862.5 | 3.75 | 666984.375 | 666981
| Nikki Lae01A | 279000 |  | 20 | 40 | 45 | 7.75 | 279000 | [5 empty] | 800381.25
| Br-02 | 177862 |  | 12 | 42.5 | 45 | 7.75 | 177862.5
| Br-03 | 177862 |  | 12 | 42.5 | 45 | 7.75 | 177862.5 | Ramp B | 110 | 40 | 45 | 7.75 | 1534500 | 6 | 9207000 | 9207000
| Rly Br | 2319187.5 |  | 140 | 47.5 | 45 | 7.75 | 2319187.5 | Nikki Lae01 | 30 | 40 | 45 | 7.75 | 418500 | 3.75 | 1569375 | 1569361
|  | 5351567.8 | [6 empty] | Nikki Lae01A | 20 | 40 | 45 | 7.75 | 279000 | 3.75 | 1046250 | 1046241
[14 empty] | 2232000 |  | 3949593.75 | 3949564
|  | 355725 | 6 | 2134350 |  |  |  |  | Rly Br | 140 | 47.5 | 45 | 7.75 | 2319187.5 | 6 | 13915125 | 13915128
|  | 697500 | 7 | 4882500 | [11 empty] | 33689250
|  | 1159593.75 | 8 | 9276750
|  | 2212818.75 |  | 16293600
3949563
[8 empty] | 425x450x77.5 Bearing pad | [8 empty] | 69
400x450x77.5 Bearing pad

## Sheet2 (hidden)
Lean | 1152.8 | 989.29 | 163.51
A3 sRC | 6443.3 | 6043.25 | 400.05
A3 OPC | 11342.1 | 11261.2 | 80.9
A1 | 3815.8 | 3715.75 | 100.05
A2 | 30.3 | 30.25 | 0.05
Class B | 3059.1 | 2738.95 | 320.15
D1 | 1130.3 | 1130.25 | 0.05
D2 | 5981.3 | 5981.25 | 0.05
1064.81

## Steel Detail (hidden)
Detail of Steel (Dia Wise)
Ser | Description | Date | A/U | Weight (Ton) | Rate (Rs) | Amount (rS) | Amount (Mn) | Remarks
1 | 10mm Dia Steel
i | Pak Steel | 2022-05-26 | Ton | 1 | 203000 | 203000 | 0.203
i | Pak Steel | 2022-11-08 | Ton | 2.16 | 223500 | 482760 | 0.48276
i | Pak Steel | 2022-11-27 | Ton | 17.8 | 223500 | 3978300 | 3.9783
i | SJ Steel | 2024-01-02 | Ton | 5 | 263700 | 1318500 | 1.3185
i | SJ Steel | 2024-03-06 | Ton | 24.82 | 264700 | 6569854 | 6.5699
i | Mughal Steel | 2024-05-16 | Ton | 16.31 | 261200 | 4260172 | 4.2602
i | Mughal Steel | 2024-05-16 | Ton | 12.98 | 261200 | 3390376 | 3.3904
i | Mughal Steel | 2024-09-09 | Ton | 9.96 | 261200 | 2601552 | 2.6016
i | Mughal Steel | 2025-04-25 | Ton | 19.925 | 244700 | 4875647.5 | 4.8756
| From Other Proj |  | Ton | 9.673 |  | 2571902.5597 | 2.5719
Total |  |  |  | 119.628 |  | 30252064.0597 | 30.2521 |  | 119.628 | 30.2521 | 0 | 0
2 | 12mm Dia Steel
i | Nomee Steel | 2022-04-13 | Ton | 27.75 | 199000 | 5522250 | 5.5222 |  | 5522250
ii | Nomee Steel | 2022-04-14 | Ton | 22.25 | 199000 | 4427750 | 4.4277
iii | Pak Steel | 2022-05-26 | Ton | 34.34 | 202000 | 6936680 | 6.9367
iv | Pak Steel | 2022-05-26 | Ton | 17.5 | 202000 | 3535000 | 3.535
v | Pak Steel | 2022-09-19 | Ton | 31.04 | 225500 | 6999520 | 6.9995
vi | Pak Steel | 2022-09-19 | Ton | 44.45 | 225500 | 10023475 | 10.0235
vii | Pak Steel | 2022-10-10 | Ton | 37.62 | 225500 | 8483310 | 8.4833
viii | Pak Steel | 2022-10-13 | Ton | 36.62 | 225500 | 8257810 | 8.2578
ix | Pak Steel | 2022-11-23 | Ton | 30.4 | 222500 | 6764000 | 6.764
x | SJ Steel | 2022-12-20 | Ton | 19.95 | 226000 | 4508700 | 4.5087
xi | SJ Steel | 2023-01-23 | Ton | 19.77 | 237000 | 4685490 | 4.6855
xii | SJ Steel | 2024-01-15 | Ton | 49.28 | 262700 | 12945856 | 12.9459
xiii | SJ Steel | 2024-02-06 | Ton | 29.46 | 262700 | 7739142 | 7.7391
xiv | SJ Steel | 2024-02-06 | Ton | 30.86 | 262700 | 8106922 | 8.1069
xiv | SJ Steel | 2024-03-06 | Ton | 49.85 | 263700 | 13145445 | 13.1454 |  | 15804859.5 | 59.935
xv | SJ Steel | 2024-03-24 | Ton | 40.75 | 263700 | 10745775 | 10.7458
xvi | SJ Steel | 2024-03-24 | Ton | 59.93 | 263700 | 15803541 | 15.8035
xvi | SJ Steel | 2024-03-24 | Ton | 29.97 | 263700 | 7903089 | 7.9031
xvi | SJ Steel | 2024-03-24 | Ton | 51.03 | 263700 | 13456611 | 13.4566
xvi | SJ Steel | 2024-07-27 | Ton | 199.91 | 260200 | 52016582 | 52.0166
xvi | Mughal Steel | 2025-04-25 | Ton | 79.875 | 243700 | 19465537.5 | 19.4655
| From Other Proj |  | Ton | 259.31 |  | 67738196.5 | 67.7382
| To Other Projs |  |  | -11.53 |  | -3476295 | -3.4763
Total |  |  |  | 1190.385 |  | 295734387 | 295.7344 | 295.7344 | 0
3 | 16mm Dia Steel
i | Nomee Steel | 2022-04-13 | Ton | 50 | 199000 | 9950000 | 9.95
ii | Pak Steel | 2022-05-26 | Ton | 15 | 202000 | 3030000 | 3.03
iii | Pak Steel | 2022-05-26 | Ton | 49.87 | 202000 | 10073740 | 10.0737
iv | Pak Steel | 2022-09-08 | Ton | 51.71 | 226500 | 11712315 | 11.7123
v | Pak Steel | 2022-09-08 | Ton | 45.4 | 226500 | 10283100 | 10.2831
vi | Pak Steel | 2022-09-08 | Ton | 22.89 | 226500 | 5184585 | 5.1846
vii | SJ Steel | 2022-09-09 | Ton | 20.08 | 226000 | 4538080 | 4.5381 |  | 20.2577
viii | SJ Steel | 2022-10-19 | Ton | 2.665 | 227000 | 604955 | 0.60496
ix | Pak Steel | 2022-10-31 | Ton | 35.8 | 222500 | 7965500 | 7.9655
x | Pak Steel | 2022-10-31 | Ton | 61.1 | 222500 | 13594750 | 13.5947
xi | Pak Steel | 2022-11-23 | Ton | 20.23 | 222500 | 4501175 | 4.5012
xii | Pak Steel | 2022-11-27 | Ton | 100 | 222500 | 22250000 | 22.25
xiii | Pak Steel | 2022-11-27 | Ton | 30.28 | 222500 | 6737300 | 6.7373
xiv | Pak Steel | 2022-12-02 | Ton | 2.47 | 222500 | 549575 | 0.54958
xv | Pak Steel | 2023-03-13 | Ton | 12 | 301500 | 3618000 | 3.618
xvi | SJ Steel | 2024-01-15 | Ton | 40.09 | 262700 | 10531643 | 10.5316
xvii | SJ Steel | 2024-02-06 | Ton | 55.13 | 262700 | 14482651 | 14.4827
xviii | SJ Steel | 2024-02-06 | Ton | 54.32 | 262700 | 14269864 | 14.2699
xix | Mughal Steel | 2024-03-13 | Ton | 99.99 | 263700 | 26367363 | 26.3674
xx | SJ Steel | 2024-03-14 | Ton | 49.325 | 263700 | 13007002.5 | 13.007
xxi | SJ Steel | 2024-03-14 | Ton | 50.67 | 263700 | 13361679 | 13.3617
xxi | SJ Steel | 2024-09-09 | Ton | 99.88 | 260200 | 25988776 | 25.9888
xvi | Mughal Steel | 2025-04-25 | Ton | 249.97 | 243700 | 60917689 | 60.9177
| From Other Proj |  | Ton | 148.836 |  | 39399987.1391 | 39.4
| To Other Projs |  |  | -16.64 |  | -5.017 | -5.017e-06
Total |  |  |  | 1351.066 |  | 332919724.6221 | 332.9197 | 1351.066 | 249.5856 | 83.3341 | 22.4165
4 | 20mm Dia Steel
i | Nomee Steel | 2022-04-13 | Ton | 11.14 | 199000 | 2216860 | 2.2169
ii | Nomee Steel | 2022-04-14 | Ton | 38.56 | 199000 | 7673440 | 7.6734
iii | SJ Steel | 2023-01-23 | Ton | 10.08 | 237000 | 2388960 | 2.389
iv | SJ Steel | 2024-02-06 | Ton | 20 | 262700 | 5254000 | 5.254
v | SJ Steel | 2024-03-14 | Ton | 15 | 263700 | 3955500 | 3.9555
v | Mughal Steel | 2024-05-16 | Ton | 49.92 | 260200 | 12989184 | 12.9892
v | Mughal Steel | 2024-09-09 | Ton | 29.84 | 260200 | 7764368 | 7.7644
| From Other Proj |  | Ton | 68.069 |  | 17779622.8 | 17.7796
| To Other Projs |  |  | -8.463 | -2.314 | -8731791.6 | -8.7318
Total |  |  |  | 234.146 |  | 51290143.2 | 51.2901 | 51.2901 | 234.146 | 51.2901 | 0 | 0
5 | 25mm Dia Steel
i | Nomee Steel | 2022-04-21 | Ton | 50 | 205500 | 10275000 | 10.275
ii | Nomee Steel | 2022-05-12 | Ton | 50 | 205500 | 10275000 | 10.275
iii | Pak Steel | 2022-05-18 | Ton | 47.85 | 202500 | 9689625 | 9.6896
iv | Pak Steel | 2022-05-26 | Ton | 15.75 | 202000 | 3181500 | 3.1815
v | Pak Steel | 2022-05-26 | Ton | 36.4 | 202500 | 7371000 | 7.371
vi | Nomee Steel | 2022-06-29 | Ton | 56 | 225500 | 12628000 | 12.628
vii | SJ Steel | 2022-07-01 | Ton | 22.255 | 223500 | 4973992.5 | 4.974
viii | SJ Steel | 2022-07-05 | Ton | 22.105 | 223500 | 4940467.5 | 4.9405
ix | Pak Steel | 2022-09-08 | Ton | 51.72 | 226500 | 11714580 | 11.7146
x | Pak Steel | 2022-09-08 | Ton | 36.52 | 226500 | 8271780 | 8.2718
xi | Pak Steel | 2022-09-08 | Ton | 46.88 | 226500 | 10618320 | 10.6183
xii | Pak Steel | 2022-09-08 | Ton | 45.32 | 226500 | 10264980 | 10.265
xiii | Pak Steel | 2022-09-08 | Ton | 7 | 226500 | 1585500 | 1.5855
xiv | Pak Steel | 2022-09-08 | Ton | 50.47 | 226500 | 11431455 | 11.4315
xv | Pak Steel | 2022-09-08 | Ton | 12.09 | 226500 | 2738385 | 2.7384
xvi | SJ Steel | 2022-09-09 | Ton | 20.02 | 226000 | 4524520 | 4.5245
xvii | SJ Steel | 2022-09-09 | Ton | 20.06 | 226000 | 4533560 | 4.5336
xviii | SJ Steel | 2022-10-01 | Ton | 9 | 226000 | 2034000 | 2.034
xix | Pak Steel | 2022-01-13 | Ton | 36.49 | 225500 | 8228495 | 8.2285
xx | Pak Steel | 2022-10-20 | Ton | 85.51 | 225500 | 19282505 | 19.2825
xxi | Pak Steel | 2022-10-31 | Ton | 27.98 | 225500 | 6309490 | 6.3095
xxii | SJ Steel | 2022-11-15 | Ton | 15.54 | 227000 | 3527580 | 3.5276 |  | 3527580
xxiii | Pak Steel | 2022-11-23 | Ton | 129.78 | 222500 | 28876050 | 28.876
xxiv | SJ Steel | 2022-01-23 | Ton | 19.97 | 237000 | 4732890 | 4.7329
xxv | Pak Steel | 2023-03-13 | Ton | 48.79 | 301500 | 14710185 | 14.7102
ix | SJ Steel | 2024-03-19 | Ton | 49.94 | 263700 | 13169178 | 13.1692
x | SJ Steel | 2024-03-13 | Ton | 49.94 | 263700 | 13169178 | 13.1692
x | Mughal Steel | 2024-03-30 | Ton | 99.915 | 260200 | 25997883 | 25.9979
x | Mughal Steel | 2024-09-09 | Ton | 25 | 260200 | 6505000 | 6.505
| From Other Proj |  | Ton | 50.604 |  | 14137056.212 | 14.1371
| To Other Projs |  |  | -33.558 |  | -8731791.6 | -8.7318
Total |  |  |  | 1205.341 |  | 280965363.612 | 280.9654 | 0 | 1205.341 | 280.9654 | 0 | 0
6 | 32mm Dia Steel
i | Nomee Steel | 2022-04-21 | Ton | 50 | 205500 | 10275000 | 10.275
ii | Nomee Steel | 2022-06-13 | Ton | 50 | 205500 | 10275000 | 10.275
iii | Pak Steel | 2022-06-28 | Ton | 49.93 | 225500 | 11259215 | 11.2592
vi | Pak Steel | 2022-06-28 | Ton | 6.15 | 225500 | 1386825 | 1.3868
v | SJ Steel | 2022-07-01 | Ton | 21.8 | 223500 | 4872300 | 4.8723
vi | SJ Steel | 2022-07-05 | Ton | 22.12 | 223500 | 4943820 | 4.9438
vii | Pak Steel | 2022-10-13 | Ton | 82.22 | 225500 | 18540610 | 18.5406
viii | Pak Steel | 2022-10-13 | Ton | 46.6 | 225500 | 10508300 | 10.5083
ix | SJ Steel | 2022-10-19 | Ton | 71.365 | 227000 | 16199855 | 16.1999
x | Pak Steel | 2022-10-31 | Ton | 61.23 | 225500 | 13807365 | 13.8074
xi | Pak Steel | 2022-10-31 | Ton | 37.24 | 225500 | 8397620 | 8.3976
xii | SJ Steel | 2022-11-15 | Ton | 71.1 | 227000 | 16139700 | 16.1397
xiii | Pak Steel | 2022-11-08 | Ton | 19 | 225500 | 4284500 | 4.2845
xiv | SJ Steel | 2022-12-20 | Ton | 48.925 | 226000 | 11057050 | 11.0571
xv | Amreli | 2022-01-20 | Ton | 49.98 | 188500 | 9421230 | 9.4212
xvi | Pak Steel | 2023-03-13 | Ton | 2.53 | 301500 | 762795 | 0.76279
xvii | SJ Steel | 2024-01-08 | Ton | 5 | 263700 | 1318500 | 1.3185
xviii | SJ Steel | 2024-02-14 | Ton | 14.78 | 263700 | 3897486 | 3.8975
xix | SJ Steel | 2024-03-13 | Ton | 66.17 | 264700 | 17515199 | 17.5152
xx | SJ Steel | 2024-03-13 | Ton | 83.78 | 264700 | 22176566 | 22.1766
xx | Mughal Steel | 2024-04-29 | Ton | 199.895 | 264700 | 52912206.5 | 52.9122
xx | Mughal Steel | 2024-04-30 | Ton | 99.84 | 264700 | 26427648 | 26.4276
xx | Mughal Steel | 2024-05-16 | Ton | 48.57 | 261200 | 12686484 | 12.6865
xx | Mughal Steel | 2024-05-16 | Ton | 51.285 | 261200 | 13395642 | 13.3956
xx | Mughal Steel | 2024-09-09 | Ton | 51.14 | 261200 | 13357768 | 13.3578
xx | Mughal Steel | 2024-09-09 | Ton | 48.77 | 261200 | 12738724 | 12.7387
| From Other Proj |  |  | 51.815 |  | 13682753.3413 | 13.6828
| To Other Projs |  |  | -24.98 |  | -7036183 | -7.0362
Total |  |  |  | 1386.255 |  | 335203978.8413 | 335.204 | 335.204 | 1386.255 | 335.204 | 0 | 0
6 | 36mm Dia Steel
i | From Other Proj |  | Ton | 10.062 | 259260 | 2608674.12 | 2.6087
Total |  |  |  | 10.062 |  | 2608674.12 | 2.6087 | 3796.3582 | 0.23316
| G Total |  |  | 5496.883 |  | 1328974335.4551 | 1328.9743
From Other Proj
1 | 32mm | 28-3-24 | Ton | 33.39 | 264700 | 8838333 | 8.8383 | Parking plaza
2 | 32mm | 13-7-24 | Ton | 3.985 | 261200 | 1040882 | 1.0409 | PECB
3 | 32mm | 22-10-24 | Ton | 1.997 | 287500.0347 | 574137.5692 | 0.57414 | DHA/NLC
4 | 32mm | 22-10-24 | Ton | 2.381 | 260699.9799 | 620726.652 | 0.62073 | Lae Proj NLC | [5 empty] | 20300 | 314.41 | 7531300 | 371
| Total for 32mm |  |  | 41.753 |  | 11074079.2213 | 11.0741 | [6 empty] | 39710 | 314.41 | 14732410 | 371
5 | 10mm | 22-10-24 | Ton | 1.723 | 287500.0347 | 495362.5597 | 0.49536 | DHA/NLC | [7 empty] | 22263710
5 | 10mm | 17-3-25 | Ton | 3.41 | 261200 | 890692 | 0.89069 | PECB | [7 empty] | 36996120
| 10mm | 17-3-25 | Ton | 4.54 | 261200 | 1185848 | 1.1858 | Yarik Sagu
| Total for 10mm |  |  | 9.673 |  | 2571902.5597 | 2.5719 | [8 empty] | 22.2637
6 | 12mm | 2023-09-10 | Ton | 4.283 | 262700 | 1125144.1 | 1.1251 | Bharakahu
7 | 12mm | 22-10-24 | Ton | 20.274 | 261200 | 5295568.8 | 5.2956 | dHA/NLC
8 | 12mm | 22-10-24 | Ton | 8.823 | 261200 | 2304567.6 | 2.3046 | Lae Proj NLC
| 12mm | 17-3-25 | Ton | 225.93 | 261200 | 59012916 | 59.0129 | Yarik Sagu
| 12mm | 30-3-23 | Ton |  | 261200 | 0 | 0 | dHA/NLC |  |  | 57.68 | 16583002 | 287500.0347
| Total for 12mm |  |  | 259.31 |  | 67738196.5 | 67.7382
9 | 16mm | 22-10-24 | Ton | 20.073 | 287500.0347 | 5770988.196 | 5.771 | DHA/NLC |  |  | 64.549 | 16827923 | 260699.9799
10 | 16mm | 22-10-24 | Ton | 7.793 | 260699.9799 | 2031634.9431 | 2.0316 | Lae Proj NLC
10 | 16mm | 17-3-25 | Ton | 120.97 | 261200 | 31597364 | 31.5974 | Yarik Sagu
| Total for 16mm |  |  | 148.836 |  | 39399987.1391 | 39.4
9 | 20mm Dia Steel | 22-10-24 | Ton | 13.613 | 261200 | 3555715.6 | 3.5557 | Lae Proj NLC
9 | 20mm Dia Steel | 22-10-24 | Ton | 0.536 | 261200 | 140003.2 | 0.14 | Lae Proj NLC
10 | 16mm | 17-3-25 | Ton | 53.92 | 261200 | 14083904 | 14.0839 | Yarik Sagu
| Total for 20mm |  |  | 68.069 |  | 17779622.8 | 0.14
9 | 25mm Dia Steel | 22-10-24 | Ton | 34.954 | 287500.0347 | 10049276.212 | 10.0493 | Lae Proj NLC
10 | 25mm | 17-3-25 | Ton | 15.65 | 261200 | 4087780 | 4.0878 | Yarik Sagu
| Total for 25mm |  |  | 50.604 |  | 14137056.212 | 14.1371
9 | 36mm Dia Steel | 22-10-24 | Ton | 10.062 | 259260 | 2608674.12 | 2.6087 | Lae Proj NLC |  |  | ASTM 615, GR-60 - 10mm | 119.628 | 30.2521 | 119.628
| Total for 32mm |  |  | 10.062 |  | 2608674.12 | 2.6087 |  |  |  | ASTM 615, GR-60 - 12mm
|  |  |  | 588.307 | [6 empty] | ASTM 615, GR-60 - 16mm
ASTM 615, GR-60 - 20mm
| To Other Projs | [9 empty] | ASTM 615, GR-60 - 25mm
| 12mm | 30-03-23 | Ton | 11.53 | 301500 | 3476295 | 3.4763 | Def Chowk |  |  | ASTM 615, GR-60 - 32mm
| Total for 10mm |  |  | 11.53 |  | 3476295 | 3.4763
| 16mm | 30-03-23 | Ton | 16.64 | 301500 | 5016960 | 5.017 | DHA/NLC
| Total for 16mm |  |  | 16.64 |  | 5016960 | 5.017
| 20mm | 30-03-23 | Ton | 2.71 | 301500 | 817065 | 0.81707 | DHA/NLC
| 20mm | 30-03-23 | Ton | 4.248 | 260200 | 1105329.6 | 1.1053 | PECB
| 20mm | 13-1-25 | Ton | 1.505 | 260200 | 391601 | 0.3916 | Def Chowk
| Total for 20mm |  |  | 8.463 |  | 2313995.6 | 2.314
| 25mm | 20-03-23 | Ton | 1 | 260200 | 260200 | 0.2602 | Def Chowk
| 25mm | 25-03-23 | Ton | 3.42 | 260200 | 889884 | 0.88988 | Bhara kahu
| 25mm | 30-03-23 | Ton | 13.41 | 260200 | 3489282 | 3.4893 | DHA/NLC
| 25mm | 27-7-24 | Ton | 3.78 | 260200 | 983556 | 0.98356 | PECB
| 25mm | 24-7-24 | Ton | 6.932 | 260200 | 1803706.4 | 1.8037 | PECB
| 25mm | 13-1-25 | Ton | 1.016 | 260200 | 264363.2 | 0.26436 | Def Chowk
| 25mm | 14-1-25 | Ton | 4 | 260200 | 1040800 | 1.0408 | PECB
| Total for 25mm |  |  | 33.558 |  | 8731791.6 | 8.7318
| 32mm | 30-03-23 | Ton | 12.69 | 301500 | 3826035 | 3.826 | DHA/NLC
| 32mm | 20-05-24 | Ton | 1.09 | 261200 | 284708 | 0.28471 | DHA/NLC
| 32mm | 2024-06-11 | Ton | 2.24 | 261200 | 585088 | 0.58509 | PECB
| 32mm | 2024-06-05 | Ton | 7.18 | 261200 | 1875416 | 1.8754 | PECB
| 32mm | 2024-10-17 | Ton | 1.78 | 261200 | 464936 | 0.46494 | PECB
| Total for 25mm |  |  | 24.98 |  | 7036183 | 7.0362
95.171

## Conc by B Plant (hidden)
Month Apr 24
Conc | Qty | Rate | Amount |  |  | 2024-12-01 | 2024-11-01 | Dif
A3 SRC |  | 15956.75 | 0 |  |  | 6443.25 | 6315.75 | 127.5 | 6517.35 | 768.4 | 400 | 842.5 | 7285.75 | 6043.25 | 96430629.4375 | -272.5 | -4348214.375
A3 OPC | 100.74 | 15827.809 | 1.5945 |  |  | 11352.1 | 11046.5 | 305.6 | 10966.604 | 385.496 | 385.496 |  |  | 10966.604 | 173577313.3674 | -79.896 | -1264578.627
A1 | 32.82 | 13987.6244 | 0.45907 |  |  | 3815.75 | 3815.7499 | 0.00014392 | 3154.636 | 661.114 | 100 |  |  | 3715.75 | 51974515.4983 | -99.9999 | -1398760.4305
A2 Conc | 16.04 | 14405.4 | 0.23106 |  |  | 30.25 | 30.25 | 0 | 61.09 |  |  |  |  | 30.25 | 435763.35 | 0 | 0
D1 | 0 | 18505.15 | 0 |  |  | 1130.25 | 1130.25 | 0 | 992.932 | 137.318 |  |  |  | 1130.25 | 20915445.7875 | 0 | 0
D2 | 0 | 19854.8 | 0 |  |  | 5981.25 | 5711.7509 | 269.4991 | 5459.27 | 521.98 |  |  |  | 5981.25 | 118756522.5 | 269.4991 | 5350851.4542
Lean | 1 | 10231.6 | 0.010232 |  |  | 1452.79 | 1439.29 | 13.5 | 586.293 | 866.497 | 600 | 49 | 1501.79 | 852.79 | 8725406.164 | -586.5 | -6000833.4
Class B | 37.12 | 12323.1 | 0.45743 |  |  | 3059.05 | 2896.55 | 162.5 | 2397 | 662.05 | 320.104 |  |  | 2738.946 | 33752305.4526 | -157.604 | -1942169.8524
|  |  | 0 |  |  | 4511.84 | 4335.84 |  |  | 1528.547 | 920.104 | C |  | 3591.736 | 42477711.6166 | -744.104 | -7943003.2524
|  |  | 0 |  |  | 3591.736 | 3591.736 | [7 empty] | 486056843.0407
|  |  |  | 3011.84 | [11 empty] | 4335.84
[6 empty] | 4511.84 | 744.104
878.6
|  |  |  | 17.6 |  | 878.6 |  | 14864366.164
[8 empty] | 102813329.4375 |  |  |  |  | 13598.2 |  | 20089500 | 1
[8 empty] | 179678870.4213 |  |  |  |  | 2039730
435763.35
|  |  |  | 34463.19 |  |  |  | 53373277.9419
[8 empty] | 37696979.055 |  |  |  | 105.96
[8 empty] | 20915445.7875 |  |  |  |  | 150
[8 empty] | 118756522.5 |  |  |  |  | 15894
[8 empty] | 528534554.6573 | 486056843.0407
|  | A3 SRC |  | 6510.8
|  | A3 SRC 7th Ave plt |  | 42
|  | IJP |  |  |  |  | 4189.593 |  |  |  | A3 conc from IJP
|  |  | 7440.3 | 7440.3 | 0 |  | 161.5002 |  |  |  | 1 | 5519.85 | 5519.85
|  | A3 OPC | 14643.054 | 14542.314 | -100.74 |  | 4351.0932 |  |  |  | 178.5 | 11505.89 | 2053801.365
|  | A2 OPC | 95.207 | 79.167 | -16.04 | [5 empty] | 71 | 10955.89 | 777868.19
|  | A1 OPC | 4545.4134 | 4351.0932 | -194.3202 | [5 empty] | 637 | 11505.89 | 7329251.93
|  | Class B | 3189.525 | 3152.405 | -37.12 | [5 empty] | 887.5 |  | 10.1664
|  | D1 Conc | 1644.083 | 1644.083 | 0 | [5 empty] | A1 conc from IJP
|  | D2 Conc | 6009.524 | 6009.524 | -3.5574e-06 | [5 empty] | 5 | 8875.4 | 44377
|  | Lean | 1758.137 | 1637.137 | -121 | [5 empty] | 156.5002 | 8875.4 | 1389002
[5 empty] | -469.2202 | [5 empty] | 161.5002 |  | 1.4334
Lean conc from IJP
[11 empty] | 83 | 6632.95 | 550534.85
[11 empty] | 37 | 6029.95 | 223108.15
[11 empty] | 120 |  | 0.77364

## Steel Summary (hidden)
Steel Details
Ser | Description | Upto date |  | Upto Last Month |  | This Month |  | YDT Previous |  | YDT Uptodate
|  | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | From Other Proj | Issued to other Proj
1 | ASTM 615, GR-60 - 10mm | 119.628 | 30.2521 | 99.703 | 25.3764 | 19.925 | 4.8756 | 19.633 | 5.1735 | 39.558 | 10.0491 | 9.673
2 | ASTM 615, GR-60 - 12mm | 1190.385 | 295.7344 | 1122.04 | 279.2805 | 68.345 | 16.4539 | 319.24 | 83.0771 | 387.585 | 99.531 | 259.31 | -11.53
3 | ASTM 615, GR-60 - 16mm | 1351.066 | 332.9197 | 1367.736 | 332.927 | -16.67 | -0.007316 | 398.836 | 100.325 | 382.166 | 100.3177 | 148.836 | -16.64
4 | ASTM 615, GR-60 - 20mm | 234.146 | 51.2901 | 209.051 | 51.2901 | 25.095 | 0 | 64.351 | 19.9023 | 89.446 | 19.9023 | 68.069 | -8.463
5 | ASTM 615, GR-60 - 25mm | 1205.341 | 280.9654 | 1213.919 | 282.661 | -8.578 | -1.6956 | 89.14 | 22.3106 | 80.562 | 20.6149 | 50.604 | -33.558
6 | ASTM 615, GR-60 - 32mm | 1386.255 | 335.204 | 1386.255 | 335.204 | 0 | 4.5475e-13 | 126.745 | 32.6917 | 126.745 | 32.6917 | 51.815 | -24.98
| Total | 5486.821 | 1326.3657 | 5398.704 | 1306.739 | 88.117 | 19.6266 | 1017.945 | 263.4801 | 1106.062 | 283.1067

## Steel Consumption (hidden)
Steel Details
Ser | Description | Upto date |  | Upto Last Month |  | This Month |  | YDT Previous |  | YDT Uptodate
|  | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | From Other Proj | Issued to other Proj
1 | ASTM 615, GR-60 - 10mm | 78.8599 | 19.9424 | 75.7035 | 19.1907 | 3.1563 | 0.75178 | 40.9938 | 10.3753 | 44.1501 | 11.1271 | 9.673
2 | ASTM 615, GR-60 - 12mm | 975.5052 | 242.3505 | 918.702 | 224.8795 | 56.8033 | 17.471 | 292.7969 | 71.9219 | 349.6002 | 89.3929 | 259.31 | -11.53
3 | ASTM 615, GR-60 - 16mm | 1240.6745 | 305.7179 | 1127.5975 | 271.0768 | 113.0771 | 34.6411 | 348.7579 | 84.1059 | 461.835 | 118.747 | 148.836 | -16.64
4 | ASTM 615, GR-60 - 20mm | 170.9465 | 37.4462 | 166.8927 | 40.1717 | 4.0538 | -2.7255 | 81.3588 | 19.3308 | 85.4126 | 16.6053 | 68.069 | -8.463
5 | ASTM 615, GR-60 - 25mm | 1153.8047 | 268.9522 | 1153.8048 | 267.5666 | -0.0001044 | 1.3857 | 105.7245 | 24.4967 | 105.7244 | 25.8824 | 50.604 | -33.558
6 | ASTM 615, GR-60 - 32mm | 1363.0463 | 329.592 | 1354.0047 | 330.1866 | 9.0416 | -0.59467 | 260.3002 | 62.8599 | 269.3418 | 62.2652 | 51.815 | -24.98
| Total | 4982.837 | 1204.0012 | 4796.7051 | 1153.0719 | 186.1319 | 50.9293 | 1129.9323 | 273.0904 | 1316.0642 | 324.0198
4858.3778
124.4592
5486.821
503.984
9.185%

## Anx L
Anx "L"
LIST OF FIXED ASSETS
Const of 10th Avenue from IJP Road to Srinagar Highway, Islamabad
Ser | Category of Asset | Purchase Cost (Rs) | Depreciation for the Month (if applicable) | Depriciation up to Date | Depriciation Year to Date | Assets Value
1 | Plant and machinery
a | Porta cabin 20'x10'x9' | 2.108 | 0.058556 | 0.17567 | 0.17567 | 1.9323 | 0.058556
2 | Ofice Eqpt
a | Air Conditon
3 | Camp Development
a | NLC Ofices, Labortary, Labour Residence & Steel Yard | 10.364 |  |  |  | 10.364 |  | 0.49352 | 1.4806
4 | Computers and Peripheral Devices
a | Printer
5 | Funiture & Fixtures
a | Table
b | Chairs
c | Table | [7 empty] | 44335
d | Revolving Chair | [7 empty] | 7536.95
e | Sofa 5 Seater | [7 empty] | 51871.95
6 | Proj Insurance | 22.175 | 1.056 | 3.1679 | 3.1679 | 19.0071 |  | 1.056
Total (Rs in Million) |  | 34.647 | 1.1145 | 3.3435 | 3.3435 | 31.3035
288000000
2880000
Note on D9: Author: 0.529

## Anx M
Anx "M"
DETAILS OF LIABILITIES
#REF!
1 | Against Contractor |  |  | Amount (M)
|  | a. | Against vetted WD
|  |  | - Payment due | 0
- Retention money
|  | b. | Against Un-vetted WD
|  |  | - Payment due | #REF!
- Retention money
|  |  | - Earnest money | 0
|  | c. | Payable against Income Tax
|  | d. | Proj Maint Cost Funds
Sub Total
2 | Payables
|  | a. | Amount payable against supplies | 40.865
|  | b. | Amount payable against Services | 6.295
|  | c. | Payable to HQ against POL
|  | d. | Salaries payable to HQ - Contract Employees
|  | c. | Others
|  |  | Sub Total | 47.16
3 | Others
|  | a. | Mob Adv | 0
|  | b. | Any Other - Muster Roll | 0
|  | c. | Secure Advance | 0
|  |  | Sub Total | 0
|  |  | Grand Total | 47.16

## Sheet3 (hidden)
Uptodate
Lean Conc | 32.2851 | 8501.4098 | 274468.5457 | 0.27447 |  |  |  |  | 29.7051 | 11541.0109
A3 CONC | 198.4993 | 13012.3516 | 2582942.6201 | 2.5829 | Lean | 37 |  |  | 106.2193 | 41268.3208
A1 Conc | 255.5 | 11296.3798 | 2886225.0308 | 2.8862 | A1 | 255.5 |  |  | 255.5 | 99266.86
Class B | 296.75 | 10128.4681 | 3005622.895 | 3.0056 | A3 | 252 |  |  | 195.601 | 75994.9005
Previous |  |  |  | 0 | B | 296.75 |  |  |  | 228071.0922
Lean Conc | 18.8351 | 8501.4098 | 160124.5843 | 0.16012
A3 CONC | 24.63 | 13012.3516 | 320494.2187 | 0.32049
A1 Conc | 22.15 | 11296.3798 | 250214.8119 | 0.25021
Class B | 12.65 | 10128.4681 | 128125.1209 | 0.12813
0
This month |  |  |  | 0
Lean Conc | 13.45 | 8501.4098 | 114343.9614 | 0.11434
A3 CONC | 173.8693 | 13012.3516 | 2262448.4014 | 2.2624
A1 Conc | 233.35 | 11296.3798 | 2636010.2189 | 2.636
Class B | 284.1 | 10128.4681 | 2877497.7742 | 2.8775
[5 empty] | POL Nov 23 | [5 empty] | 204000 | 0
[5 empty] | Loader B950 | 760 | 800 | 1560 |  | 50 | 214000 | 10.7
[5 empty] | Loader E950 | 360 | 660 | 1020 |  | 49.93 | 225500 | 11.2592
[5 empty] | D/Cabin Ku 3125 | 220 | 130 | 350 |  | 6.15 | 225500 | 1.3868
[5 empty] | W/Bouzer | 60 | 120 | 180 |  | 21.8 | 225500 | 4.9159
[5 empty] | Excavator | 380 | 240 | 620 |  | 22.12 | 225500 | 4.9881
[5 empty] | Roller | 290 | 460 | 750 |  | 48.925 | 225500 | 11.0326
[5 empty] | TM E85510205 | 60 | 220 | 280 |  | 142.47 | 225500 | 32.127
[5 empty] | Gen 200 KVA | 300 | 290 | 590 |  | 46.6 | 225500 | 10.5083
[5 empty] | Gen 100 KVA | 145 | 350 | 495 |  | 51.11 | 225500 | 11.5253
[10 empty] | 61.23 | 225500 | 13.8074
[6 empty] | 2575 | 3270 |  |  | 37.24 | 225500 | 8.3976
[6 empty] | 304 | 297.6 |  |  | 19 | 214500 | 4.0755
[6 empty] | 782800 | 973152 |  |  | 31.11 | 225500 | 7.0153
[6 empty] | 1755952 |  |  |  | 587.685 |  | 131.739
1.756
|  | 2083.8368 | 2052.7886
|  | 7501.8125 | 7390.0391

## Steel Consumption March 24 (hidden)
Dia Wise Steel Qty for March 2024
Ser | Structure | Length (m) | RD | Nos | Dia of Steel Qty Each (Ton) | [5 empty] | Total Qty (Ton) | Remarks
[5 empty] | 10mm | 12mm | 16mm | 20mm | 25mm | 32mm
A | Test Piles
i | Test Pile - at Ramp (A) | 30 | 0+240 to 0+381 | 0 |  | 0 |  |  | 0 |  | 0
ii | Test Pile - At Ramp (B) 25M | 25 | 0+364.077 | 0 |  | 0 |  |  | 0 |  | 0
iii | Test Pile - Bridge 02 (I-9 & I-10) | 40 | 0+302 | 0 |  | 0 |  |  | 0 |  | 0
iv | Test Pile - Bridge 03 (I-9 & I-10) | 40 | 0+384 | 0 |  | 0 |  |  | 0 |  | 0
v | Test Pile - Niki Lai Br 01 | 30 | 0+618 to 0+708 | 0 |  | 0 |  |  | 0 |  | 0
vi | Test Pile - Niki Lai Br 01A | 30 | 0+147 to 0+238 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 2842.4045
vii | Test Pile - Railway Br | 28 | 1+302 to 1+477 | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 298.3556
B | Working Piles | [12 empty] | 1244.2154
i | Ramp A Abutment-02 Working Pile | 25 | 0+235 to 0+377 | 3 |  | 3.6702 | 0 |  | 9.7076 | 9.5925 | 22.9703 |  |  | 2518.3208
ii | Ramp B Pier-02 Working Pile | 26 | 0+363 to 0+712 | 1 |  | 0.76165 | 2.5444 |  | 0.20922 | 15.3921 | 18.9074
iii | Ramp B Pier-03 Working Pile | 26 | 0+363 to 0+712 | 2 |  | 1.5233 | 5.0888 |  | 0.41844 | 30.7842 | 37.8147
iv | Ramp B Pier 4B Working Pile | 27 | 0+363 to 0+712 | 3 |  | 1.8947 | 0 |  | 0.1363 | 29.113 | 31.144
v | Railway Bridge Pier 4 Working Pile | 27 | 1+302 to 1+477 | 8 |  | 2.7563 | 5.7436 |  | 0.81902 | 34.0417 | 43.3607
vi | Railway Bridge Pier 3 Working Pile | 27 | 1+302 to 1+477 | 6 |  | 2.0672 | 4.3077 |  | 0.61427 | 24.9925 | 31.9817
C | Girders
i | Ramp A | 35 | 0+235 to 0+377 | 1 | 0.0076 | 2.6791 | 0.78004 |  | 0.28209 |  | 3.7488 |  |  | 10 | 12 | 16 | 19 | 25 | Total
ii | Ramp B | 30 | 0+363 to 0+712 | 21 | 0.13755 | 51.9681 | 21.773 |  | 2.0519 |  | 75.9305 |  |  | 6.55 | 2473.78 | 1152.4 | 0 | 154.74 | 3787.47
D | Deck Slab
i | Nikki Lai BR-01A (Abutment 01 to Pier 01) | 30.1 | 0+166 to 0+227 | 1 |  | 13.242 | 18.253 | 0 | 0 |  | 31.495
E | MSE Panels
| S | - | - | 77 | 0.024 | 0.00668 |  |  |  |  | 2.3624
| Sy | - | - | 15 | 0.03263 | 0.00668 |  |  |  |  | 0.58965
| H10 | - | - | 3 | 0.01577 | 0.00579 |  |  |  |  | 0.06468
| H14 | - | - | 16 | 0.0216 | 0.00957 |  |  |  |  | 0.49872
| H16 | - | - | 10 | 0.02521 | 0.00668 |  |  |  |  | 0.3189
| H20 | - | - | 8 | 0.03149 | 0.00957 |  |  |  |  | 0.32848
| H23 | - | - | 4 | 0.03536 | 0.00957 |  |  |  |  | 0.17972
| By | - | - | 58 | 0.01337 | 0.00378 |  |  |  |  | 0.9947
F | Pile Cap
i | Bridge 02 (I-9 & I-10) |  | 0+302 | 0 |  |  | 0 |  | 0 | 0 | 0
G | Pier Shaft | [12 empty] | 635.8519 | 0 | 3860.706 | 33280.9113 | 37777.4692
i | Nikki Lae BR-01 Pier-01 Shaft-01 | 6.109 | 0+618 to 0+708 | 0 |  |  | 0 |  | 0 |  | 0 |  | 165.364 | 1089.759
ii | Nikki Lae BR-01 Pier-01 Shaft-02 | 6.429 | 0+618 to 0+708 | 0 |  |  | 0 |  | 0 |  | 0 |  | 174 | 1134.146
iii | Nikki Lae BR-01 Pier-01 Shaft-03 | 6.279 | 0+618 to 0+708 | 0 |  |  | 0 |  | 0 |  | 0 |  | 169.374 | 1113.34
iv | Nikki Lae BR-01 Pier-01 Shaft-04 | 6.249 | 0+618 to 0+708 | 0 |  |  | 0 |  | 0 |  | 0 |  | 169.374 | 1109.179
v | Nikki Lae BR-02 Pier-01 Shaft-01 | 1.204 | 0+618 to 0+708 | 0 |  |  | 0 |  | 0 |  | 0 |  | 32.573 | 375.066
vi | Nikki Lae BR-02 Pier-01 Shaft-02 | 1.169 | 0+618 to 0+708 | 0 |  |  | 0 |  | 0 |  | 0 |  | 32.573 | 370.212
vii | Nikki Lae BR-02 Pier-01 Shaft-03 | 1.239 | 0+618 to 0+708 | 0 |  |  | 0 |  | 0 |  | 0 |  | 32.573 | 379.921
viii | Nikki Lae BR-02 Pier-01 Shaft-04 | 1.41 | 0+618 to 0+708 | 0 |  |  | 0 |  | 0 |  | 0 |  | 39.205 | 403.779
| Nikki Lae BR-01A Pier-01 Shaft-1 to 4 | 7.909 | 0+166 to 0+227 | 0 |  |  | 0 |  | 0 |  | 0 |  | 215.18 | 1592.53
H | Retaining Wall
i | RD (0+183.3 to 0+198.28) |  |  | 0 |  |  | 0 | 0 | 0 |  | 0
ii | RD (0+163.34 to 0+183.3)-01 |  |  | 0 |  |  | 0 | 0 | 0 |  | 0
iii | RD (0+163.34 to 0+183.3)-02 |  |  | 0 |  |  | 0 |  | 0 |  | 0
[5 empty] | 0.34458 | 80.6208 | 58.4905 | 0 | 14.2389 | 143.9161 | 302.6903
[5 empty] | 0.34975 | 81.8301 | 59.3679 | 0 | 14.4524 | 146.0748 | 307.2307
[7 empty] | 0 |  | 0

## Cement (hidden)
Upto 31st March 2024
Ser | This Month |  | Uptodate
| Qty | Amount | Qty | Amount
1 | 654.04 | 16.1549 | 8385.753 | 25.3158

## Rate Analysis A3 SRC (hidden)
Rate Analysis
A3 Conc (SRC)
A | Material |  |  |  | Qty = 1 CM
Ser | Description | A/U | Qty | Rate | Amount
1 | Cement | Kg | 410 | 28.2 | 11562 |  | 6
2 | Sand | Cft | 14.67 | 85 | 1246.95 |  | 6
3 | Crush 10-20 mm | Cft | 14.51 | 100 | 1451 | 450 | 7
4 | Crush 20-25 mm | Cft | 9.18 | 100 | 918 |  | 6
5 | Admix | Kg | 5.28 | 110 | 580.8 | 24600 | 6
6 | Water | litres | 198 | 1 | 198
Total |  |  |  |  | 15956.75 |  | 6
6
|  | 700 | 15956.75 | 11169725 | 11.1697
|  | 1400 | 15956.75 | 22339450 | 22.3394

## Sheet1 (hidden)
217548 | 299949
228365 | 343749 |  |  | 915665
99380 | 98461 |  |  | 556600
177342 | 290097 |  |  | 4957770
177342 | 456489 |  |  | 433000
134999 | 293148 |  |  | 382000
171345 | 297475
173941 | 125478 |  |  | 7245035
155768 | 348557
381029 | 369949
171021 | 382930
209110 | 188265
127644 | 279863
129807 | 419840
287652 | 155249
59277 | 306344
159992 | 327113 | 41931 | 279565
87692 |  | 75000 | 68800
|  | 116931 | 348365
3149254 | 4982956

## Rate Analysis A3 OPC (hidden)
Rate Analysis
A3 Conc (OPC)
A | Material |  |  |  | Qty = 1 CM
Ser | Description | A/U | Qty | Rate | Amount
1 | Cement | Kg | 420 | 28.2 | 11844 | 6
2 | Sand | Cft | 14.0112 | 85 | 1190.9551 | 6
3 | Crush 10-20 mm | Cft | 13.0449 | 100 | 1304.4944 | 7
4 | Crush 20-25 mm | Cft | 7.1236 | 100 | 712.3596 | 6
5 | Admix | Kg | 5.3 | 110 | 583 | 6
6 | Water | litres | 193 | 1 | 193
Total |  |  |  |  | 15827.809 | 6
6
WD
| Nikki Lae 1 | 100 | 15827.809 | 1582780.8989 | 1.5828
| Bill no. 5 |  |  | 0 | 0
|  | 100 |  |  | 1.5828
|  | 204 | 15827.809 | 3228873.0337 | 3.2289

## Rate Analysis A2 OPC (hidden)
Rate Analysis
A2 Conc (OPC)
A | Material |  |  |  | Qty = 1 CM
Ser | Description | A/U | Qty | Rate | Amount
1 | Cement | Kg | 350 | 28.2 | 9870 |  |  |  | 6
2 | Sand | Cft | 15.46 | 85 | 1314.1 |  |  |  | 6
3 | Crush 10-20 mm | Cft | 15.25 | 100 | 1525 |  | 450 |  | 7
4 | Crush 20-25 mm | Cft | 9.72 | 100 | 972 |  |  |  | 6
5 | Admix | Kg | 4.83 | 110 | 531.3 |  |  |  | 6
6 | Water | litres | 193 | 1 | 193
Total |  |  |  |  | 14405.4 |  |  |  | 6
6
WD
| Nikki Lae 1 | 2 | 14405.4 | 28810.8 | 0.028811 | 45.07 | 18200 | 820274
[6 empty] | 45.5 | 18200 | 828100
[6 empty] | 50.6 | 18900 | 956340
[6 empty] | 141.17 |  | 2604714
18450.9032
18.4509

## Rate Analysis A1 OPC (hidden)
Rate Analysis
A1 Conc (OPC)
A | Material |  |  |  | Qty = 1 CM
Ser | Description | A/U | Qty | Rate | Amount
1 | Cement | Kg | 330 | 28.2 | 9306 |  |  |  | 6
2 | Sand | Cft | 18.119 | 85 | 1540.119 |  |  |  | 6
3 | Crush 10-20 mm | Cft | 16.2209 | 100 | 1622.0856 |  | 450 |  | 7
4 | Crush 20-25 mm | Cft | 8.8642 | 100 | 886.4198 |  |  |  | 6
5 | Admix | Kg | 4 | 110 | 440 |  |  |  | 6
6 | Water | litres | 193 | 1 | 193
Total |  |  |  |  | 13987.6244 |  |  |  | 6
6
[6 empty] | 45.07 | 18200 | 820274
[6 empty] | 45.5 | 18200 | 828100
|  | 50 | 13987.6244 | 699381.2218 | 0.69938 | 50.6 | 18900 | 956340
[6 empty] | 141.17 |  | 2604714
18450.9032
18.4509

## Rate Analysis D1 OPC (hidden)
Rate Analysis
D1 Conc (OPC)
A | Material |  |  |  | Qty = 1 CM
Ser | Description | A/U | Qty | Rate | Amount
1 | Cement | Kg | 500 | 28.2 | 14100 |  |  |  | 6
2 | Sand | Cft | 14.39 | 85 | 1223.15 |  |  |  | 6
3 | Crush 10-20 mm | Cft | 14.25 | 100 | 1425 |  | 450 |  | 7
4 | Crush 20-25 mm | Cft | 9.07 | 100 | 907 |  |  |  | 6
5 | Admix | Kg | 6 | 110 | 660 |  |  |  | 6
6 | Water | litres | 190 | 1 | 190
Total |  |  |  |  | 18505.15 |  |  |  | 6
6
| Panels | 70 | 18505.15 | 1295360.5 | 1.2954
[6 empty] | 45.07 | 18200 | 820274
|  | 125 | 18505.15 | 2313143.75 | 2.3131 | 45.5 | 18200 | 828100
[6 empty] | 50.6 | 18900 | 956340
[6 empty] | 141.17 |  | 2604714
18450.9032
18.4509

## Rate Analysis D2 OPC (hidden)
Rate Analysis
D2 Conc (OPC)
A | Material |  |  |  | Qty = 1 CM
Ser | Description | A/U | Qty | Rate | Amount
1 | Cement | Kg | 550 | 28.2 | 15510 |  |  |  | 6
2 | Sand | Cft | 13.88 | 85 | 1179.8 |  |  |  | 6
3 | Crush 10-20 mm | Cft | 13.69 | 100 | 1369 |  | 450 |  | 7
4 | Crush 20-25 mm | Cft | 8.72 | 100 | 872 |  |  |  | 6
5 | Admix | Kg | 6.6 | 110 | 726 |  |  |  | 6
6 | Water | litres | 198 | 1 | 198
Total |  |  |  |  | 19854.8 |  |  |  | 6
6
| Exp jt Br-03 | 350 | 19854.8 | 6949180 | 6.9492
[6 empty] | 45.07 | 18200 | 820274
|  | 662.5 | 19854.8 | 13153805 | 13.1538 | 45.5 | 18200 | 828100
[6 empty] | 50.6 | 18900 | 956340
[6 empty] | 141.17 |  | 2604714
18450.9032
18.4509

## Rate Analysis Class B (hidden)
Rate Analysis
Conc Class B(OPC)
A | Material |  |  |  | Qty = 1 CM
Ser | Description | A/U | Qty | Rate | Amount
1 | Cement | Kg | 275 | 28.2 | 7755 |  |  |  | 6
2 | Sand | Cft | 16.48 | 85 | 1400.8 |  |  |  | 6
3 | Crush 10-20 mm | Cft | 16.27 | 100 | 1627 |  | 450 |  | 7
4 | Crush 20-25 mm | Cft | 10.36 | 100 | 1036 |  |  |  | 6
5 | Admix | Kg | 3.03 | 110 | 333.3 |  |  |  | 6
6 | Water | litres | 171 | 1 | 171
Total |  |  |  |  | 12323.1 |  |  |  | 6
6
WD
| Bill 4d | 132
| Bill No. 6 |  |  |  |  | 45.07 | 18200 | 820274
|  | 45 | 12323.1 | 554539.5 | 0.55454 | 45.5 | 18200 | 828100
[6 empty] | 50.6 | 18900 | 956340
|  | 135 | 12323.1 | 1663618.5 | 1.6636 | 141.17 |  | 2604714
18450.9032
18.4509

## Rate Analysis Lean (hidden)
Rate Analysis
Lean (OPC)
A | Material |  |  |  | Qty = 1 CM
Ser | Description | A/U | Qty | Rate | Amount
1 | Cement | Kg | 210 | 28.2 | 5922 |  |  |  | 6
2 | Sand | Cft | 16.76 | 85 | 1424.6 |  |  |  | 6
3 | Crush 10-20 mm | Cft | 16.53 | 100 | 1653 |  | 450 |  | 7
4 | Crush 20-25 mm | Cft | 10.53 | 100 | 1053 |  |  |  | 6
6 | Water | litres | 179 | 1 | 179
Total |  |  |  |  | 10231.6 |  |  |  | 6
6
WD
Bill 6
| Br-03 |  |  |  |  | 45.07 | 18200 | 820274
|  | 46 | 10231.6 | 470653.6 | 0.47065 | 45.5 | 18200 | 828100
[6 empty] | 50.6 | 18900 | 956340
[6 empty] | 141.17 |  | 2604714
18450.9032
18.4509